## Распайка жгутов
Распайка жгутов EVT-PRE-20
Логический pinout; физическую длину, разъёмы и обжим сверить до заказа жгута.
Interface | Connector_Ref | Pin | Net | Direction_at_MAIN | Nominal_voltage | Current_class | Wire_rule | Shield_pair_rule | Keying_requirement | Release_status | Notes
MIC1 | J_MIC1 | 1 | 1V8_MIC | OUT | 1.8V | LOW | AWG28_or_larger | Route_with_GND | KEYED | LOGICAL_FROZEN | Same 6-pin physical order on all MIC connectors
MIC1 | J_MIC1 | 2 | GND | RETURN | 0V | LOW | AWG28_or_larger | Return_for_1V8_PDM_WAKE_CFG | KEYED | LOGICAL_FROZEN
MIC1 | J_MIC1 | 3 | PDM_CLK | OUT | 1.8V_logic | LOW | AWG28_or_larger | Twist_or_pair_with_GND_if_harness_long | KEYED | LOGICAL_FROZEN | Series damping footprint at source
MIC1 | J_MIC1 | 4 | PDM_DATA1 | IN | 1.8V_logic | LOW | AWG28_or_larger | Twist_or_pair_with_GND_if_harness_long | KEYED | LOGICAL_FROZEN
AAD_WAKE1 | J_MIC1 | 5 | MIC_WAKE1 | IN | 1.8V_logic | LOW | AWG28_or_larger | Route_with_GND_avoid_PDM_clk_crosstalk | KEYED | LOGICAL_FROZEN | T5838 AAD WAKE output preserved for low-power acoustic wake
AAD_CFG1 | J_MIC1 | 6 | AAD_CFG | OUT | 1.8V_one_wire | LOW | AWG28_or_larger | Route_with_GND_avoid_PDM_clk_crosstalk | KEYED | LOGICAL_FROZEN | Common T5838 THSEL one-wire configuration bus; same write applied to all four microphones
MIC2 | J_MIC2 | 1 | 1V8_MIC | OUT | 1.8V | LOW | AWG28_or_larger | Route_with_GND | KEYED | LOGICAL_FROZEN
MIC2 | J_MIC2 | 2 | GND | RETURN | 0V | LOW | AWG28_or_larger | Return_for_1V8_PDM_WAKE_CFG | KEYED | LOGICAL_FROZEN
MIC2 | J_MIC2 | 3 | PDM_CLK | OUT | 1.8V_logic | LOW | AWG28_or_larger | Twist_or_pair_with_GND_if_harness_long | KEYED | LOGICAL_FROZEN
MIC2 | J_MIC2 | 4 | PDM_DATA2 | IN | 1.8V_logic | LOW | AWG28_or_larger | Twist_or_pair_with_GND_if_harness_long | KEYED | LOGICAL_FROZEN
AAD_WAKE2 | J_MIC2 | 5 | MIC_WAKE2 | IN | 1.8V_logic | LOW | AWG28_or_larger | Route_with_GND_avoid_PDM_clk_crosstalk | KEYED | LOGICAL_FROZEN | T5838 AAD WAKE output
AAD_CFG2 | J_MIC2 | 6 | AAD_CFG | OUT | 1.8V_one_wire | LOW | AWG28_or_larger | Route_with_GND_avoid_PDM_clk_crosstalk | KEYED | LOGICAL_FROZEN | Common T5838 THSEL one-wire configuration bus
MIC3 | J_MIC3 | 1 | 1V8_MIC | OUT | 1.8V | LOW | AWG28_or_larger | Route_with_GND | KEYED | LOGICAL_FROZEN
MIC3 | J_MIC3 | 2 | GND | RETURN | 0V | LOW | AWG28_or_larger | Return_for_1V8_PDM_WAKE_CFG | KEYED | LOGICAL_FROZEN
MIC3 | J_MIC3 | 3 | PDM_CLK | OUT | 1.8V_logic | LOW | AWG28_or_larger | Twist_or_pair_with_GND_if_harness_long | KEYED | LOGICAL_FROZEN
MIC3 | J_MIC3 | 4 | PDM_DATA3 | IN | 1.8V_logic | LOW | AWG28_or_larger | Twist_or_pair_with_GND_if_harness_long | KEYED | LOGICAL_FROZEN
AAD_WAKE3 | J_MIC3 | 5 | MIC_WAKE3 | IN | 1.8V_logic | LOW | AWG28_or_larger | Route_with_GND_avoid_PDM_clk_crosstalk | KEYED | LOGICAL_FROZEN | T5838 AAD WAKE output
AAD_CFG3 | J_MIC3 | 6 | AAD_CFG | OUT | 1.8V_one_wire | LOW | AWG28_or_larger | Route_with_GND_avoid_PDM_clk_crosstalk | KEYED | LOGICAL_FROZEN | Common T5838 THSEL one-wire configuration bus
MIC4 | J_MIC4 | 1 | 1V8_MIC | OUT | 1.8V | LOW | AWG28_or_larger | Route_with_GND | KEYED | LOGICAL_FROZEN
MIC4 | J_MIC4 | 2 | GND | RETURN | 0V | LOW | AWG28_or_larger | Return_for_1V8_PDM_WAKE_CFG | KEYED | LOGICAL_FROZEN
MIC4 | J_MIC4 | 3 | PDM_CLK | OUT | 1.8V_logic | LOW | AWG28_or_larger | Twist_or_pair_with_GND_if_harness_long | KEYED | LOGICAL_FROZEN
MIC4 | J_MIC4 | 4 | PDM_DATA4 | IN | 1.8V_logic | LOW | AWG28_or_larger | Twist_or_pair_with_GND_if_harness_long | KEYED | LOGICAL_FROZEN
AAD_WAKE4 | J_MIC4 | 5 | MIC_WAKE4 | IN | 1.8V_logic | LOW | AWG28_or_larger | Route_with_GND_avoid_PDM_clk_crosstalk | KEYED | LOGICAL_FROZEN | T5838 AAD WAKE output
AAD_CFG4 | J_MIC4 | 6 | AAD_CFG | OUT | 1.8V_one_wire | LOW | AWG28_or_larger | Route_with_GND_avoid_PDM_clk_crosstalk | KEYED | LOGICAL_FROZEN | Common T5838 THSEL one-wire configuration bus
MAIN_PWR | J_PWR1 | 1 | 3V8_MODEM | IN | 3.8V | HIGH | AWG18_0.75mm2_Molex430300038 | Dedicated_return_pin_2 | KEYED_LATCH | LOGICAL_FROZEN | Exact selected Micro-Fit power terminal; validate burst current and harness temperature
MAIN_PWR | J_PWR1 | 2 | GND_MODEM | RETURN | 0V | HIGH | AWG18_0.75mm2_Molex430300038 | Dedicated_return_for_3V8 | KEYED_LATCH | LOGICAL_FROZEN | Exact selected Micro-Fit power terminal
MAIN_PWR | J_PWR1 | 3 | 3V3_DIGITAL | IN | 3.3V | MEDIUM | AWG18_0.75mm2_Molex430300038 | Dedicated_return_pin_4 | KEYED_LATCH | LOGICAL_FROZEN | Exact selected Micro-Fit power terminal; conservative common harness standard
MAIN_PWR | J_PWR1 | 4 | GND_DIGITAL | RETURN | 0V | MEDIUM | AWG18_0.75mm2_Molex430300038 | Dedicated_return_for_3V3 | KEYED_LATCH | LOGICAL_FROZEN | Exact selected Micro-Fit power terminal
MAIN_PWR | J_PWR1 | 5 | 1V8_MIC | IN | 1.8V | LOW | AWG18_0.75mm2_Molex430300038 | Dedicated_return_pin_6 | KEYED_LATCH | LOGICAL_FROZEN | Remain powered while T5838 AAD monitoring is armed; exact selected Micro-Fit power terminal
MAIN_PWR | J_PWR1 | 6 | GND_MIC | RETURN | 0V | LOW | AWG18_0.75mm2_Molex430300038 | Dedicated_return_for_1V8 | KEYED_LATCH | LOGICAL_FROZEN | Exact selected Micro-Fit power terminal
MAIN_PWR | J_PWR1 | 7 | PWR_GOOD | IN | 3.3V_logic | LOW | AWG20_to_24_Molex430300001 | Pair_with_logic_ground_if_needed | KEYED_LATCH | LOGICAL_FROZEN | Control terminal 430300001; power-side output to MAIN
MAIN_PWR | J_PWR1 | 8 | FAULT | IN | 3.3V_logic | LOW | AWG20_to_24_Molex430300001 | Pair_with_logic_ground_if_needed | KEYED_LATCH | LOGICAL_FROZEN | Control terminal 430300001; aggregate power-side fault/alert output to MAIN
MAIN_PWR | J_PWR1 | 9 | EN_MODEM | OUT | 3.3V_logic | LOW | AWG20_to_24_Molex430300001 | Pair_with_logic_ground_if_needed | KEYED_LATCH | LOGICAL_FROZEN | Control terminal 430300001; default safe OFF
MAIN_PWR | J_PWR1 | 10 | EN_AUX | OUT | 3.3V_logic | LOW | AWG20_to_24_Molex430300001 | Pair_with_logic_ground_if_needed | KEYED_LATCH | LOGICAL_FROZEN | Control terminal 430300001; controls auxiliary rails policy while AAD requires 1V8_MIC available
MAIN_PWR | J_PWR1 | 11 | I2C2_SCL | BIDIR_OD | 3.3V_logic | LOW | AWG20_to_24_Molex430300001 | Route_with_GND_DIGITAL_keep_short | KEYED_LATCH | LOGICAL_FROZEN | 100 kHz Rev.A power/sensor I2C; pull-ups are on PCB-MAIN; INA226 is on PCB-PWR
MAIN_PWR | J_PWR1 | 12 | I2C2_SDA | BIDIR_OD | 3.3V_logic | LOW | AWG20_to_24_Molex430300001 | Route_with_GND_DIGITAL_keep_short | KEYED_LATCH | LOGICAL_FROZEN | 100 kHz Rev.A power/sensor I2C; pull-ups are on PCB-MAIN; INA226 address 0x40
SWD | J_SWD | 1 | VTREF | IN | 3.3V | LOW | Fixture_pogo_or_AWG28 | No_shield | KEYED_OR_FIXTURE | LOGICAL_FROZEN
SWD | J_SWD | 2 | SWDIO | BIDIR | 3.3V_logic | LOW | Fixture_pogo_or_AWG28 | Short | KEYED_OR_FIXTURE | LOGICAL_FROZEN
SWD | J_SWD | 3 | SWCLK | IN | 3.3V_logic | LOW | Fixture_pogo_or_AWG28 | Short | KEYED_OR_FIXTURE | LOGICAL_FROZEN
SWD | J_SWD | 4 | NRST | IN | 3.3V_logic | LOW | Fixture_pogo_or_AWG28 | Short | KEYED_OR_FIXTURE | LOGICAL_FROZEN
SWD | J_SWD | 5 | GND | RETURN | 0V | LOW | Fixture_pogo_or_AWG28 | Reference | KEYED_OR_FIXTURE | LOGICAL_FROZEN
PWR_INPUT | J_PWR1_IN | 1 | VBAT_PLUS | IN | 10.0_to_14.6V_provisional | HIGH | AWG18_0.75mm2_Molex430300038 | Dedicated_return_pin_2 | KEYED_HIGH_CURRENT | LOGICAL_FROZEN | Selected Micro-Fit terminal is 18 AWG only; 5 A capture envelope and final thermal/fault review required
PWR_INPUT | J_PWR1_IN | 2 | VBAT_MINUS | RETURN | 0V | HIGH | AWG18_0.75mm2_Molex430300038 | Dedicated_return_for_VBAT | KEYED_HIGH_CURRENT | LOGICAL_FROZEN | Selected Micro-Fit terminal is 18 AWG only; final connector thermal test required

## Соединения
Межблочные соединения
Источником является проектный реестр межблочных соединений; открытые интерфейсы отмечены в статусе.
Link_ID | From | From_Ref | To | To_Ref | Signals | Electrical_Domain | Connector_Status | Cable_Status | Required_Protection | Design_Status | Verification
LNK-001 | SLD_Tech_SLP080S_12M | PV_OUT | Victron_SmartSolar_75_10 | PV_IN | PV+;PV- | 22.52V_Voc_4.56A_Isc_STC | CONTROLLER_TERMINAL_AND_PANEL_CONNECTOR_OPEN | OPEN_GAUGE_LENGTH | Polarized IP connector fuse or breaker per selected controller | SELECTED_EVT_CANDIDATES_PHYSICAL_INTERFACE_OPEN | Polarity cold Voc Isc Pmax insulation thermal connector and pull
LNK-002 | Victron_SmartSolar_75_10 | BAT_OUT | RELiON_RB40 | M8_TERMINALS | BAT+;BAT- | 12.8V_up_to_10A | CONTROLLER_TERMINAL_TO_M8_RING_OPEN | OPEN_GAUGE_LENGTH | Battery-side fuse reverse current control and 0C low-temperature inhibit | SELECTED_EVT_CANDIDATES_PHYSICAL_INTERFACE_OPEN | Charge profile configuration export cutoff reverse current quiescent thermal and reconnect
LNK-003 | RELiON_RB40 | M8_TERMINALS | PCB_PWR | J_PWR1_IN | VBAT+;VBAT- | 10.0_to_14.6V_provisional_transients_TBD | MICRO_FIT_2P_430450213_SELECTED | 18AWG_0.75mm2_TERMINAL_430300038 | Fuse near battery M8 terminal reverse polarity TVS and current limit | SCHEMATIC_PENDING | Polarity surge short fuse coordination connector thermal cold behavior and temperature
LNK-004 | PCB_PWR | J_MAIN_PWR | PCB_MAIN | J_PWR1 | 3V8_MODEM;GND_MODEM;3V3_DIGITAL;GND_DIGITAL;1V8_MIC;GND_MIC;PWR_GOOD;FAULT;EN_MODEM;EN_AUX;I2C2_SCL;I2C2_SDA | Mixed_power_and_3V3_logic_I2C | MICRO_FIT_12P_430451202_ELECTRICAL_SELECTED | 18AWG_power;20-24AWG_control_I2C | Default-safe enables; dedicated returns; keyed connector; I2C pull-ups on PCB-MAIN; optional source series damping footprints | SCHEMATIC_PENDING | Pin-by-pin continuity; load step; brownout; fault injection; AAD rail-state; INA226 0x40 readout/calibration; I2C rise-time at final harness length
LNK-005 | PCB_MAIN | J_MIC1 | PCB_MIC_1 | J1 | 1V8_MIC;GND;PDM_CLK;PDM_DATA1;MIC_WAKE1;AAD_CFG | 1V8_logic_power | MOLEX_PICO_LOCK_6P_5040500691_SELECTED | OPEN_EQUALIZED_LENGTH | ESD EMI series termination strain relief WAKE integrity and THSEL one-wire timing per SI review | SCHEMATIC_PENDING | Mapping delay noise phase AAD wake latency THSEL configuration and false-wake test
LNK-006 | PCB_MAIN | J_MIC2 | PCB_MIC_2 | J1 | 1V8_MIC;GND;PDM_CLK;PDM_DATA2;MIC_WAKE2;AAD_CFG | 1V8_logic_power | MOLEX_PICO_LOCK_6P_5040500691_SELECTED | OPEN_EQUALIZED_LENGTH | ESD EMI series termination strain relief WAKE integrity and THSEL one-wire timing per SI review | SCHEMATIC_PENDING | Mapping delay noise phase AAD wake latency THSEL configuration and false-wake test
LNK-007 | PCB_MAIN | J_MIC3 | PCB_MIC_3 | J1 | 1V8_MIC;GND;PDM_CLK;PDM_DATA3;MIC_WAKE3;AAD_CFG | 1V8_logic_power | MOLEX_PICO_LOCK_6P_5040500691_SELECTED | OPEN_EQUALIZED_LENGTH | ESD EMI series termination strain relief WAKE integrity and THSEL one-wire timing per SI review | SCHEMATIC_PENDING | Mapping delay noise phase AAD wake latency THSEL configuration and false-wake test
LNK-008 | PCB_MAIN | J_MIC4 | PCB_MIC_4 | J1 | 1V8_MIC;GND;PDM_CLK;PDM_DATA4;MIC_WAKE4;AAD_CFG | 1V8_logic_power | MOLEX_PICO_LOCK_6P_5040500691_SELECTED | OPEN_EQUALIZED_LENGTH | ESD EMI series termination strain relief WAKE integrity and THSEL one-wire timing per SI review | SCHEMATIC_PENDING | Mapping delay noise phase AAD wake latency THSEL configuration and false-wake test
LNK-009 | PCB_MAIN | U8 | BG95 | U8 | UART_TX;UART_RX;PWRKEY;RESET_N;STATUS;DTR;RI;VBAT;GND | Modem_1V8_logic_3V8_power | ON_BOARD | ON_BOARD | Level translation bulk decoupling ESD and RF keepout | OPEN_SCHEMATIC | Attach TLS sleep wake reset and LTE burst
LNK-010 | BG95 | U8 | Cellular_SMA_bulkhead | AE1_BH | RF_CELL | 50_ohm | HIROSE_UFL_PLUS_CAB01035_SMAF_CANDIDATE | CAB01035_150MM_LENGTH_TEMP_MATE_OPEN | ESD matching no-load policy bend radius strain relief and sealed bulkhead | SELECTED_EVT_CANDIDATE_RF_LAYOUT_OPEN | VNA pigtail loss mate retention conducted power and enclosure desense
LNK-011 | PCB_MAIN | U9 | MAX_M10S | U9 | UART_TX;UART_RX;TIMEPULSE;RESET_N;VCC;GND | 3V3 | ON_BOARD | ON_BOARD | Backup supply filtering ESD and RF keepout | OPEN_SCHEMATIC | Cold warm fix PPS offset spoof jam and concurrent LTE
LNK-012 | MAX_M10S | U9 | GNSS_SMA_bulkhead | AE2_BH | RF_GNSS_BIASED | 50_ohm | HIROSE_UFL_PLUS_CAB01035_SMAF_CANDIDATE | CAB01035_150MM_LENGTH_TEMP_MATE_OPEN | Bias supervisor ESD DC block SAW bend radius strain relief and sealed bulkhead | SELECTED_EVT_CANDIDATE_RF_LAYOUT_OPEN | VNA pigtail loss 3.3 V bias current fault response sensitivity fix PPS and coexistence
LNK-013 | PCB_MAIN | U10 | LoRa_module | U10 | SPI_SCK;SPI_MISO;SPI_MOSI;NSS;DIO1;BUSY;RESET_N;TXEN;RXEN;VCC;GND | 3V3 | ON_BOARD | ON_BOARD | TXEN and RXEN separately controlled with LOW pull-down defaults; DIO2 NC; safe reset and CLOSE state | OPEN_SCHEMATIC | Identity TCXO sleep RX conducted TX and mutual exclusion only after signed profile approval
LNK-014 | LoRa_module | U10 | LoRa_SMA_bulkhead | AE3_BH | RF_LORA | 50_ohm | HIROSE_UFL_PLUS_CAB01035_SMAF_CANDIDATE | CAB01035_150MM_LENGTH_TEMP_MATE_OPEN | ESD pi matching no-load policy bend radius strain relief and sealed bulkhead | SELECTED_EVT_CANDIDATE_RF_LAYOUT_OPEN | VNA pigtail loss frequency power sensitivity coexistence and RU868 profile
LNK-015 | PCB_MAIN | U11 | Raytac_MDBT50Q_P1MV2 | U11 | UART_TX;UART_RX;BLE_EN;BLE_DFU_REQ;VCC;GND | 3V3 | ON_BOARD | ON_BOARD | Default disable authenticated service and PCB antenna keepout | OPEN_SCHEMATIC | Authenticated pairing GATT OTA sleep current enclosure RF and separate nRF SWD recovery
LNK-016 | PCB_MAIN | U2 | QSPI_NOR | U2 | CS_N;CLK;IO0;IO1;IO2;IO3;VCC;GND | 3V3 | ON_BOARD | ON_BOARD | Series damping decoupling and boot-safe state | OPEN_SCHEMATIC | ID erase write read power-loss endurance
LNK-017 | PCB_MAIN | J12 | Industrial_microSD | U12 | CLK;CMD;D0;D1;D2;D3;DET;VCC;GND | 3V3 | GCT_MEM2052_00_195_00_A | ON_BOARD | ESD current limit pull resistors and controlled removal policy | ELECTRICAL_AUTHORITY_FROZEN_SCHEMATIC_PENDING | CID full write read detect power-loss recovery; exact contacts in PCB_MAIN_CONNECTOR_FIXTURE_PIN_AUTHORITY_REV_A.csv
LNK-018 | PCB_MAIN | J11 | Service_USB_C | USB2_device_host_cable | VBUS;D+;D-;CC1;CC2;GND;SHIELD | USB_5V_sense_and_3V3_logic | GCT_USB4105_GF_A_120 | EXTERNAL_USB_C_CABLE | USB ESD separate CC Rd sense-only VBUS and controlled shield bond | ELECTRICAL_AUTHORITY_FROZEN_SCHEMATIC_PENDING | STM32 enumeration system-memory recovery ESD connector orientation and environmental limit; never shared with BG95 USB
LNK-019 | PCB_MAIN | TP_MCU_SWD | Programming_fixture | Pogo_SWD | SWDIO;SWCLK;NRST;VTREF;GND | 3V3 | TEST_PADS_5P | FIXTURE_POGO | Protected access and sense-only VTREF | ELECTRICAL_AUTHORITY_FROZEN_PLACEMENT_PENDING | Connect program readback protection and cycle test; exact contact map fixed
LNK-020 | PCB_MAIN | TP_EOL | EOL_fixture | Pogo_AUX | RAIL_SENSE;TEST_UART;PWR_GOOD;FAULT;BOOT0;REV_STRAPS;I2C2;GND | Mixed_3V3_3V8_1V8 | TEST_PADS_13P | FIXTURE_POGO | Protected high-impedance sense controlled BOOT0 and guarded open-drain I2C | ELECTRICAL_AUTHORITY_FROZEN_PLACEMENT_PENDING | Known-fault coverage INA226 calibration and MSA; exact 13-contact map fixed
LNK-021 | BG95 | U8 | SIM_mux | U13 | USIM_VDD;USIM_RST;USIM_CLK;USIM_DATA;USIM_GND | 1V8_USIM | ON_BOARD | ON_BOARD | Short guarded traces series tuning pads decoupling and high-Z disable | OPEN_SCHEMATIC | Signal integrity leakage levels powered-off isolation and ESD
LNK-022 | SIM_mux | U13 | Nano_SIM_slot_1 | J_SIM1 | SIM1_VDD;SIM1_RST;SIM1_CLK;SIM1_DATA;GND | 1V8_USIM | TE_2336582_1_PROCUREMENT_RISK | ON_BOARD | Low-capacitance TVS local bypass RF filtering and service-cover access | OPEN_SCHEMATIC | ICCID slot mapping hot-plug disabled 100 switch cycles ESD and second-source validation
LNK-023 | SIM_mux | U13 | Nano_SIM_slot_2 | J_SIM2 | SIM2_VDD;SIM2_RST;SIM2_CLK;SIM2_DATA;GND | 1V8_USIM | TE_2336582_1_PROCUREMENT_RISK | ON_BOARD | Low-capacitance TVS local bypass RF filtering and service-cover access | OPEN_SCHEMATIC | ICCID slot mapping hot-plug disabled 100 switch cycles ESD and second-source validation
LNK-024 | STM32U585 | U1 | SIM_mux_and_slots | U13;J_SIM1;J_SIM2 | SIM_MUX_SEL;SIM_MUX_EN;SIM1_DET;SIM2_DET | 3V3_GPIO_with_1V8_compatible_mux_control | ON_BOARD | ON_BOARD | Boot-safe pull states and no slot switching while BG95 powered | OPEN_CUBEMX | Boot brownout unauthorized command and safe-switch state machine
LNK-025 | PCB_MIC_1..4 | MIC_WAKE1..4_AAD_CFG | STM32U585 | PA8_MIC_WAKE_PA15_AAD_CFG | MIC_WAKE1;MIC_WAKE2;MIC_WAKE3;MIC_WAKE4 -> U17 OR -> U18 level shift -> PA8 MIC_WAKE; PA15 -> U7 level shift -> shared AAD_CFG -> pin6 of all four 6P MIC harnesses | 1V8_to_3V3_and_3V3_to_1V8 | ON_BOARD_PLUS_6P_PICO_LOCK_HARNESSES | FOUR_EQUALIZED_6P_HARNESSES | SN74LVC32APWR at 1.8 V plus SN74AXC1T45DRLR to 3.3 V for WAKE; SN74AXC8T245 channel for AAD_CFG; defined boot-safe states | SCHEMATIC_PENDING | AAD threshold configuration wake edge false-wake power sequencing Stop-mode wake THSEL write timing and measured S0 current
LNK-026 | PCB_MAIN | J13 | Normally_closed_tamper_loop | External_tamper_switch | TAMPER_IN;GND | 3V3_contact | Molex_504050_0291 | Molex_504051_0201_harness | Pull-up debounce and connector-side ESD | ELECTRICAL_AUTHORITY_FROZEN_MECHANICS_PENDING | Closed secure and open alarm/cable-break behavior; exact two-contact map fixed
LNK-027 | BG95 | U8 | Cellular_USB_recovery_fixture | TP_CELL_USB | CELL_USB_VBUS;CELL_USB_DP;CELL_USB_DM;GND_MODEM | USB_fixture_only | TEST_PADS_4P | FIXTURE_POGO | Isolated USB protection and no connection to J11 | ELECTRICAL_AUTHORITY_FROZEN_PLACEMENT_PENDING | Modem USB recovery enumeration and isolation test
LNK-028 | BG95 | U8 | Cellular_debug_recovery_fixture | TP_CELL_DBG | U8_VDD_EXT_1V8;CELL_DBG_TXD_1V8;CELL_DBG_RXD_1V8;CELL_USB_BOOT_1V8;GND_MODEM | 1V8_logic | TEST_PADS_5P | FIXTURE_POGO | High-impedance VREF-gated debug and current-limited recovery-only USB_BOOT | ELECTRICAL_AUTHORITY_FROZEN_PLACEMENT_PENDING | Debug communication USB recovery boot sequencing and normal-low safety test
LNK-029 | RELiON_RB40 | BT1_BODY_AND_M8 | Victron_SmartSolar_75_10 | SCC075010060R | BAT_TEMP;BAT_VOLTAGE | VE_Smart_Bluetooth | SBS050150200_M10_EYELETS_SELECTED_CANDIDATE | 0.45M_LEADS_10M_WIRELESS_RANGE | Approved washer and retention stack on RB40 M8 terminals plus sensor attachment and network fail-state review | SELECTED_EVT_CANDIDATE_ENVIRONMENTAL_NETWORK_OPEN | Eyelet retention torque pairing retention actual-temperature reception cutoff at 0 C resume above 0.5 C -10..60 C device limit and cold soak
LNK-030 | Cellular_SMA_bulkhead | AE1_BH | Taoglas_G30_B_108111 | ANT_CELL | RF_CELL | 50_ohm | SMA_NORMAL_POLARITY | G30_INTEGRAL_1M_CABLE_CANDIDATE | Weather seal connector torque strain relief lightning and installation policy | SELECTED_EVT_CANDIDATE_INSTALLED_RF_OPEN | Installed VSWR cable loss BG95-M3 bands attach sensitivity and LTE/RU868/GNSS coexistence
LNK-031 | GNSS_SMA_bulkhead | AE2_BH | Taoglas_AA_166_A_301111 | ANT_GNSS | RF_GNSS_BIASED | 50_ohm | SMA_NORMAL_POLARITY | AA166_INTEGRAL_3M_RG174_CANDIDATE | Weather seal connector torque mounting plane strain relief and antenna bias limit | SELECTED_EVT_CANDIDATE_INSTALLED_RF_OPEN | Current at 3.3 V at most 50 mA sensitivity fix PPS cable loss and transmitter coexistence
LNK-032 | LoRa_SMA_bulkhead | AE3_BH | Taoglas_TI_89_B_2111W | ANT_LORA | RF_LORA | 50_ohm | SMA_NORMAL_POLARITY | DIRECT_TERMINAL_ANTENNA | Weather seal connector torque mechanical support and no-load policy | SELECTED_EVT_CANDIDATE_INSTALLED_RF_OPEN | Installed VSWR conducted power sensitivity range and RU868 radiated compliance

## Маршрут сборки
Маршрут сборки станций
Статусы OPEN сохраняются до фактической сборки и записи доказательств.
Step | Gate | Operation | Applies_To | Prerequisite | Equipment_or_Document | Acceptance | Evidence | Rework_or_Hold | Status
MFG-010 | QG0 | Verify released manufacturing bundle | LOT | SHA256 manifest available | Release index and verifier | All hashes match and no OPEN blocker authorized for build | Verification log | HOLD | OPEN
MFG-020 | QG0 | Verify materials and deviations | LOT | Incoming inspection completed | BOM AVL IC records NCR log | All items accepted or deviation signed | Material release record | HOLD | OPEN
MFG-030 | QG0 | Select lot and assign serials travellers and housing plan | 20_SELECTED_EVT_UNITS | EVT-20 selected and serial/housing registers controlled | EVT_LOT_SELECTION LOT_SERIAL_REGISTER HOUSING_LOT_PLAN and traveller | DIO-EVT-001 through DIO-EVT-020 assigned with no duplicates; all primary housings vacuum cast; 3D fallback controlled | Selection plus serial and housing registers | HOLD | PARTIAL_SELECTION_COMPLETE_TRAVELLERS_PENDING
MFG-040 | QG1 | Stencil paste placement and reflow | PCB_MAIN_PCB_PWR_PCB_MIC | Released Gerber PnP BOM stencil and profile | Printer placer oven thermocouples | Profile within frozen paste limits and traceable batch | Reflow profile plus machine exports | Approved rework only | OPEN
MFG-050 | QG1 | AOI visual and X-ray | ALL_PCBA | Reflow complete | AOI microscope X-ray plan | IC-004 and IC-005 accepted | Images and defect log | Rework then repeat inspection | OPEN
MFG-060 | QG1 | Bare power resistance check | ALL_PCBA | Inspection accepted | DMM current-limited supply | No rail-to-ground short against released limits | Measurements | HOLD and diagnose | OPEN
MFG-070 | QG1 | First power with current limit | PCB_MAIN_PCB_PWR | Resistance accepted | Bench supply logger thermal camera | No latch-up overheating or current limit event | Power log plus thermal image | HOLD and diagnose | OPEN
MFG-080 | QG1 | Program immutable boot foundation | PCB_MAIN | First power accepted | Trusted programmer signed release manifest | Readback version and protection state match release | Programmer log by serial | Scrap or controlled recovery | OPEN
MFG-090 | QG1 | Program station and coprocessor test builds | PCB_MAIN | Boot foundation accepted | Programmer and manifests | Hashes and versions match selected release | Programmer log | Repeat only under work instruction | OPEN
MFG-100 | QG1 | PCB_MAIN boundary scan and interface self-test | PCB_MAIN | Test firmware loaded | EOL fixture and self-test | All fitted interfaces including both SIM slots enumerate and test points pass | Machine-readable log | Rework and rerun full step | OPEN
MFG-110 | QG1 | PCB_PWR load and protection test | PCB_PWR | First power accepted | Electronic load surge fixtures and thermal camera | All rails protection and temperature within frozen limits | CSV waveforms and thermal images | HOLD and diagnose | OPEN
MFG-120 | QG1 | PCB_MIC individual acoustic test | PCB_MIC | Visual inspection accepted | Calibrated speaker reference mic fixture | Identity sensitivity noise and phase within frozen limits | Per-board calibration CSV | Reject or approved rework | OPEN
MFG-130 | QG1 | Build and verify harnesses | HARNESS | Incoming accepted | Harness tester and drawing | 100 percent continuity polarity labels and length pass | Tester export | Rework then full retest | OPEN
MFG-140 | QG1 | Install PCB and antennas in electronics module | 20_units | Subassemblies accepted | Assembly drawing torque tools ESD bench | No interference; antennas and coax routing match drawing | Traveller photos and torques | Disassemble under controlled instruction | OPEN
MFG-150 | QG1 | Assemble four-microphone geometry | 20_units | Four accepted PCB_MIC and housing parts | Geometry jig and calibrated measurement | Triangle sides and MIC4 offset within released tolerance | Measurements plus photo | Adjust or replace parts | OPEN
MFG-160 | QG1 | Install seals membranes and vents | 20_units | Housing parts accepted | Assembly drawing gauges and clean bench | Correct lot orientation compression and clean acoustic ports | Lot refs plus close-up photos | Replace single-use seals | OPEN
MFG-170 | QG1 | Assemble lower power module | 20_units | Battery MPPT PCB_PWR accepted | Insulated tools fuse and torque plan | Polarity fuse BMS MPPT and strain relief correct | Traveller plus torque values | HOLD on any polarity conflict | OPEN
MFG-180 | QG1 | Join modules and protective earth if applicable | 20_units | Upper and lower modules complete | Released interconnect drawing and DMM | Connector keying continuity insulation and fuse correct | Continuity record | HOLD and diagnose | OPEN
MFG-190 | QG1 | Trusted provisioning | 20_units | Hardware identity stable | Offline provisioning station and MFG-003 procedure | Unique serial IDs keys and certificates installed and verified | Controlled provisioning receipt | Zeroize and reprovision only by authorization | OPEN
MFG-200 | QG1 | Apply labels and QR | 20_units | Provisioning accepted | Released label artwork and scanner | Human text and QR resolve same serial HW region and device ID | Scan log plus photo | Replace label and rescan | OPEN
MFG-210 | QG2 | Run 100 percent EOL | 20_units | Fully assembled unit | EOL fixture network simulators RF loads and EOL spec | All mandatory EOL tests PASS with original logs | EOL bundle by serial | Rework then full EOL rerun | OPEN
MFG-220 | QG2 | Leak test before live outdoor exposure | 20_units | EOL electrical safe | Pressure decay or approved leak fixture | Meets frozen enclosure-specific limit | Leak curve | HOLD and inspect seals | OPEN
MFG-230 | QG2 | Final visual and configuration audit | 20_units | EOL and leak accepted | Traveller serial register manifests | No damage; all identifiers and configuration mutually consistent | Final checklist and photos | HOLD | OPEN
MFG-240 | QG2 | Close traveller and unit passport | 20_units | All steps accepted | Controlled records | No blank mandatory field and evidence paths resolve | Signed traveller and passport | HOLD | OPEN
MFG-250 | QG2 | Pack for EVT transport | 20_units | Unit released | Packing instruction ESD caps battery rules | Correct accessories protection state and labels | Packing photo and pack list | Repack | OPEN
MFG-260 | QG2 | Lot release review | LOT | All records for the selected 4 10 or 20-unit lot closed | Lot review board | Zero unexplained missing selected-lot unit; deviations dispositioned | Lot release minutes | HOLD | OPEN

## Входной контроль
Входной контроль
Исходный план проекта.
IC_ID | Incoming_Item | Lot_Definition | Control | Sample | Acceptance | Equipment | Evidence | Failure_Action | Status
IC-001 | Bare PCB each revision | One fabrication batch | Commercial receipt reconciliation | ALL_SHIPMENTS_DOCUMENT_RECONCILIATION | Purchase-order line revision quantity and visible shipping condition agree | Document review | Purchase order and packing slip | Hold only the discrepant shipment line and resolve with supplier | OPEN
IC-002 | Bare PCB each revision | One fabrication batch | Supplier electrical net-test evidence | 100_PERCENT_SUPPLIER | All boards supplier e-tested and report references the released netlist | Net-test report | Report identifier and hash | Stop the affected fabrication batch until report discrepancy is resolved | OPEN
IC-003 | Bare PCB each revision | One fabrication batch | Selected-lot first article dimensions finish stackup and coupon | FIRST_ARTICLE_PLUS_DRAWING_DEFINED_FEATURES | Measured controlled features and finish comply with the released drawing | Caliper microscope and supplier coupon | FAI measurements and coupon report | Stop only affected fabrication batch and open supplier NCR | OPEN
IC-004 | PCBA each assembly and revision | One assembly batch | Assembler AOI and visual process control | 100_PERCENT_ASSEMBLER_AOI | No wrong polarity bridge tombstone missing part or unapproved DNP | AOI plus microscope | AOI export and defect log | Rework affected unit under approved instruction and expand only for systemic defect | OPEN
IC-005 | PCBA hidden termination risk | One assembly batch | Process-defined X-ray at first article and suspect locations | PROCESS_DEFINED_FIRST_ARTICLE_AND_SUSPECTS | No void short open or placement defect beyond the released criterion | X-ray | X-ray records linked to serial or panel | Stop affected assembly units and expand scope only when defect is systemic | OPEN
IC-006 | MCU and security-critical IC | One purchase shipment | PO and packing-slip reconciliation followed by electrical identity at PCBA EOL | DOCUMENT_ONLY_AT_RECEIPT_FUNCTIONAL_AT_PCBA_EOL | Exact manufacturer MPN and package were ordered with no substitution and device identity passes EOL | Document review ESD workstation and programmer | Purchase record plus PCBA EOL identity log | Hold only an obvious mismatched or damaged package; expand review only for systemic discrepancy | OPEN
IC-007 | Cellular modem | One purchase shipment | PO reconciliation followed by IMEI firmware and conducted power-up at PCBA EOL | ALL_UNITS_AT_PCBA_EOL | Exact BG95-M3 identity unique valid IMEI and approved firmware baseline pass | Fixture and modem tool | Purchase record and IMEI register without credentials | Remove failed module from assembly flow and expand review only if systemic | OPEN
IC-008 | LoRa module | One purchase shipment | PO reconciliation followed by identity sleep-current and conducted-RF checks at EOL and EVT | ALL_UNITS_FUNCTIONAL_AT_EOL_RF_DURING_EVT | Exact E22-900M22S castellated-ANT identity and sleep behavior pass; RF evidence meets approved profile | Fixture RF load and analyzer | Purchase record module EOL log and EVT RF plots | Remove failed unit and expand review only if systemic | OPEN
IC-009 | GNSS module | One purchase shipment | PO reconciliation followed by identity fix and TIMEPULSE at PCBA EOL | ALL_UNITS_AT_PCBA_EOL | Exact MAX-M10S-00B identity fix and TIMEPULSE pass in controlled setup | GNSS simulator or known-good antenna | Purchase record and receiver logs | Remove failed unit and expand review only if systemic | OPEN
IC-010 | MEMS microphones | One purchase shipment | PO reconciliation followed by port inspection and acoustic EOL | ALL_UNITS_AT_ASSEMBLY_AND_EOL | Exact MMICT5838-00-012 identity has no port damage and assembled channel meets released acoustic limits | Microscope and acoustic fixture | Purchase record and channel sensitivity data | Remove failed unit and expand review only for systematic shift | OPEN
IC-011 | RELiON RB40 battery pack | One purchase shipment | Commercial receipt plus every-unit safe installation and EVT qualification | ALL_UNITS_SAFETY_AT_INSTALLATION_FUNCTIONAL_DURING_EVT | Exact RB40 line quantity and shipping condition agree; polarity and open-circuit voltage are safe at installation; capacity DCIR BMS and cold behavior meet EVT criteria | DMM DC load battery cycler scale and chamber | Purchase and packing records applicable transport documents installation record and EVT curves | Isolate an unsafe or damaged unit in the designated battery-safe area; expand review only if systemic | OPEN
IC-012 | Victron SCC075010060R plus SBS050150200 | One purchase shipment | Commercial receipt followed by installation configuration EOL and cold-system EVT | ALL_UNITS_AT_INSTALLATION_AND_EOL_COLD_VALIDATION_DURING_EVT | Exact articles install with approved terminal stack; VE.Smart reports battery temperature; 0 C inhibit reconnect reverse current quiescent and thermal behavior meet released criteria | PV simulator battery simulator load logger torque tools pull gauge and chamber | Purchase record configuration export retention data charge curves network log and thermal results | Remove failed article from assembly flow and expand review only if systemic | OPEN
IC-013 | SLD Tech SLP080S-12M solar panel | One purchase shipment | Commercial receipt followed by installed-unit checks and panel EVT | ALL_UNITS_DAMAGE_AND_VOC_AT_INSTALLATION_FULL_VALIDATION_DURING_EVT | Exact model has no visible transit damage; installed Voc polarity and dimensions are correct; IV insulation wet leakage and cold-Voc meet released criteria | PV analyzer insulation tester light source and chamber | Purchase record installation checks and EVT IV records | Remove damaged or failed panel and expand review only if systemic | OPEN
IC-014 | Taoglas G30.B.108111 AA.166.A.301111 TI.89.B.2111W and CAB.0243 | One purchase shipment per exact MPN | Commercial receipt followed by installed continuity mate route seal and RF validation | ALL_INSTALLED_CABLES_AT_EOL_RF_AND_ENVIRONMENT_DURING_EVT | Exact no-substitution identities and normal SMA polarity install correctly; CAB.0243 follows the 6.8 mm bend limit and the complete chain meets released seal and RF limits | VNA continuity fixture pull gauge torque tools seal fixture and chamber | Purchase record EOL continuity and mate log plus EVT S-parameter seal and temperature records | Remove failed item from assembly flow and expand review only if systemic | OPEN
IC-015 | Harnesses | One custom manufacturing batch | Selected-lot continuity polarity dimensions and process first article | 100_PERCENT_CONTINUITY_PLUS_PROCESS_FIRST_ARTICLE | Every harness passes net and polarity test and first-article retention meets the released drawing | Harness tester caliper and pull gauge | Tester export FAI and controlled measurements | Return or rework affected harness under approved instruction; expand only if systemic | OPEN
IC-016 | Housing parts each technology | One custom manufacturing batch | Selected-lot visual inspection and drawing-defined first article | ALL_UNITS_VISUAL_PLUS_DRAWING_DEFINED_FIRST_ARTICLE | Released material drawing critical dimensions gasket land and fit are satisfied | CMM or calibrated tools and microscope | FAI measurements material record and defect log | Stop affected manufacturing batch and open supplier NCR only for confirmed discrepancy | OPEN
IC-017 | Fasteners glands membranes gaskets | One purchase shipment | Commercial receipt followed by fit during normal assembly | DOCUMENT_ONLY_AT_RECEIPT_FIT_DURING_ASSEMBLY | Exact manufacturer MPN or released specification was ordered with no substitution and installed fit passes | Document review caliper thread gauge and assembly fixture | Purchase record and assembly traveller | Hold only mismatched damaged or non-fitting item; expand review only if systemic | OPEN
IC-018 | Moisture-sensitive components | One shipment | MSL package humidity-card and floor-life handling | ALL_MSL_PACKAGES | Package is sealed indicator is valid and exposure time is tracked | ESD workstation and MSL log | MSL handling log | Segregate only affected exposed package and follow the approved bake or disposition process | OPEN
IC-019 | SIM mux and two SIM connectors | One purchase shipment | PO reconciliation followed by coplanarity card-detect leakage and switching at assembly and EOL | ALL_UNITS_AT_ASSEMBLY_AND_EOL | Exact approved MPN and footprint are installed; both slots map to the correct ICCID without waveform violation | Microscope fixture scope and BG95 test firmware | Purchase record EOL waveforms cycle log and ICCID references | Remove failed unit and expand review only if systemic; schematic review on repeated failure | OPEN

## План корпусов
План корпусов
Решение заказчика 29.09.2026: первый лот 20 изделий печатается; физический выпуск CAD и первый образец ещё требуются.
Serial | Primary_Process | Primary_Qty | Fallback_Process | Fallback_Qty_if_Activated | Fallback_Activation | Injection_Molding_Scope | Status
DIO-EVT-001 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-002 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-003 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-004 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-005 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-006 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-007 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-008 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-009 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-010 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-011 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-012 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-013 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-014 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-015 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-016 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-017 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-018 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-019 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING
DIO-EVT-020 | 3D_PRINT | 1 | NOT_SELECTED | 0 |  | SOURCE_DATA_AND_DFM_ONLY | FIRST_LOT_3D_PRINT_DECISION_CAD_PENDING

## PCB-MAIN Rev B DFM
PCB-MAIN Rev B · контроль выпуска
Кандидат 105 · 8 слоёв · DRC 0 ошибок · 0 неразведённых · ERC 0 · заводской DFM ожидается
№ | Проверка | Состояние | Действие / доказательство
1 | Трассировка и DRC | PASS | 0 ошибок, 0 неразведённых; отчёт drc_candidate.json
2 | ERC схемы | PASS | 0 нарушений; отчёт erc_candidate.json
3 | Монтажные позиции | PASS | 227 позиций BOM_PCBA и POS_TOP_PCBA совпадают
4 | DNP | PASS | 15 позиций вынесены в PCB-MAIN_DNP.csv
5 | Стек 8 слоёв 1,6 мм | По данным JLC — PASS; выбрать в заказе | 8 слоёв, 1,6 мм и стек JLC08161H-3313 опубликованы; диэлектрики зафиксировать в выбранной опции
6 | Переходы в площадках | POFV опубликован; сверить в заказе | 74 перехода fill/cap по координатам: 57 в SMD-площадках и 17 вне; эпоксидное заполнение, медная крышка
7 | Импеданс и сверловка | По данным JLC — PASS; выбрать опцию | 0,15/0,25 мм — опубликованный минимум для многослойной платы; возможна доплата
8 | Площадки J6/J7/J11 | ОЖИДАЕТСЯ | Проверить изменённую геометрию у производителя
9 | Первый монтажный образец | ОЖИДАЕТСЯ | AOI, X-ray скрытых выводов, электрический тест
10 | Функциональный EVT | ОЖИДАЕТСЯ | Первое включение и полный маршрут испытаний

## Серийные 1 лот
Серийные номера первого лота
DIO-EVT-001…020.
Serial | Lot | PCB_MAIN_SN | PCB_MAIN_REV | PCB_PWR_SN | PCB_PWR_REV | MIC1_SN | MIC2_SN | MIC3_SN | MIC4_SN | Housing_Technology | Housing_Rev | LoRa_Profile | Modem_IMEI | SIM1_ICCID_Ref | SIM2_ICCID_Ref | Preferred_SIM_Slot | APN_Mode | Battery_Lot | MPPT_Lot | FW_Release | Provisioning_Record | EOL_Record | Status
DIO-EVT-001 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-002 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-003 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-004 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-005 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-006 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-007 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-008 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-009 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-010 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-011 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-012 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-013 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-014 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-015 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-016 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-017 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-018 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-019 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD
DIO-EVT-020 | EVT-PRE-20 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SELECTED_EVT_LOT_AWAITING_BUILD

## Серийные 2 лот
Серийные номера второго лота и стенда
DIO-EVT-021…040 и DIO-EVT-B01.
Serial | Lot | PCB_MAIN_SN | PCB_MAIN_REV | PCB_PWR_SN | PCB_PWR_REV | MIC1_SN | MIC2_SN | MIC3_SN | MIC4_SN | Housing_Technology | Housing_Rev | LoRa_Profile | Modem_IMEI | SIM1_ICCID_Ref | SIM2_ICCID_Ref | Preferred_SIM_Slot | APN_Mode | Battery_Lot | MPPT_Lot | FW_Release | Provisioning_Record | EOL_Record | Status
DIO-EVT-021 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-022 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-023 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-024 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-025 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-026 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-027 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-028 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-029 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-030 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-031 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-032 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-033 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-034 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-035 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-036 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-037 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-038 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-039 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-040 | EVT-PRE-20-LOT-2 | [8 empty] | VACUUM_CASTING_PRIMARY |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | SECOND_GROUP_RESERVED_AWAITING_BUILD
DIO-EVT-B01 | BENCH | [8 empty] | BENCH_FIXTURE |  | RU868_LOCKED |  |  |  |  | PUBLIC_ONLY | [5 empty] | BENCH_UNIT_RESERVED