## Summary
Dioneya EVT-PRE-20 Rev.A production BOM
Lot stations | PCB-MAIN PCBA | PCB-PWR PCBA | PCB-MIC PCBA | T5838 microphones | Vacuum-cast housings
4 | 4 | 4 | 16 | 16 | 4
10 | 10 | 10 | 40 | 40 | 10
20 | 20 | 20 | 80 | 80 | 20
Selected scenario | EVT-20 | 20 stations | DIO-EVT-001..020 | Purchase gate | BLOCKED
Control | Status
Source commit | cf9ee11a9491
Engineering BOM rows | 295
Procurement roll-up rows | 124
QG-1 | PASS
QG-2 technical BOM | PASS
Board procurement basis | PRIMARY: full PCBA; ALT: bare PCB quotation only; 2 spare PCB-MAIN / PCB-PWR / PCB-MIC in either track
Open production-release blockers
Blocker | Affected items | Required closure evidence
System physical qualification | BAT1, PV1, MPPT1, MPPT-TEMP, ANT-CELL, ANT-GNSS, ANT-LORA, RF-PIGTAIL | Complete assembly/EOL/EVT physical evidence; commercial supplier quotes are customer-owned
PCB and assembly manufacturing release | ASM-MAIN, PCB-MAIN, ASM-PWR, PCB-PWR, ASM-MIC, PCB-MIC | Complete routing, DRC, Review B, CAM/DFM and selected-process evidence; customer selects supplier
Input protection, harness and housing physical release | PWR-TVS-01, PWR-FUSE-01, HARNESS, HSG-VC | Close 16/20 PCB-PWR physical tests, final harness lengths/process evidence and housing source/FAI
Deferred physical EVT | Operator, physical SIM-cycle and 24-hour evidence is collected after station assembly. It does not replace PCB Review B or strict BOM QG-2.

## Procurement
Procurement_ID | Assemblies | Item_IDs | RefDes | Category | Manufacturer | MPN | Package | Value | Variant | Population | Qty_4 | Spares_4 | Procure_qty_4 | Qty_10 | Spares_10 | Procure_qty_10 | Qty_20 | Spares_20 | Procure_qty_20 | Spare_policy | BOM_disposition | Status | China_source_policy | Incoming_control
PR-001 | PCB-MAIN | ASM-MAIN | - | PCBA | Dioneya controlled design | DIO-ASM-MAIN-REV-A | 6-layer PCBA build-to-print service scope |  | COMMON | N/A | 4 | 2 | 6 | 10 | 2 | 12 | 20 | 2 | 22 | FIXED_LOT_MIN | CONTROLLED_CUSTOMER_RFQ_SCOPE | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_EMS_SELECTION_PENDING | Customer-selected qualified EMS; quotation and purchase outside the engineering repository | AOI plus X-ray where hidden joints plus functional test
PR-002 | PCB-MIC | ASM-MIC | - | PCBA | Dioneya controlled design | DIO-ASM-MIC-REV-A | 2-layer microphone PCBA build-to-print service scope |  | COMMON | N/A | 16 | 2 | 18 | 40 | 2 | 42 | 80 | 2 | 82 | FIXED_LOT_MIN | CONTROLLED_CUSTOMER_RFQ_SCOPE | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_EMS_SELECTION_PENDING | Customer-selected qualified EMS; quotation and purchase outside the engineering repository | AOI acoustic port inspection channel functional test
PR-003 | PCB-PWR | ASM-PWR | - | PCBA | Dioneya controlled design | DIO-ASM-PWR-REV-A | assembled 4-layer power PCB build-to-print service scope; EVT DIM-003 90x60x1.6 mm and H1-H4 accepted; outer 2 oz target; inner 1 oz target; final stackup pending DFM |  | COMMON | N/A | 4 | 2 | 6 | 10 | 2 | 12 | 20 | 2 | 22 | FIXED_LOT_MIN | CONTROLLED_CUSTOMER_RFQ_SCOPE | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_EMS_SELECTION_PENDING | Customer-selected qualified EMS; quotation and purchase outside the engineering repository | AOI functional high-current thermal
PR-004 | SYSTEM | HARNESS | - | Harness | Dioneya controlled design | DIO-HARNESS-SET-REV-A | Controlled labeled station harness set Rev.A |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 2 | 22 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_BUILD_TO_PRINT_IDENTITY | CONTROLLED_INTERNAL_ARTICLE_PHYSICAL_RELEASE_PENDING | Customer-selected qualified harness assembler; build only to the controlled drawing and schedule | 100 percent continuity polarity pull sample
PR-005 | SYSTEM | HSG-3D | HSG1 | Housing | TBD | TBD | Assembly |  | THREE_D_PRINT_FALLBACK | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | CONDITIONAL_NOT_RELEASED | SOURCE_PACKAGE_REQUIRED | Qualified print supplier or controlled FlashForge 5M Pro process | Engineering sample dimensions material finish leak fit acoustic and RF checks
PR-006 | SYSTEM | HSG-IM | HSG1 | Housing | TBD | TBD | Source_data |  | INJECTION_MOLDING_FUTURE | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | CONDITIONAL_NOT_RELEASED | SOURCE_PACKAGE_REQUIRED | Qualified mold manufacturer for DFM quotation | Source audit wall draft ribs bosses parting ejector shrink material and tooling concept
PR-007 | SYSTEM | HSG-VC | HSG1 | Housing | Dioneya controlled design | DIO-HSG-VC-REV-A | Vacuum-cast polyurethane housing set build-to-print scope |  | VACUUM_CASTING_PRIMARY | N/A | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_CUSTOMER_RFQ_SCOPE | CONTROLLED_INTERNAL_ARTICLE_MECHANICAL_RELEASE_PENDING | Customer-selected qualified vacuum-casting supplier; quotation and purchase outside the engineering repository | FAI dimensions material cure finish inserts leak fit acoustic and RF checks
PR-008 | PCB-MAIN | PCB-MAIN | - | Bare PCB | Dioneya controlled design | DIO-PCB-MAIN-REV-A | 6-layer FR-4 110x75x1.6 mm build-to-print fabrication scope |  | COMMON | N/A | 4 | 2 | 6 | 10 | 2 | 12 | 20 | 2 | 22 | FIXED_LOT_MIN | CONTROLLED_CUSTOMER_RFQ_SCOPE | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_FAB_SELECTION_PENDING | Customer-selected qualified PCB fabricator; quotation and purchase outside the engineering repository | Coupon dimensions finish stackup impedance and netlist test
PR-009 | PCB-MIC | PCB-MIC | - | Bare PCB | Dioneya controlled design | DIO-PCB-MIC-REV-A | 2-layer FR-4 microphone PCB build-to-print fabrication scope |  | COMMON | N/A | 16 | 2 | 18 | 40 | 2 | 42 | 80 | 2 | 82 | FIXED_LOT_MIN | CONTROLLED_CUSTOMER_RFQ_SCOPE | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_FAB_SELECTION_PENDING | Customer-selected qualified PCB fabricator; quotation and purchase outside the engineering repository | Outline hole position finish netlist
PR-010 | PCB-PWR | PCB-PWR | - | Bare PCB | Dioneya controlled design | DIO-PCB-PWR-REV-A | 4-layer FR-4 90x60x1.6 mm build-to-print fabrication scope; EVT DIM-003 and H1-H4 accepted; outer 2 oz target; inner 1 oz target; final stackup pending DFM |  | COMMON | N/A | 4 | 2 | 6 | 10 | 2 | 12 | 20 | 2 | 22 | FIXED_LOT_MIN | CONTROLLED_CUSTOMER_RFQ_SCOPE | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_FAB_SELECTION_PENDING | Customer-selected qualified PCB fabricator; quotation and purchase outside the engineering repository | Copper thickness netlist high-current and Kelvin review
PR-011 | PCB-PWR | PWR-FUSE-01 | F1 | Protection | Littelfuse | 0451008.MRL | Nano2_451_6.1x2.69mm |  | COMMON | FITTED | 4 | 2 | 6 | 10 | 5 | 15 | 20 | 10 | 30 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | CANDIDATE_SELECTED_FOR_EVT_QUALIFICATION_NATIVE_VALUE_ECO_APPLIED_REPEAT_EVIDENCE_PASS_PHYSICAL_QUALIFICATION_PENDING | Authorized distributor | Marking continuity and controlled fault clearing
PR-012 | PCB-MAIN | J-SIM1 ¦ J-SIM2 | J6 ¦ J7 | SIM | TE Connectivity | 2336582-1 | Nano-SIM 4FF connector with DET |  | COMMON | FITTED | 8 | 2 | 10 | 20 | 6 | 26 | 40 | 10 | 50 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | TECHNICALLY_SELECTED_PROCUREMENT_RISK | Approved connector vendor | Mating cycles card detect coplanarity and ESD
PR-013 | HARNESS-PWR-MAIN | H-PWR-MAIN | H_PWR_MAIN:A/B | Housing | Molex | 43025-1200 | Micro-Fit 3.0 12-circuit housing |  | COMMON | FITTED | 8 | 1 | 9 | 20 | 2 | 22 | 40 | 4 | 44 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_MECHANICS_I2C_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-014 | HARNESS-PWR-MAIN | T-PWR-MAIN-CTL | H_PWR_MAIN control contacts | Terminal | Molex | 43030-0001 | Micro-Fit female crimp terminal 20-24 AWG class |  | COMMON | FITTED | 48 | 3 | 51 | 120 | 6 | 126 | 240 | 12 | 252 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_I2C_PULL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-015 | HARNESS-PWR-MAIN | T-PWR-MAIN-PWR | H_PWR_MAIN power contacts | Terminal | Molex | 43030-0038 | Micro-Fit female crimp terminal 18 AWG class |  | COMMON | FITTED | 48 | 3 | 51 | 120 | 6 | 126 | 240 | 12 | 252 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_CURRENT_PULL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-016 | PCB-PWR | J-PWR-IN | J1 | Connector | Molex | 430450213 | 2 positions |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_MECHANICS | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-017 | PCB-MAIN ¦ PCB-PWR | J-PWR-MAIN ¦ J-PWR-PWR | J2 ¦ J_PWR | Connector | Molex | 430451202 | 12 positions |  | COMMON | FITTED | 8 | 2 | 10 | 20 | 6 | 26 | 40 | 10 | 50 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | MECHANICAL_AUTHORITY_FROZEN_PENDING_HARNESS_SI ¦ SELECTED_ELECTRICAL_PENDING_MECHANICS | Authorized Molex distributor | Marking dimensions latch mate continuity
PR-018 | PCB-MAIN | J-TAMPER | J13 | Connector | Molex | 5040500291 | Pico-Lock 1.50 mm 2-circuit right-angle SMT |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | MECHANICAL_AUTHORITY_FROZEN_PENDING_PHYSICAL_TEST | Authorized Molex distributor | Mating pull continuity cable-break and cover-open fault coverage
PR-019 | PCB-MAIN ¦ PCB-MIC | J-MIC ¦ J-MIC-MAIN | J_MIC1;J_MIC2;J_MIC3;J_MIC4 ¦ PCB-MIC:J1 x4 | Connector | Molex | 5040500691 | Pico-Lock 1.50 mm 6-circuit right-angle SMT |  | COMMON | FITTED | 32 | 6 | 38 | 80 | 12 | 92 | 160 | 24 | 184 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | MECHANICAL_AUTHORITY_FROZEN_PENDING_SI_AAD | Authorized Molex distributor ¦ Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample ¦ Mating pull test contact resistance continuity and temperature
PR-020 | HARNESS-MIC | H-MIC | H_MIC1:A/B;H_MIC2:A/B;H_MIC3:A/B;H_MIC4:A/B | Housing | Molex | 5040510601 | Pico-Lock 1.50 mm 6-circuit housing |  | COMMON | FITTED | 32 | 4 | 36 | 80 | 8 | 88 | 160 | 16 | 176 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_HARNESS_LENGTH_PULL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-021 | HARNESS-MIC | T-MIC | H_MIC1..H_MIC4 contacts | Terminal | Molex | 5040520098 | Pico-Lock crimp terminal 28-24 AWG |  | COMMON | FITTED | 192 | 48 | 240 | 480 | 48 | 528 | 960 | 48 | 1008 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_CRIMP_PULL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-022 | SYSTEM | ANT-GNSS | AE2 | Antenna | Taoglas | AA.166.A.301111 | IP67 magnetic 37.8x40.4x10 mm with 3 m RG174 SMA(M) |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 2 | 22 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Taoglas or established distributor; exact AA.166.A.301111 only; no substitution | Reconcile PO packing slip quantity and visible damage; verify connector cable route current at 3.3 V receiver sensitivity PPS mounting and coexistence during assembly EOL and EVT
PR-023 | PCB-MAIN | MAIN-010-FL1 | FL1 | SAW_Filter | Abracon | ABSES5AF-L100KM | 1109-5 | 1582.4 MHz wideband GNSS SAW | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-024 | PCB-MAIN | U8 | U8 | Cellular | Quectel | BG95-M3 | LGA-102_23.6x19.9mm |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_INCOMING_ID_AND_POST_ASSEMBLY_EVT | Quectel authorized channel or CM with traceability | IMEI label firmware RF conducted attach TLS
PR-025 | PCB-MAIN | MAIN-010-FB1 | FB1 | Ferrite_Bead | Murata | BLM31KN601SN1L | 1206 | 600 Ohm at 100 MHz | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-026 | SYSTEM | RF-PIGTAIL | J8/J9/J10 cable | RF cable | Taoglas | CAB.0243 | 1.13 mm micro-coax 150 mm MHF I/U.FL-compatible R/A to waterproof SMA(F) bulkhead |  | COMMON | FITTED | 12 | 2 | 14 | 30 | 3 | 33 | 60 | 6 | 66 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Taoglas or established distributor; exact CAB.0243 only; no substitution | Reconcile PO packing slip quantity and visible damage; verify every installed cable continuity polarity length and route then mate retention bend seal torque temperature and VNA performance during assembly EOL and EVT
PR-027 | PCB-PWR | PWR-C-100N | C1;C2;C4;C6 | Passive | TDK | CGA2B3X7R1E104K050BB | 0402 | 100 nF 25 V X7R | COMMON | FITTED | 16 | 40 | 56 | 40 | 40 | 80 | 80 | 40 | 120 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | LOCKED_CANDIDATE_PENDING_DERATING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-028 | PCB-MIC | C-MIC | PCB-MIC:C1 x4 | Passive | TDK | CGA2B3X7R1E104K050BB | 0402 1005 metric | 100 nF 25 V X7R | COMMON | FITTED | 16 | 40 | 56 | 40 | 40 | 80 | 80 | 40 | 120 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SAMPLE | Traceable passive vendor | Value package reel label capacitance sample
PR-029 | PCB-PWR | PWR-C-LDO | C7;C8 | Passive | TDK | CGA3E1X7R1A225K080AC | 0603 | 2.2 uF 10 V X7R | COMMON | FITTED | 8 | 40 | 48 | 20 | 40 | 60 | 40 | 40 | 80 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | LOCKED_CANDIDATE_PENDING_DERATING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-030 | PCB-PWR | PWR-C-CIN-HF | C9;C20;C21 | Passive | TDK | CGA3E2X7R1H104K080AA | 0603 | 100 nF 50 V X7R | COMMON | FITTED | 12 | 40 | 52 | 30 | 40 | 70 | 60 | 40 | 100 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | CONTROLLED_CANDIDATE_PENDING_MULTIPLE_REVIEWS | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-031 | PCB-PWR | PWR-COUT-3V3 ¦ PWR-COUT-3V8 | C3;C14;C15;C16 ¦ C5;C17;C18;C19 | Passive | TDK | CGA6P3X7R1E226M250AB | 1210 | 22 uF 25 V X7R | COMMON | FITTED | 32 | 80 | 112 | 80 | 80 | 160 | 160 | 80 | 240 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | LOCKED_CANDIDATE_PENDING_DERATING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-032 | PCB-PWR | PWR-C-INPUT | C10;C11;C12 | Passive | TDK | CGA6P3X7R1H475K250AB | 1210 | 4.7 uF 50 V X7R | COMMON | FITTED | 12 | 40 | 52 | 30 | 40 | 70 | 60 | 40 | 100 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | CONTROLLED_CANDIDATE_PENDING_MULTIPLE_REVIEWS | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-033 | PCB-PWR | PWR-REV-FET | Q1 | Protection | Texas Instruments | CSD18540Q5B | VSON-CLIP 5x6 mm |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED | SELECTED_TECHNICALLY_PROCUREMENT_CHECK | Authorized distributor | Marking Rds thermal and reverse fault test
PR-034 | SYSTEM | BAT1 | BT1 | Battery | Epower Tech Co. Ltd | DIO-BAT-LFP-12V50-H-REV-A | 198x166x170 mm body; 182-184 mm including M8 studs |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 1 | 21 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Epower Tech supplier-configured heated article DIO-BAT-LFP-12V50-H-REV-A only; no substitution; PO must state heater option dimensions terminal geometry and applicable UN38.3 SDS and route documents | Reconcile PO packing slip quantity configuration and damage; check every unit dimensions polarity and OCV; verify heater threshold and current then capacity DCIR BMS charge inhibit and cold behavior during assembly and EVT
PR-035 | PCB-MAIN | U10 | U10 | LoRa | Ebyte | E22-900M22S | SMD_20x14_22P_1.27mm |  | RU868_PILOT | FITTED | 4 | 2 | 6 | 10 | 3 | 13 | 20 | 6 | 26 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_CASTELLATED_OPTION_RF_REGULATORY | Ebyte official store or authorized distributor | Marking antenna-interface option firmware conducted power sensitivity sleep current
PR-036 | PCB-PWR | PWR-C-BULK | C13 | Passive | Panasonic Industry | EEH-ZK1V101XP | SMD can 6.3x7.7 mm | 100 uF 35 V hybrid | COMMON | FITTED | 4 | 40 | 44 | 10 | 40 | 50 | 20 | 40 | 60 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | LOCKED_CANDIDATE_PACKAGE_REVIEW_PENDING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-037 | PCB-PWR | PWR-R-100K-01 | R1 | Passive | Panasonic Industry | ERA-2AEB104X | 0402 | 100 kOhm 0.1% | COMMON | FITTED | 4 | 40 | 44 | 10 | 40 | 50 | 20 | 40 | 60 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | LOCKED_CANDIDATE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-038 | PCB-PWR | PWR-R-35K7 | R2 | Passive | Panasonic Industry | ERA-2AEB3572X | 0402 | 35.7 kOhm 0.1% | COMMON | FITTED | 4 | 40 | 44 | 10 | 40 | 50 | 20 | 40 | 60 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | LOCKED_CANDIDATE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-039 | PCB-PWR | PWR-R-86K6 | R3;R7 | Passive | Panasonic Industry | ERA-2AEB8662X | 0402 | 86.6 kOhm 0.1% | COMMON | FITTED | 8 | 40 | 48 | 20 | 40 | 60 | 40 | 40 | 80 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | LOCKED_CANDIDATE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-040 | PCB-MAIN | MAIN-010-R98 | R98 | Resistor | Panasonic | ERJ-2GE0R00X | 0402 | 0 Ohm | COMMON | DNP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | CONTROLLED_DNP | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-041 | PCB-MAIN | MAIN-010-R103 ¦ MAIN-010-R39 ¦ MAIN-010-R40 ¦ MAIN-010-R42 ¦ MAIN-010-R43 ¦ MAIN-010-R50 ¦ MAIN-010-R51 ¦ MAIN-010-R52 ¦ MAIN-010-R53 ¦ MAIN-010-R54 ¦ MAIN-010-R55 ¦ MAIN-010-R73 | R103 ¦ R39 ¦ R40 ¦ R42 ¦ R43 ¦ R50 ¦ R51 ¦ R52 ¦ R53 ¦ R54 ¦ R55 ¦ R73 | Resistor | Panasonic | ERJ-2GE0R00X | 0402 | 0 Ohm | COMMON | FITTED | 48 | 0 | 48 | 120 | 0 | 120 | 240 | 0 | 240 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-042 | PCB-PWR | PWR-R-0R-DNP | R5;R9 | Passive | Panasonic Industry | ERJ-2GE0R00X | 0402 | 0 ohm | COMMON | DNP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | CONTROLLED_DNP | LOCKED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-043 | PCB-PWR | PWR-R-0R | R4;R8 | Passive | Panasonic Industry | ERJ-2GE0R00X | 0402 | 0 ohm | COMMON | FITTED | 8 | 40 | 48 | 20 | 40 | 60 | 40 | 40 | 80 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | LOCKED_FITTED | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-044 | PCB-MIC | R-MIC | PCB-MIC:R1 x4 | Passive | Panasonic Industry | ERJ-2GE0R00X | 0402 1005 metric | 0 ohm | COMMON | FITTED | 16 | 40 | 56 | 40 | 40 | 80 | 80 | 40 | 120 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | SELECTED_POPULATED_BASELINE_PENDING_SI | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-045 | PCB-MAIN | MAIN-010-R60 ¦ MAIN-010-R61 | R60 ¦ R61 | Resistor | Panasonic | ERJ-2GEJ104X | 0402 | 100 kOhm 5% 0.1 W | COMMON | FITTED | 8 | 0 | 8 | 20 | 0 | 20 | 40 | 0 | 40 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-046 | PCB-MAIN | MAIN-010-R59 | R59 | Resistor | Panasonic | ERJ-2GEJ561X | 0402 | 560 Ohm 5% 0.1 W | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-047 | PCB-MAIN | MAIN-010-R100 ¦ MAIN-010-R102 ¦ MAIN-010-R38 ¦ MAIN-010-R41 ¦ MAIN-010-R95 | R100 ¦ R102 ¦ R38 ¦ R41 ¦ R95 | Resistor | Panasonic | ERJ-2RKF1001X | 0402 | 1 kOhm 1% | COMMON | FITTED | 20 | 0 | 20 | 50 | 0 | 50 | 100 | 0 | 100 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-048 | PCB-MAIN | MAIN-010-R1 ¦ MAIN-010-R28 ¦ MAIN-010-R30 ¦ MAIN-010-R31 ¦ MAIN-010-R46 ¦ MAIN-010-R48 ¦ MAIN-010-R49 ¦ MAIN-010-R67 ¦ MAIN-010-R68 ¦ MAIN-010-R7 ¦ MAIN-010-R76 ¦ MAIN-010-R78 ¦ MAIN-010-R85 ¦ MAIN-010-R86 ¦ MAIN-010-R87 ¦ MAIN-010-R88 ¦ MAIN-010-R89 ¦ MAIN-010-R90 ¦ MAIN-010-R99 | R1 ¦ R28 ¦ R30 ¦ R31 ¦ R46 ¦ R48 ¦ R49 ¦ R67 ¦ R68 ¦ R7 ¦ R76 ¦ R78 ¦ R85 ¦ R86 ¦ R87 ¦ R88 ¦ R89 ¦ R90 ¦ R99 | Resistor | Panasonic | ERJ-2RKF1002X | 0402 | 10 kOhm 1% | COMMON | FITTED | 76 | 0 | 76 | 190 | 0 | 190 | 380 | 0 | 380 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-049 | PCB-PWR | PWR-R-10K-DNP | R15 | Passive | Panasonic Industry | ERJ-2RKF1002X | 0402 | 10 kOhm 1% | COMMON | DNP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | CONTROLLED_DNP | LOCKED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-050 | PCB-PWR | PWR-R-10K | R10;R12 | Passive | Panasonic Industry | ERJ-2RKF1002X | 0402 | 10 kOhm 1% | COMMON | FITTED | 8 | 40 | 48 | 20 | 40 | 60 | 40 | 40 | 80 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | LOCKED_FITTED | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-051 | PCB-MAIN | MAIN-010-R4 ¦ MAIN-010-R6 | R4 ¦ R6 | Resistor | Panasonic | ERJ-2RKF1003X | 0402 | 100 kOhm 1% | COMMON | DNP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | CONTROLLED_DNP | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-052 | PCB-MAIN | MAIN-010-R19 ¦ MAIN-010-R2 ¦ MAIN-010-R20 ¦ MAIN-010-R21 ¦ MAIN-010-R22 ¦ MAIN-010-R23 ¦ MAIN-010-R29 ¦ MAIN-010-R3 ¦ MAIN-010-R32 ¦ MAIN-010-R33 ¦ MAIN-010-R34 ¦ MAIN-010-R35 ¦ MAIN-010-R45 ¦ MAIN-010-R47 ¦ MAIN-010-R5 ¦ MAIN-010-R63 ¦ MAIN-010-R64 ¦ MAIN-010-R65 ¦ MAIN-010-R66 ¦ MAIN-010-R77 ¦ MAIN-010-R96 | R19 ¦ R2 ¦ R20 ¦ R21 ¦ R22 ¦ R23 ¦ R29 ¦ R3 ¦ R32 ¦ R33 ¦ R34 ¦ R35 ¦ R45 ¦ R47 ¦ R5 ¦ R63 ¦ R64 ¦ R65 ¦ R66 ¦ R77 ¦ R96 | Resistor | Panasonic | ERJ-2RKF1003X | 0402 | 100 kOhm 1% | COMMON | FITTED | 84 | 0 | 84 | 210 | 0 | 210 | 420 | 0 | 420 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-053 | PCB-PWR | PWR-R-100K | R6;R11 | Passive | Panasonic Industry | ERJ-2RKF1003X | 0402 | 100 kOhm 1% | COMMON | FITTED | 8 | 40 | 48 | 20 | 40 | 60 | 40 | 40 | 80 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | LOCKED_FITTED | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-054 | PCB-MAIN | MAIN-010-R97 | R97 | Resistor | Panasonic | ERJ-2RKF1004X | 0402 | 1 MOhm 1% | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-055 | PCB-MAIN | MAIN-010-R13 ¦ MAIN-010-R14 | R13 ¦ R14 | Resistor | Panasonic | ERJ-2RKF2201X | 0402 | 2.2 kOhm 1% | COMMON | FITTED | 8 | 0 | 8 | 20 | 0 | 20 | 40 | 0 | 40 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-056 | PCB-MAIN | MAIN-010-R10 ¦ MAIN-010-R101 ¦ MAIN-010-R11 ¦ MAIN-010-R12 ¦ MAIN-010-R15 ¦ MAIN-010-R16 ¦ MAIN-010-R17 ¦ MAIN-010-R18 ¦ MAIN-010-R36 ¦ MAIN-010-R37 ¦ MAIN-010-R56 ¦ MAIN-010-R57 ¦ MAIN-010-R58 ¦ MAIN-010-R69 ¦ MAIN-010-R70 ¦ MAIN-010-R71 ¦ MAIN-010-R72 ¦ MAIN-010-R74 ¦ MAIN-010-R75 ¦ MAIN-010-R79 ¦ MAIN-010-R8 ¦ MAIN-010-R80 ¦ MAIN-010-R81 ¦ MAIN-010-R82 ¦ MAIN-010-R83 ¦ MAIN-010-R84 ¦ MAIN-010-R9 ¦ MAIN-010-R91 ¦ MAIN-010-R92 | R10 ¦ R101 ¦ R11 ¦ R12 ¦ R15 ¦ R16 ¦ R17 ¦ R18 ¦ R36 ¦ R37 ¦ R56 ¦ R57 ¦ R58 ¦ R69 ¦ R70 ¦ R71 ¦ R72 ¦ R74 ¦ R75 ¦ R79 ¦ R8 ¦ R80 ¦ R81 ¦ R82 ¦ R83 ¦ R84 ¦ R9 ¦ R91 ¦ R92 | Resistor | Panasonic | ERJ-2RKF22R0X | 0402 | 22 Ohm 1% | COMMON | FITTED | 116 | 0 | 116 | 290 | 0 | 290 | 580 | 0 | 580 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-057 | PCB-MAIN | MAIN-010-R24 ¦ MAIN-010-R26 | R24 ¦ R26 | Resistor | Panasonic | ERJ-2RKF4701X | 0402 | 4.7 kOhm 1% | COMMON | FITTED | 8 | 0 | 8 | 20 | 0 | 20 | 40 | 0 | 40 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-058 | PCB-PWR | PWR-R-4K7-DNP | R13;R14 | Passive | Panasonic Industry | ERJ-2RKF4701X | 0402 | 4.7 kOhm 1% | COMMON | DNP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | CONTROLLED_DNP | LOCKED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-059 | PCB-MAIN | MAIN-010-R25 ¦ MAIN-010-R27 ¦ MAIN-010-R44 | R25 ¦ R27 ¦ R44 | Resistor | Panasonic | ERJ-2RKF4702X | 0402 | 47 kOhm 1% | COMMON | FITTED | 12 | 0 | 12 | 30 | 0 | 30 | 60 | 0 | 60 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-060 | PCB-MAIN | MAIN-010-R93 ¦ MAIN-010-R94 | R93 ¦ R94 | Resistor | Panasonic | ERJ-2RKF5101X | 0402 | 5.1 kOhm 1% | COMMON | FITTED | 8 | 0 | 8 | 20 | 0 | 20 | 40 | 0 | 40 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-061 | PCB-MAIN | MAIN-010-R62 | R62 | Resistor | Panasonic | ERJ-8GEYJ100V | 1206 | 10 Ohm 5% 0.25 W | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-062 | PCB-MAIN | U14-U15 | U14;U15 | ESD | STMicroelectronics | ESDALC6V1-5P6 | SOT666_1.6x1.6mm |  | COMMON | FITTED | 8 | 2 | 10 | 20 | 5 | 25 | 40 | 10 | 50 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SIM_ESD_SI_SAMPLE | Authorized distributor | Capacitance leakage ESD rating marking
PR-063 | SYSTEM | ANT-CELL | AE1 | Antenna | Taoglas | G30.B.108111 | IP67 screw-mount dome with 1 m cable and SMA(M) |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 2 | 22 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Taoglas or established distributor; exact G30.B.108111 only; no substitution; resolve manufacturer page cable-construction discrepancy on quote | Reconcile PO packing slip quantity and visible damage; verify cable length connector mate route seal installed VSWR loss attach and coexistence during assembly EOL and EVT
PR-064 | PCB-MAIN | MAIN-010-C64 | C64 | Capacitor | Murata | GRM1555C1E470JA01D | 0402 | 47 pF 25 V C0G | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-065 | PCB-MAIN | MAIN-010-C69 ¦ MAIN-010-C70 ¦ MAIN-010-C79 ¦ MAIN-010-C80 | C69 ¦ C70 ¦ C79 ¦ C80 | Capacitor | Murata | GRM1555C1H100JA01D | 0402 | 10 pF 50 V C0G | COMMON | DNP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | CONTROLLED_DNP | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-066 | PCB-MAIN | MAIN-010-C43 ¦ MAIN-010-C47 | C43 ¦ C47 | Capacitor | Murata | GRM1555C1H100JA01D | 0402 | 10 pF 50 V C0G | COMMON | FITTED | 8 | 0 | 8 | 20 | 0 | 20 | 40 | 0 | 40 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-067 | PCB-MAIN | MAIN-010-C40 | C40 | Capacitor | Murata | GRM1555C1H101JA01D | 0402 | 100 pF 50 V C0G | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-068 | PCB-MAIN | MAIN-010-C39 | C39 | Capacitor | Murata | GRM1555C1H151JA01D | 0402 | 150 pF 50 V C0G | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-069 | PCB-MAIN | MAIN-010-C54 ¦ MAIN-010-C55 ¦ MAIN-010-C56 ¦ MAIN-010-C57 ¦ MAIN-010-C58 ¦ MAIN-010-C59 | C54 ¦ C55 ¦ C56 ¦ C57 ¦ C58 ¦ C59 | Capacitor | Murata | GRM1555C1H330JA01D | 0402 | 33 pF 50 V C0G | COMMON | DNP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | CONTROLLED_DNP | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-070 | PCB-MAIN | MAIN-010-C42 ¦ MAIN-010-C46 | C42 ¦ C46 | Capacitor | Murata | GRM1555C1H330JA01D | 0402 | 33 pF 50 V C0G | COMMON | FITTED | 8 | 0 | 8 | 20 | 0 | 20 | 40 | 0 | 40 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-071 | PCB-MAIN | MAIN-010-C41 | C41 | Capacitor | Murata | GRM1555C1H680JA01D | 0402 | 68 pF 50 V C0G | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-072 | PCB-MAIN | MAIN-010-C14 ¦ MAIN-010-C15 | C14 ¦ C15 | Capacitor | Murata | GRM155R61A225KE15D | 0402 | 2.2 uF 10 V X5R | COMMON | FITTED | 8 | 0 | 8 | 20 | 0 | 20 | 40 | 0 | 40 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-073 | PCB-MAIN | MAIN-010-C11 ¦ MAIN-010-C22 ¦ MAIN-010-C9 | C11 ¦ C22 ¦ C9 | Capacitor | Murata | GRM155R61C105KA12D | 0402 | 1 uF 16 V X5R | COMMON | FITTED | 12 | 0 | 12 | 30 | 0 | 30 | 60 | 0 | 60 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-074 | PCB-MAIN | MAIN-010-C63 | C63 | Capacitor | Murata | GRM155R71C103KA01D | 0402 | 10 nF 16 V X7R | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-075 | PCB-MAIN | MAIN-010-C48 ¦ MAIN-010-C52 ¦ MAIN-010-C53 ¦ MAIN-010-C76 ¦ MAIN-010-C78 | C48 ¦ C52 ¦ C53 ¦ C76 ¦ C78 | Capacitor | Murata | GRM155R71E103KA01D | 0402 | 10 nF 25 V X7R | COMMON | FITTED | 20 | 0 | 20 | 50 | 0 | 50 | 100 | 0 | 100 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-076 | PCB-MAIN | MAIN-010-C16 ¦ MAIN-010-C17 | C16 ¦ C17 | Capacitor | Murata | GRM155R71E104KE14D | 0402 | 100 nF 25 V X7R | COMMON | DNP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | CONTROLLED_DNP | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-077 | PCB-MAIN | MAIN-010-C1 ¦ MAIN-010-C10 ¦ MAIN-010-C12 ¦ MAIN-010-C18 ¦ MAIN-010-C2 ¦ MAIN-010-C21 ¦ MAIN-010-C23 ¦ MAIN-010-C25 ¦ MAIN-010-C26 ¦ MAIN-010-C27 ¦ MAIN-010-C28 ¦ MAIN-010-C29 ¦ MAIN-010-C3 ¦ MAIN-010-C30 ¦ MAIN-010-C31 ¦ MAIN-010-C32 ¦ MAIN-010-C33 ¦ MAIN-010-C34 ¦ MAIN-010-C35 ¦ MAIN-010-C4 ¦ MAIN-010-C45 ¦ MAIN-010-C49 ¦ MAIN-010-C5 ¦ MAIN-010-C50 ¦ MAIN-010-C51 ¦ MAIN-010-C60 ¦ MAIN-010-C62 ¦ MAIN-010-C65 ¦ MAIN-010-C66 ¦ MAIN-010-C68 ¦ MAIN-010-C7 ¦ MAIN-010-C71 ¦ MAIN-010-C73 ¦ MAIN-010-C74 ¦ MAIN-010-C8 | C1 ¦ C10 ¦ C12 ¦ C18 ¦ C2 ¦ C21 ¦ C23 ¦ C25 ¦ C26 ¦ C27 ¦ C28 ¦ C29 ¦ C3 ¦ C30 ¦ C31 ¦ C32 ¦ C33 ¦ C34 ¦ C35 ¦ C4 ¦ C45 ¦ C49 ¦ C5 ¦ C50 ¦ C51 ¦ C60 ¦ C62 ¦ C65 ¦ C66 ¦ C68 ¦ C7 ¦ C71 ¦ C73 ¦ C74 ¦ C8 | Capacitor | Murata | GRM155R71E104KE14D | 0402 | 100 nF 25 V X7R | COMMON | FITTED | 140 | 0 | 140 | 350 | 0 | 350 | 700 | 0 | 700 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-078 | PCB-MAIN | MAIN-010-C37 | C37 | Capacitor | Murata | GRM155R71E224KE14D | 0402 | 220 nF 25 V X7R | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-079 | PCB-MAIN | MAIN-010-C38 | C38 | Capacitor | Murata | GRM155R71E473KA01D | 0402 | 47 nF 25 V X7R | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-080 | PCB-MAIN | MAIN-010-C77 | C77 | Capacitor | Murata | GRM155R72A472KA01D | 0402 | 4.7 nF 100 V X7R | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-081 | PCB-MAIN | MAIN-010-C13 ¦ MAIN-010-C20 ¦ MAIN-010-C24 ¦ MAIN-010-C6 ¦ MAIN-010-C61 ¦ MAIN-010-C67 ¦ MAIN-010-C72 ¦ MAIN-010-C75 | C13 ¦ C20 ¦ C24 ¦ C6 ¦ C61 ¦ C67 ¦ C72 ¦ C75 | Capacitor | Murata | GRM188R61A106KE69D | 0603 | 10 uF 10 V X5R | COMMON | FITTED | 32 | 0 | 32 | 80 | 0 | 80 | 160 | 0 | 160 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-082 | PCB-MAIN | MAIN-010-C19 | C19 | Capacitor | Murata | GRM21BR61A226ME44L | 0805 | 22 uF 10 V X5R | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-083 | PCB-PWR | U-MON-01 | U2 | Monitor | Texas Instruments | INA226AIDGSR | VSSOP-10 |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED | SELECTED_REV_A_12PIN_I2C | Authorized distributor | Marking I2C ID calibration and reference-meter compare
PR-084 | PCB-MAIN | U3 | U3 | Motion | STMicroelectronics | LIS2DW12TR | LGA-12_2x2mm |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SAMPLE | Authorized distributor | Marking orientation WHO_AM_I and self-test
PR-085 | PCB-PWR | PWR-REV-CTL | U1 | Protection | Texas Instruments | LM74700QDBVRQ1 | SOT-23-6 |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SCHEMATIC_SAMPLE | Authorized distributor | Marking reverse test and gate waveform
PR-086 | PCB-PWR | U-PWR1 ¦ U-PWR2 | U3 ¦ U4 | Power | Texas Instruments | LMR604403SRAKR | RAK-9 |  | COMMON | FITTED | 8 | 2 | 10 | 20 | 6 | 26 | 40 | 10 | 50 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_DESIGN_CALC_SAMPLE | Authorized distributor | Load step ripple efficiency sleep current thermal and EMI ¦ Load step ripple efficiency thermal and EMI
PR-087 | PCB-MAIN | MAIN-010-L1 | L1 | Inductor | Murata | LQH32PN2R2NN0L | 1210 | 2.2 uH 20% | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-088 | PCB-MAIN | MAIN-010-L2 | L2 | Inductor | Murata | LQW15AN27NJ00D | 0402 | 27 nH 5% | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-089 | PCB-MAIN | MAIN-010-U5 | U5 | Operational_Amplifier | Analog Devices | LT6000IDCB#TRMPBF | DFN-6_DCB_2x3mm | Single rail-to-rail low-power op amp | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-090 | PCB-MAIN | U9 | U9 | GNSS | u-blox | MAX-M10S-00B | LCC-18_9.7x10.1mm |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_GNSS_RF_TIMING_SAMPLE | Authorized distributor or traceable module channel | Marking firmware satellite fix PPS test
PR-091 | PCB-MAIN | U11 | U11 | BLE | Raytac | MDBT50Q-P1MV2 | nRF52840_SMD_10.5x15.5_61P_PCB_antenna |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_ENCLOSURE_RF | Raytac authorized channel or traceable distributor | Module label firmware BLE 2M coded PHY pairing OTA current RF range and temperature test
PR-092 | PCB-MAIN | J-SD1 | J12 | Connector | GCT | MEM2052-00-195-00-A | microSD push-push SMT 1.95 mm with detect |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | MECHANICAL_AUTHORITY_FROZEN_PENDING_PHYSICAL_TEST | Authorized GCT distributor | Mating detect coplanarity and cycle sample
PR-093 | PCB-MAIN | Q-MODEM-PWRKEY ¦ Q-MODEM-RESET ¦ Q-SIM-MUX-EN | Q1 ¦ Q2 ¦ Q3 | Transistor | Nexperia | MMBT3904,215 | SOT23 |  | COMMON | FITTED | 12 | 3 | 15 | 30 | 9 | 39 | 60 | 15 | 75 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_CONTROL_TIMING_SAMPLE ¦ SELECTED_PENDING_SIM_SAFE_STATE_SAMPLE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-094 | PCB-MIC | MK1 | MK1 | Microphone | TDK InvenSense | MMICT5838-00-012 | LGA-CAV-5 3.5x2.65x0.98 mm |  | COMMON | FITTED | 16 | 4 | 20 | 40 | 8 | 48 | 80 | 16 | 96 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SAMPLE | TDK authorized channel and same lot requested | Marking lot acoustic sensitivity noise phase and port inspection
PR-095 | PCB-PWR | PWR-NET-TIE | NT1;NT2;NT3 | PCB feature | PCB fabrication | NET_TIE_COPPER_REV_A | NetTie-2 SMD pad 0.5 mm | 2-pad copper net tie | COMMON | PCB_FEATURE | 12 | 0 | 12 | 30 | 0 | 30 | 60 | 0 | 60 | NONE | CONTROLLED_PENDING_VERIFICATION | LOCKED_LAYOUT_PENDING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-096 | PCB-MAIN | MAIN-010-D3 ¦ MAIN-010-D5 | D3 ¦ D5 | RF_ESD | Nexperia | PESD5V0C1BSF | SOD962-2 | 5 V bidirectional 0.2 pF RF ESD | COMMON | FITTED | 8 | 0 | 8 | 20 | 0 | 20 | 40 | 0 | 40 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-097 | PCB-MAIN | MAIN-010-D1 ¦ MAIN-010-D2 | D1 ¦ D2 | Supply_TVS | Nexperia | PESD5V0S1UL | SOD882 | 5 V unidirectional 150 W TVS | COMMON | FITTED | 8 | 0 | 8 | 20 | 0 | 20 | 40 | 0 | 40 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-098 | SYSTEM | MPPT-TEMP | TS-BAT1 | Sensor | Victron Energy | SBS050150200 | Smart Battery Sense long range up to 10 m radio with 0.45 m leads and M10 eyelets |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 1 | 21 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Victron authorized distributor; exact SBS050150200 only; no substitution | Reconcile PO packing slip quantity and visible damage; verify 0.45 m lead M10 eyelets retention on the battery M8 terminals accuracy VE.Smart pairing cutoff reconnect and network retention during station assembly EOL and cold EVT
PR-099 | SYSTEM | MPPT1 | U-MPPT | Controller | Victron Energy | SCC075010060R | 100x113x40 mm IP43 electronics IP22 terminals |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 1 | 21 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Victron authorized distributor; exact SCC075010060R only; no substitution | Reconcile PO packing slip quantity and visible damage; bind article and firmware at installation; export configuration and test charge profile reverse current quiescent thermal and cutoff during assembly EOL and EVT
PR-100 | PCB-MAIN | U12 | U12 | Storage | Kingston | SDCIT2/32GB | microSD_card_8_contact |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SAMPLE_ENDURANCE | Kingston authorized channel | CID capacity full write/read temperature and power-loss sample
PR-101 | SYSTEM | PV1 | PV1 | Solar panel | SLD Tech / Solarland | SLP080S-12M | 1475x342x40 mm framed 36-cell panel |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 1 | 21 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | SLD Tech or authorized distributor; exact SLP080S-12M only; no substitution | Reconcile PO packing slip quantity and visible transit damage; measure installed-unit Voc and perform IV insulation wet-leakage cold-Voc bracket cable and transport validation during assembly and EVT
PR-102 | PCB-PWR | PWR-TVS-01 | D1 | Protection | Littelfuse | SMBJ18A | SMB_DO-214AA |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | CANDIDATE_PENDING_SURGE_PROFILE | Authorized distributor | Marking clamp pulse and thermal sample
PR-103 | PCB-MAIN | U18 | U18 | Logic | Texas Instruments | SN74AXC1T45DRLR | SOT-5X3_6 |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_AAD_WAKE_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-104 | PCB-MAIN | U16 ¦ U7 | U16 ¦ U7 | Level translator ¦ Logic | Texas Instruments | SN74AXC8T245PWR | TSSOP-24 |  | COMMON | FITTED | 8 | 2 | 10 | 20 | 6 | 26 | 40 | 10 | 50 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SI_AAD_SAMPLE ¦ SELECTED_PENDING_UART_POWER_SAMPLE | Authorized or traceable tier-1 channel ¦ Do not substitute auto-direction device without review | Logic levels direction leakage sleep test ¦ Marking MPN package orientation electrical functional sample
PR-105 | PCB-MAIN | MAIN-010-U6 | U6 | Open_Drain_Buffer | Texas Instruments | SN74LVC1G07DBVR | SOT-23-5_DBV | Single non-inverting open-drain buffer | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-106 | PCB-MAIN | U17 | U17 | Logic | Texas Instruments | SN74LVC32APWR | TSSOP-14 |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_AAD_WAKE_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-107 | PCB-MAIN | U1 | U1 | MCU | STMicroelectronics | STM32U585VIT6Q | LQFP100_14x14 |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_TARGET_SAMPLE | Authorized distributor or traceable tier-1 China channel | Label lot date code package X-ray sample ID readout
PR-108 | PCB-MAIN | U4 | U4 | Temperature | STMicroelectronics | STTS22HTR | UDFN-6L_2x2mm |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_ASSEMBLY_REVIEW | Authorized distributor | X-ray sample ID and temperature compare
PR-109 | PCB-MAIN | MAIN-010-Q4 | Q4 | Dual_MOSFET | Vishay | Si1016X-T1-GE3 | SOT-563_SC-89 | Complementary N and P channel 20 V | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-110 | PCB-MAIN | X1 | X1 | Clock | SiTime | SiT1552AI-JE-DCC-32.768D | CSP-4_1.5x0.8mm | 32.768 kHz full-swing LVCMOS | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_LSE_BYPASS_REVIEW | Authorized distributor | Frequency and current sample test
PR-111 | PCB-MAIN | MAIN-010-C36 ¦ MAIN-010-C44 | C36 ¦ C44 | Capacitor | KEMET | T520D107M006ATE015 | 7343-31 | 100 uF 6.3 V 15 mOhm polymer | COMMON | FITTED | 8 | 0 | 8 | 20 | 0 | 20 | 40 | 0 | 40 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-112 | SYSTEM | ANT-LORA | AE3 | Antenna | Taoglas | TI.89.B.2111W | IP67 terminal antenna 180x13 mm SMA(M) |  | RU868_PILOT | FITTED | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 2 | 22 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Taoglas or established distributor; exact TI.89.B.2111W only; no substitution | Reconcile PO packing slip quantity and visible damage; verify connector mate installed VSWR conducted power sensitivity coexistence and RU868 radiated compliance during assembly EOL and EVT
PR-113 | PCB-MAIN | MAIN-010-D10 ¦ MAIN-010-D11 ¦ MAIN-010-D6 ¦ MAIN-010-D7 ¦ MAIN-010-D8 ¦ MAIN-010-D9 | D10 ¦ D11 ¦ D6 ¦ D7 ¦ D8 ¦ D9 | ESD_Diode | Texas Instruments | TPD1E05U06DYAR | SOD-523_DYA | 5.5 V 0.5 pF ESD | COMMON | FITTED | 24 | 0 | 24 | 60 | 0 | 60 | 120 | 0 | 120 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-114 | PCB-MAIN | MAIN-010-D4 | D4 | RF_ESD | Texas Instruments | TPD1E05U06DYAR | SOD-523_DYA | 5.5 V unidirectional 0.5 pF RF ESD | COMMON | FITTED | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-115 | PCB-MAIN | MAIN-010-U25 ¦ MAIN-010-U26 | U25 ¦ U26 | USB_ESD_Array | Texas Instruments | TPD2EUSB30DRTR | SOT-9X3_DRT | 2 channel 0.7 pF USB ESD | COMMON | FITTED | 8 | 0 | 8 | 20 | 0 | 20 | 40 | 0 | 40 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-116 | PCB-MAIN | MAIN-010-U19 ¦ MAIN-010-U20 ¦ MAIN-010-U21 ¦ MAIN-010-U22 ¦ MAIN-010-U23 ¦ MAIN-010-U24 ¦ MAIN-010-U27 | U19 ¦ U20 ¦ U21 ¦ U22 ¦ U23 ¦ U24 ¦ U27 | ESD_Array | Texas Instruments | TPD4E05U06DQAR | USON-10_DQA | 4 channel 0.5 pF ESD | COMMON | FITTED | 28 | 0 | 28 | 70 | 0 | 70 | 140 | 0 | 140 | NONE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-117 | PCB-PWR | U-PWR3 | U5 | Power | Texas Instruments | TPS7A2018PDBVR | SOT-23-5 |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_NOISE_SAMPLE | Authorized distributor | Noise PSRR dropout thermal and AAD sleep current
PR-118 | PCB-MAIN | U13 | U13 | SIM switch | Texas Instruments | TS3A27518EPWR | TSSOP-24_PW |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_USIM_SI_SAMPLE | Authorized distributor or traceable tier-1 channel | Marking supply leakage Ron capacitance and 100 switch cycles
PR-119 | PCB-MAIN | J-RF-CELL ¦ J-RF-GNSS | J8 ¦ J9 | RF connector | Hirose | U.FL-R-SMT-1(60) | U.FL SMT receptacle |  | COMMON | FITTED | 8 | 4 | 12 | 20 | 8 | 28 | 40 | 16 | 56 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | LAYOUT_ZONE_FROZEN_PENDING_RF_VALIDATION | Authorized Hirose distributor | Visual mate gauge continuity VNA and VSWR ¦ Visual mate gauge continuity receiver sensitivity and active-antenna current
PR-120 | PCB-MAIN | J-RF-LORA | J10 | RF connector | Hirose | U.FL-R-SMT-1(60) | U.FL SMT receptacle |  | RU868_PILOT | FITTED | 4 | 2 | 6 | 10 | 4 | 14 | 20 | 8 | 28 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | LAYOUT_ZONE_FROZEN_PENDING_RF_VALIDATION | Authorized Hirose distributor | Visual mate gauge continuity conducted power sensitivity and VSWR
PR-121 | PCB-MAIN | J-USB | J11 | Connector | GCT | USB4105-GF-A-120 | 16 positions |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | MECHANICAL_AUTHORITY_FROZEN_PENDING_PHYSICAL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample
PR-122 | PCB-MAIN | U2 | U2 | Memory | Winbond | W25Q512JVFIQ | SOIC-16_300mil |  | COMMON | FITTED | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SAMPLE | Authorized or traceable LCSC-class channel | Marking electrical ID read/write/erase soak
PR-123 | PCB-PWR | R-SHUNT-01 | RSH1 | Shunt | Vishay Dale | WSK2512R0100FEA | WSK2512 4-terminal 6.35x3.18 mm | 10 mOhm 1% 1 W | COMMON | FITTED | 4 | 2 | 6 | 10 | 5 | 15 | 20 | 10 | 30 | SCALE_CEIL_FROM_20_BASELINE | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_KELVIN_LAYOUT_SAMPLE | Authorized current-sense resistor vendor | Resistance TCR marking and four-wire reference measurement
PR-124 | PCB-PWR | PWR-L | L1;L2 | Passive | Coilcraft | XAL7030-472MEC | XAL7030 | 4.7 uH +/-20% | COMMON | FITTED | 8 | 10 | 18 | 20 | 10 | 30 | 40 | 10 | 50 | FIXED_LOT_MIN | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_LAYOUT_THERMAL_EMI | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample

## Engineering BOM
Item_ID | Assembly | RefDes | Category | Description | Manufacturer | MPN | Package | Qty_per_station | Qty_4 | Spares_4 | Procure_qty_4 | Qty_10 | Spares_10 | Procure_qty_10 | Qty_20 | Spares_20 | Procure_qty_20 | Spare_policy | Variant | Status | China_source_policy | Incoming_control | Notes | Value | Line_class | Population | Temperature_C | BOM_disposition
ASM-MAIN | PCB-MAIN | - | PCBA | Assembled main controller PCB | Dioneya controlled design | DIO-ASM-MAIN-REV-A | 6-layer PCBA build-to-print service scope | 1 | 4 | 2 | 6 | 10 | 2 | 12 | 20 | 2 | 22 | FIXED_LOT_MIN | COMMON | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_EMS_SELECTION_PENDING | Customer-selected qualified EMS; quotation and purchase outside the engineering repository | AOI plus X-ray where hidden joints plus functional test | PRIMARY procurement track; internal assembled-article identity only; routing DRC CAM DFM stencil Review B and EOL scope remain mandatory before build |  | PCBA_SERVICE | N/A | N/A | CONTROLLED_CUSTOMER_RFQ_SCOPE
PCB-MAIN | PCB-MAIN | - | Bare PCB | Main controller bare PCB | Dioneya controlled design | DIO-PCB-MAIN-REV-A | 6-layer FR-4 110x75x1.6 mm build-to-print fabrication scope | 1 | 4 | 2 | 6 | 10 | 2 | 12 | 20 | 2 | 22 | FIXED_LOT_MIN | COMMON | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_FAB_SELECTION_PENDING | Customer-selected qualified PCB fabricator; quotation and purchase outside the engineering repository | Coupon dimensions finish stackup impedance and netlist test | ALTERNATIVE quotation track only; internal bare-board identity only; final stackup impedance routing DRC CAM DFM coupon and Review B remain mandatory before fabrication |  | BARE_PCB | N/A | N/A | CONTROLLED_CUSTOMER_RFQ_SCOPE
U1 | PCB-MAIN | U1 | MCU | Ultra-low-power secure MCU | STMicroelectronics | STM32U585VIT6Q | LQFP100_14x14 | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_TARGET_SAMPLE | Authorized distributor or traceable tier-1 China channel | Label lot date code package X-ray sample ID readout | Rev.A freeze source MAIN_COMPONENT_FREEZE_REV_A.csv; blockers: CubeMX exact-package IOC; target build; sample verification |  | ELECTRICAL_COMPONENT | FITTED | -40..85 exact selected part | CONTROLLED_PENDING_VERIFICATION
U2 | PCB-MAIN | U2 | Memory | 512 Mbit 64 MB QSPI NOR | Winbond | W25Q512JVFIQ | SOIC-16_300mil | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_SAMPLE | Authorized or traceable LCSC-class channel | Marking electrical ID read/write/erase soak | Rev.A freeze source MAIN_COMPONENT_FREEZE_REV_A.csv; blockers: availability/endurance/power-loss test |  | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
U3 | PCB-MAIN | U3 | Motion | Low-power accelerometer | STMicroelectronics | LIS2DW12TR | LGA-12_2x2mm | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_SAMPLE | Authorized distributor | Marking orientation WHO_AM_I and self-test | Rev.A freeze source MAIN_COMPONENT_FREEZE_REV_A.csv; blockers: orientation/self-test verification |  | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
U4 | PCB-MAIN | U4 | Temperature | Digital temperature sensor | STMicroelectronics | STTS22HTR | UDFN-6L_2x2mm | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_ASSEMBLY_REVIEW | Authorized distributor | X-ray sample ID and temperature compare | Rev.A freeze source MAIN_COMPONENT_FREEZE_REV_A.csv; blockers: CM UDFN yield; exposed-pad land pattern; thermal response validation |  | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
U7 | PCB-MAIN | U7 | Level translator | Directional 1.8V to 3.3V translator | Texas Instruments | SN74AXC8T245PWR | TSSOP-24 | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_SI_AAD_SAMPLE | Do not substitute auto-direction device without review | Logic levels direction leakage sleep test | Rev.A freeze source MAIN_COMPONENT_FREEZE_REV_A.csv; blockers: PDM skew and final-harness SI; PDM_CLK source termination; THSEL one-wire fanout/timing; measured S0 current |  | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
U8 | PCB-MAIN | U8 | Cellular | LPWA modem Cat M1 NB2 EGPRS | Quectel | BG95-M3 | LGA-102_23.6x19.9mm | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_INCOMING_ID_AND_POST_ASSEMBLY_EVT | Quectel authorized channel or CM with traceability | IMEI label firmware RF conducted attach TLS | Rev.A freeze source MAIN_COMPONENT_FREEZE_REV_A.csv; blockers: ordered module marking and firmware identity at incoming inspection; operator attach; LTE and EGPRS burst; certification; cold-limit qualification |  | ELECTRICAL_COMPONENT | FITTED | -35..75 operating; -40..85 extended | CONTROLLED_PENDING_VERIFICATION
J-SIM1 | PCB-MAIN | J6 | SIM | Nano-SIM push-push connector slot 1 | TE Connectivity | 2336582-1 | Nano-SIM 4FF connector with DET | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | TECHNICALLY_SELECTED_PROCUREMENT_RISK | Approved connector vendor | Mating cycles card detect coplanarity and ESD | Rev.A connector freeze; blockers: TE page reports active but not currently available; qualify a pin/footprint/temperature/lifecycle-compatible 4FF DET second source before release |  | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
J-SIM2 | PCB-MAIN | J7 | SIM | Nano-SIM push-push connector slot 2 | TE Connectivity | 2336582-1 | Nano-SIM 4FF connector with DET | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | TECHNICALLY_SELECTED_PROCUREMENT_RISK | Approved connector vendor | Mating cycles card detect coplanarity and ESD | Rev.A connector freeze; blockers: same as SIM1; source two identical slots for lot or qualify one common second source |  | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
U13 | PCB-MAIN | U13 | SIM switch | 6-channel bidirectional 2 to 1 multiplexer | Texas Instruments | TS3A27518EPWR | TSSOP-24_PW | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_USIM_SI_SAMPLE | Authorized distributor or traceable tier-1 channel | Marking supply leakage Ron capacitance and 100 switch cycles | Rev.A freeze source MAIN_COMPONENT_FREEZE_REV_A.csv; blockers: selected-card VDD minimum; CLK/DATA edge integrity; leakage and reset isolation |  | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
U14-U15 | PCB-MAIN | U14;U15 | ESD | Low-capacitance TVS array for each SIM connector | STMicroelectronics | ESDALC6V1-5P6 | SOT666_1.6x1.6mm | 2 | 8 | 2 | 10 | 20 | 5 | 25 | 40 | 10 | 50 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_SIM_ESD_SI_SAMPLE | Authorized distributor | Capacitance leakage ESD rating marking | Two identical five-line SIM ESD arrays; exact maps in PCB_MAIN_DUAL_SIM_PIN_AUTHORITY_REV_A.csv |  | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
U9 | PCB-MAIN | U9 | GNSS | Independent GNSS with TIMEPULSE | u-blox | MAX-M10S-00B | LCC-18_9.7x10.1mm | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_GNSS_RF_TIMING_SAMPLE | Authorized distributor or traceable module channel | Marking firmware satellite fix PPS test | Rev.A freeze source MAIN_COMPONENT_FREEZE_REV_A.csv; blockers: active antenna and cable; SAW/coexistence; supervisor fault response; PPS and holdover |  | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
U10 | PCB-MAIN | U10 | LoRa | 850-930 MHz 22 dBm SX1262 SPI module | Ebyte | E22-900M22S | SMD_20x14_22P_1.27mm | 1 | 4 | 2 | 6 | 10 | 3 | 13 | 20 | 6 | 26 | SCALE_CEIL_FROM_20_BASELINE | RU868_PILOT | SELECTED_PENDING_CASTELLATED_OPTION_RF_REGULATORY | Ebyte official store or authorized distributor | Marking antenna-interface option firmware conducted power sensitivity sleep current | Rev.A freeze source MAIN_COMPONENT_FREEZE_REV_A.csv; blockers: supplier confirmation of castellated ANT option with no fitted module IPEX; RU868 conducted/radiated test; current; supply availability |  | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
U11 | PCB-MAIN | U11 | BLE | BLE commissioning diagnostics and signed OTA coprocessor | Raytac | MDBT50Q-P1MV2 | nRF52840_SMD_10.5x15.5_61P_PCB_antenna | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_ENCLOSURE_RF | Raytac authorized channel or traceable distributor | Module label firmware BLE 2M coded PHY pairing OTA current RF range and temperature test | Rev.A freeze source MAIN_COMPONENT_FREEZE_REV_A.csv; blockers: 2.4 GHz enclosure range; SWD/DFU/reset firmware and evidence |  | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
U12 | PCB-MAIN | U12 | Storage | Industrial microSD 32 GB | Kingston | SDCIT2/32GB | microSD_card_8_contact | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_SAMPLE_ENDURANCE | Kingston authorized channel | CID capacity full write/read temperature and power-loss sample | Rev.A freeze source MAIN_COMPONENT_FREEZE_REV_A.csv; blockers: authorized-channel procurement; CID/capacity; full write/read; temperature and power-loss sample |  | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
J-SD1 | PCB-MAIN | J12 | Connector | microSD push-push connector with detect | GCT | MEM2052-00-195-00-A | microSD push-push SMT 1.95 mm with detect | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | MECHANICAL_AUTHORITY_FROZEN_PENDING_PHYSICAL_TEST | Authorized GCT distributor | Mating detect coplanarity and cycle sample | Rev.A connector freeze; exact electrical map in PCB_MAIN_CONNECTOR_FIXTURE_PIN_AUTHORITY_REV_A.csv; blockers: card retention cycle and power-loss test; service-cover seal |  | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
J-TAMPER | PCB-MAIN | J13 | Connector | Two-position normally-closed tamper loop | Molex | 5040500291 | Pico-Lock 1.50 mm 2-circuit right-angle SMT | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | MECHANICAL_AUTHORITY_FROZEN_PENDING_PHYSICAL_TEST | Authorized Molex distributor | Mating pull continuity cable-break and cover-open fault coverage | Rev.A connector freeze; exact electrical map in PCB_MAIN_CONNECTOR_FIXTURE_PIN_AUTHORITY_REV_A.csv; blockers: cable length and strain relief; pull and fault-coverage test |  | ELECTRICAL_COMPONENT | FITTED | -40..105 | CONTROLLED_PENDING_VERIFICATION
J-PWR-MAIN | PCB-MAIN | J_PWR | Connector | Power/control/I2C harness from PCB-PWR | Molex | 430451202 | 12 positions | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | MECHANICAL_AUTHORITY_FROZEN_PENDING_HARNESS_SI | Authorized Molex distributor | Marking dimensions latch mate continuity | Mating Molex_430251200; terminal Molex_430300038 power; Molex_430300001 control/I2C; blockers: I2C harness capacitance and pull-up validation; mating harness bend and pull test |  | ELECTRICAL_COMPONENT | FITTED | header -40..125; housing -40..105 | CONTROLLED_PENDING_VERIFICATION
J-RF-CELL | PCB-MAIN | J8 | RF connector | Cellular RF connector | Hirose | U.FL-R-SMT-1(60) | U.FL SMT receptacle | 1 | 4 | 2 | 6 | 10 | 4 | 14 | 20 | 8 | 28 | SCALE_CEIL_FROM_20_BASELINE | COMMON | LAYOUT_ZONE_FROZEN_PENDING_RF_VALIDATION | Authorized Hirose distributor | Visual mate gauge continuity VNA and VSWR | Rev.A connector freeze; coax assembly and RF validation remain blocking: CAB.0243 MHF-I/U.FL-compatible mate and retention; 150 mm route and 6.8 mm minimum bend; bulkhead seal and numeric IP classification; installed cellular VNA/VSWR and coexistence |  | ELECTRICAL_COMPONENT | FITTED | -40..90 | CONTROLLED_PENDING_VERIFICATION
J-RF-GNSS | PCB-MAIN | J9 | RF connector | GNSS RF connector | Hirose | U.FL-R-SMT-1(60) | U.FL SMT receptacle | 1 | 4 | 2 | 6 | 10 | 4 | 14 | 20 | 8 | 28 | SCALE_CEIL_FROM_20_BASELINE | COMMON | LAYOUT_ZONE_FROZEN_PENDING_RF_VALIDATION | Authorized Hirose distributor | Visual mate gauge continuity receiver sensitivity and active-antenna current | Rev.A connector freeze; coax assembly and RF validation remain blocking: exact active antenna and cable; CAB.0243 MHF-I/U.FL-compatible mate and retention; 150 mm route and 6.8 mm minimum bend; bulkhead seal and numeric IP classification; VNA/receiver sensitivity |  | ELECTRICAL_COMPONENT | FITTED | -40..90 | CONTROLLED_PENDING_VERIFICATION
J-RF-LORA | PCB-MAIN | J10 | RF connector | LoRa RF connector | Hirose | U.FL-R-SMT-1(60) | U.FL SMT receptacle | 1 | 4 | 2 | 6 | 10 | 4 | 14 | 20 | 8 | 28 | SCALE_CEIL_FROM_20_BASELINE | RU868_PILOT | LAYOUT_ZONE_FROZEN_PENDING_RF_VALIDATION | Authorized Hirose distributor | Visual mate gauge continuity conducted power sensitivity and VSWR | Rev.A connector freeze; coax assembly and RF validation remain blocking: CAB.0243 MHF-I/U.FL-compatible mate and retention; 150 mm route and 6.8 mm minimum bend; bulkhead seal and numeric IP classification; 868 MHz installed conducted/radiated test |  | ELECTRICAL_COMPONENT | FITTED | -40..90 | CONTROLLED_PENDING_VERIFICATION
X1 | PCB-MAIN | X1 | Clock | 32.768 kHz low drift oscillator | SiTime | SiT1552AI-JE-DCC-32.768D | CSP-4_1.5x0.8mm | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_LSE_BYPASS_REVIEW | Authorized distributor | Frequency and current sample test | Rev.A freeze source MAIN_COMPONENT_FREEZE_REV_A.csv; blockers: CubeMX LSE bypass wiring; holdover drift measurement; complete physical pins and no-external-bypass decision in PCB_MAIN_PASSIVE_SUPPORT_AUTHORITY_REV_A.csv; physical pins: 1=GND;2=LSE_IN;3=3V3_DIGITAL;4=GND | 32.768 kHz full-swing LVCMOS | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
PWR-REV-CTL | PCB-PWR | U1 | Protection | Reverse polarity and reverse current controller | Texas Instruments | LM74700QDBVRQ1 | SOT-23-6 | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_SCHEMATIC_SAMPLE | Authorized distributor | Marking reverse test and gate waveform | Rev.A freeze source POWER_COMPONENT_FREEZE_REV_A.csv; 3.2-65 V controller; external N-MOSFET; low-loss reverse protection; blockers: surge/fuse coordination; gate network review; bench reverse test |  | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
PWR-REV-FET | PCB-PWR | Q1 | Protection | 60 V low-Rds(on) N-MOSFET | Texas Instruments | CSD18540Q5B | VSON-CLIP 5x6 mm | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_TECHNICALLY_PROCUREMENT_CHECK | Authorized distributor | Marking Rds thermal and reverse fault test | Rev.A freeze source POWER_COMPONENT_FREEZE_REV_A.csv; 60 V; Rds(on) <=2.2 mOhm at VGS=10 V; blockers: authorized-channel stock; SOA/thermal calculation; gate transient review |  | ELECTRICAL_COMPONENT | FITTED | -55..175 | CONTROLLED
U-PWR1 | PCB-PWR | U3 | Power | 3.8 V modem synchronous buck | Texas Instruments | LMR604403SRAKR | RAK-9 | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_DESIGN_CALC_SAMPLE | Authorized distributor | Load step ripple efficiency thermal and EMI | Rev.A freeze source POWER_COMPONENT_FREEZE_REV_A.csv; 3-36 V input; 4 A; TI-verified adjustable mode; 3.8 V nominal; low-Iq synchronous buck; blockers: C11 effective capacitance under bias; C20 local CIN_HF placement; 2.7 A+ BG95 burst; EMI; thermal |  | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
U-PWR2 | PCB-PWR | U4 | Power | 3.3 V digital synchronous buck | Texas Instruments | LMR604403SRAKR | RAK-9 | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_DESIGN_CALC_SAMPLE | Authorized distributor | Load step ripple efficiency sleep current thermal and EMI | Rev.A freeze source POWER_COMPONENT_FREEZE_REV_A.csv; 3-36 V input; 4 A; TI-verified fixed 3.3 V mode; low-Iq synchronous buck; blockers: C12 effective capacitance under bias; C21 local CIN_HF placement; load-step; sleep-current; EMI; thermal |  | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
U-PWR3 | PCB-PWR | U5 | Power | 1.8 V low-noise microphone LDO | Texas Instruments | TPS7A2018PDBVR | SOT-23-5 | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_NOISE_SAMPLE | Authorized distributor | Noise PSRR dropout thermal and AAD sleep current | Rev.A freeze source POWER_COMPONENT_FREEZE_REV_A.csv; fixed 1.8 V; 300 mA; low-noise/high-PSRR LDO; blockers: input/output capacitor review; PDM noise test; enable sequencing |  | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
U-MON-01 | PCB-PWR | U2 | Monitor | Total battery current voltage and power monitor | Texas Instruments | INA226AIDGSR | VSSOP-10 | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_REV_A_12PIN_I2C | Authorized distributor | Marking I2C ID calibration and reference-meter compare | Rev.A freeze source POWER_COMPONENT_FREEZE_REV_A.csv; 3.3 V I2C; address 0x40; 10 mOhm Kelvin shunt capture; Current_LSB 200 uA/bit; Power_LSB 5 mW/bit; blockers: Kelvin layout review; I2C harness capacitance/pull-up test; calibration against reference meter |  | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED
R-SHUNT-01 | PCB-PWR | RSH1 | Shunt | 10 mOhm 4-terminal Kelvin current shunt | Vishay Dale | WSK2512R0100FEA | WSK2512 4-terminal 6.35x3.18 mm | 1 | 4 | 2 | 6 | 10 | 5 | 15 | 20 | 10 | 30 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_KELVIN_LAYOUT_SAMPLE | Authorized current-sense resistor vendor | Resistance TCR marking and four-wire reference measurement | Rev.A freeze source POWER_COMPONENT_FREEZE_REV_A.csv; exact four-terminal land pattern controlled; blockers: Kelvin routing review; +70 C thermal; four-wire resistance and reference-meter calibration | 10 mOhm 1% 1 W | ELECTRICAL_COMPONENT | FITTED | -65..170 | CONTROLLED_PENDING_VERIFICATION
J-PWR-PWR | PCB-PWR | J2 | Connector | Power/control/I2C harness to PCB-MAIN | Molex | 430451202 | 12 positions | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_ELECTRICAL_PENDING_MECHANICS | Authorized Molex distributor | Marking dimensions latch mate continuity | Mating Molex_430251200; terminal Molex_430300038 power; Molex_430300001 control/I2C; blockers: right-angle orientation and service clearance; pin-current allocation; I2C harness capacitance and pull-up validation |  | ELECTRICAL_COMPONENT | FITTED | header -40..125; housing -40..105 | CONTROLLED_PENDING_VERIFICATION
PWR-TVS-01 | PCB-PWR | D1 | Protection | Protected-bus transient clamp candidate | Littelfuse | SMBJ18A | SMB_DO-214AA | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | CANDIDATE_PENDING_SURGE_PROFILE | Authorized distributor | Marking clamp pulse and thermal sample | Rev.A freeze source POWER_COMPONENT_FREEZE_REV_A.csv; 18 V standoff; 20.0-22.1 V breakdown; 29.2 V max clamp; 600 W class; blockers: measured/source transient envelope; fuse coordination; thermal pulse test |  | ELECTRICAL_COMPONENT | FITTED | -65..150 | CONTROLLED_PENDING_VERIFICATION
PWR-FUSE-01 | PCB-PWR | F1 | Protection | PCB input fuse candidate | Littelfuse | 0451008.MRL | Nano2_451_6.1x2.69mm | 1 | 4 | 2 | 6 | 10 | 5 | 15 | 20 | 10 | 30 | SCALE_CEIL_FROM_20_BASELINE | COMMON | CANDIDATE_SELECTED_FOR_EVT_QUALIFICATION_NATIVE_VALUE_ECO_APPLIED_REPEAT_EVIDENCE_PASS_PHYSICAL_QUALIFICATION_PENDING | Authorized distributor | Marking continuity and controlled fault clearing | Rev.A freeze source POWER_COMPONENT_FREEZE_REV_A.csv; 8 A nominal; 0.0077 Ohm nominal cold resistance; 20.23 A2s nominal melting I2t; standard 25% continuous derating plus temperature rerating required; blockers: native value-only ECO applied with footprint placement topology and nets retained; repeat ERC/PDF/human hierarchy review PASS; +70 C derating; inrush; fault energy; 8.5 A connector ceiling; battery-side primary-fuse coordination |  | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
ASM-PWR | PCB-PWR | - | PCBA | Assembled protected power interface PCB | Dioneya controlled design | DIO-ASM-PWR-REV-A | assembled 4-layer power PCB build-to-print service scope; EVT DIM-003 90x60x1.6 mm and H1-H4 accepted; outer 2 oz target; inner 1 oz target; final stackup pending DFM | 1 | 4 | 2 | 6 | 10 | 2 | 12 | 20 | 2 | 22 | FIXED_LOT_MIN | COMMON | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_EMS_SELECTION_PENDING | Customer-selected qualified EMS; quotation and purchase outside the engineering repository | AOI functional high-current thermal | PRIMARY procurement track; internal assembled-article identity only; final copper routing DRC CAM DFM Review B and current thermal fault EOL scope remain mandatory before build |  | PCBA_SERVICE | N/A | N/A | CONTROLLED_CUSTOMER_RFQ_SCOPE
PCB-PWR | PCB-PWR | - | Bare PCB | Power interface bare PCB | Dioneya controlled design | DIO-PCB-PWR-REV-A | 4-layer FR-4 90x60x1.6 mm build-to-print fabrication scope; EVT DIM-003 and H1-H4 accepted; outer 2 oz target; inner 1 oz target; final stackup pending DFM | 1 | 4 | 2 | 6 | 10 | 2 | 12 | 20 | 2 | 22 | FIXED_LOT_MIN | COMMON | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_FAB_SELECTION_PENDING | Customer-selected qualified PCB fabricator; quotation and purchase outside the engineering repository | Copper thickness netlist high-current and Kelvin review | ALTERNATIVE quotation track only; internal bare-board identity only; selected copper and plating routing DRC CAM DFM serial mechanical revalidation and Review B remain mandatory before fabrication |  | BARE_PCB | N/A | N/A | CONTROLLED_CUSTOMER_RFQ_SCOPE
ASM-MIC | PCB-MIC | - | PCBA | Assembled identical microphone leaf PCB | Dioneya controlled design | DIO-ASM-MIC-REV-A | 2-layer microphone PCBA build-to-print service scope | 4 | 16 | 2 | 18 | 40 | 2 | 42 | 80 | 2 | 82 | FIXED_LOT_MIN | COMMON | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_EMS_SELECTION_PENDING | Customer-selected qualified EMS; quotation and purchase outside the engineering repository | AOI acoustic port inspection channel functional test | PRIMARY procurement track; internal assembled-article identity only; final Review B CAM DFM acoustic-port process and selected-lot EOL remain mandatory before build |  | PCBA_SERVICE | N/A | N/A | CONTROLLED_CUSTOMER_RFQ_SCOPE
PCB-MIC | PCB-MIC | - | Bare PCB | Microphone leaf bare PCB | Dioneya controlled design | DIO-PCB-MIC-REV-A | 2-layer FR-4 microphone PCB build-to-print fabrication scope | 4 | 16 | 2 | 18 | 40 | 2 | 42 | 80 | 2 | 82 | FIXED_LOT_MIN | COMMON | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_FAB_SELECTION_PENDING | Customer-selected qualified PCB fabricator; quotation and purchase outside the engineering repository | Outline hole position finish netlist | ALTERNATIVE quotation track only; internal bare-board identity only; panelization final Review B CAM DFM net test and acoustic opening control remain mandatory before fabrication |  | BARE_PCB | N/A | N/A | CONTROLLED_CUSTOMER_RFQ_SCOPE
MK1 | PCB-MIC | MK1 | Microphone | Digital bottom-port PDM MEMS microphone | TDK InvenSense | MMICT5838-00-012 | LGA-CAV-5 3.5x2.65x0.98 mm | 4 | 16 | 4 | 20 | 40 | 8 | 48 | 80 | 16 | 96 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_SAMPLE | TDK authorized channel and same lot requested | Marking lot acoustic sensitivity noise phase and port inspection | Exact orderable T5838 MPN; do not mix alternate MPN within station |  | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
C-MIC | PCB-MIC | PCB-MIC:C1 x4 | Passive | 100 nF 25 V X7R microphone VDD decoupling | TDK | CGA2B3X7R1E104K050BB | 0402 1005 metric | 4 | 16 | 40 | 56 | 40 | 40 | 80 | 80 | 40 | 120 | FIXED_LOT_MIN | COMMON | SELECTED_PENDING_SAMPLE | Traceable passive vendor | Value package reel label capacitance sample | One C1 per PCB-MIC leaf; exact native schematic reference and automotive-grade MLCC | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
J-MIC | PCB-MIC | PCB-MIC:J1 x4 | Connector | 6-position microphone leaf board header | Molex | 5040500691 | Pico-Lock 1.50 mm 6-circuit right-angle SMT | 4 | 16 | 3 | 19 | 40 | 6 | 46 | 80 | 12 | 92 | SCALE_CEIL_FROM_20_BASELINE | COMMON | MECHANICAL_AUTHORITY_FROZEN_PENDING_SI_AAD | Authorized Molex distributor | Mating pull test contact resistance continuity and temperature | Mating housing 5040510601; terminal 5040520098; pinout 1V8/GND/CLK/DATA/WAKE/AAD_CFG(THSEL); -40..105 C |  | ELECTRICAL_COMPONENT | FITTED | -40..105 | CONTROLLED_PENDING_VERIFICATION
BAT1 | SYSTEM | BT1 | Battery | Heated 12.8 V 50 Ah 640 Wh LiFePO4 battery with BMS | Epower Tech Co. Ltd | DIO-BAT-LFP-12V50-H-REV-A | 198x166x170 mm body; 182-184 mm including M8 studs | 1 | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 1 | 21 | SCALE_CEIL_FROM_20_BASELINE | COMMON | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Epower Tech supplier-configured heated article DIO-BAT-LFP-12V50-H-REV-A only; no substitution; PO must state heater option dimensions terminal geometry and applicable UN38.3 SDS and route documents | Reconcile PO packing slip quantity configuration and damage; check every unit dimensions polarity and OCV; verify heater threshold and current then capacity DCIR BMS charge inhibit and cold behavior during assembly and EVT | EVT baseline is 50 Ah and 640 Wh; 80 percent usable energy is 512 Wh and supports a 0.711 W 30-day average before heater consumption; accepted EVT minimum is -20 C; charge only after the cells reach the supplier-approved threshold; -40 C remains a post-EVT series qualification target |  | SYSTEM_ITEM | FITTED | -20..60 heated operation; 0..55 charge; -20..60 discharge | CONTROLLED
PV1 | SYSTEM | PV1 | Solar panel | 80 W 12 V monocrystalline outdoor solar panel | SLD Tech / Solarland | SLP080S-12M | 1475x342x40 mm framed 36-cell panel | 1 | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 1 | 21 | SCALE_CEIL_FROM_20_BASELINE | COMMON | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | SLD Tech or authorized distributor; exact SLP080S-12M only; no substitution | Reconcile PO packing slip quantity and visible transit damage; measure installed-unit Voc and perform IV insulation wet-leakage cold-Voc bracket cable and transport validation during assembly and EVT | 80 W baseline; Vmp 18.46 V Imp 4.33 A Voc 22.52 V Isc 4.56 A and -40..85 C; physical panel and mechanical-system qualification remain production-release gates |  | SYSTEM_ITEM | FITTED | -40..85 | CONTROLLED
MPPT1 | SYSTEM | U-MPPT | Controller | External SmartSolar 10 A LiFePO4 MPPT controller | Victron Energy | SCC075010060R | 100x113x40 mm IP43 electronics IP22 terminals | 1 | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 1 | 21 | SCALE_CEIL_FROM_20_BASELINE | COMMON | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Victron authorized distributor; exact SCC075010060R only; no substitution | Reconcile PO packing slip quantity and visible damage; bind article and firmware at installation; export configuration and test charge profile reverse current quiescent thermal and cutoff during assembly EOL and EVT | SmartSolar MPPT 75/10; 12/24 V 10 A 75 V and 145 W nominal PV at 12 V; pair with MPPT-TEMP in one VE.Smart network and set low-temperature cutoff to 0 C; -30..60 C controller range and exposed terminals require enclosure and cold-system qualification |  | SYSTEM_ITEM | FITTED | -30..60 | CONTROLLED
MPPT-TEMP | SYSTEM | TS-BAT1 | Sensor | Wireless battery voltage and temperature sensor for MPPT | Victron Energy | SBS050150200 | Smart Battery Sense long range up to 10 m radio with 0.45 m leads and M10 eyelets | 1 | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 1 | 21 | SCALE_CEIL_FROM_20_BASELINE | COMMON | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Victron authorized distributor; exact SBS050150200 only; no substitution | Reconcile PO packing slip quantity and visible damage; verify 0.45 m lead M10 eyelets retention on the battery M8 terminals accuracy VE.Smart pairing cutoff reconnect and network retention during station assembly EOL and cold EVT | Required for SmartSolar low-temperature inhibit; attach to DIO-BAT-LFP-12V50-H-REV-A body and M8 terminals through an approved retention stack; official operating range is -10..60 C and 10 m denotes wireless range not lead length; prove temperature reception fallback below -10 C charge cutoff warm-up threshold reconnect and cold-system behavior before production release |  | SYSTEM_ITEM | FITTED | -10..60 | CONTROLLED
ANT-CELL | SYSTEM | AE1 | Antenna | Outdoor wideband cellular antenna with SMA male cable | Taoglas | G30.B.108111 | IP67 screw-mount dome with 1 m cable and SMA(M) | 1 | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 2 | 22 | SCALE_CEIL_FROM_20_BASELINE | COMMON | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Taoglas or established distributor; exact G30.B.108111 only; no substitution; resolve manufacturer page cable-construction discrepancy on quote | Reconcile PO packing slip quantity and visible damage; verify cable length connector mate route seal installed VSWR loss attach and coexistence during assembly EOL and EVT | 698-960 and 1710-2700 MHz manufacturer headline coverage for BG95-M3; SMA(M) mates outside the housing to RF-PIGTAIL bulkhead; manufacturer page conflicts on RG-316 versus RG-178 cable wording so the ordered construction must be recorded without inferring a value |  | SYSTEM_ITEM | FITTED | -40..85 | CONTROLLED
ANT-GNSS | SYSTEM | AE2 | Antenna | Outdoor active multi-GNSS L1 antenna with SMA male cable | Taoglas | AA.166.A.301111 | IP67 magnetic 37.8x40.4x10 mm with 3 m RG174 SMA(M) | 1 | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 2 | 22 | SCALE_CEIL_FROM_20_BASELINE | COMMON | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Taoglas or established distributor; exact AA.166.A.301111 only; no substitution | Reconcile PO packing slip quantity and visible damage; verify connector cable route current at 3.3 V receiver sensitivity PPS mounting and coexistence during assembly EOL and EVT | 1559-1610 MHz and 3-5 V active antenna; SMA(M) mates outside the housing to RF-PIGTAIL bulkhead; project current limit is at most 50 mA and installed sensitivity remains a physical production-release gate |  | SYSTEM_ITEM | FITTED | -40..85 | CONTROLLED
ANT-LORA | SYSTEM | AE3 | Antenna | Outdoor RU868 terminal antenna with SMA male | Taoglas | TI.89.B.2111W | IP67 terminal antenna 180x13 mm SMA(M) | 1 | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 2 | 22 | SCALE_CEIL_FROM_20_BASELINE | RU868_PILOT | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Taoglas or established distributor; exact TI.89.B.2111W only; no substitution | Reconcile PO packing slip quantity and visible damage; verify connector mate installed VSWR conducted power sensitivity coexistence and RU868 radiated compliance during assembly EOL and EVT | 860-930 MHz with 862-874 MHz measured 868 MHz range; SMA(M) mounts on RF-PIGTAIL bulkhead; installed RF and regulatory evidence remain production-release gates |  | SYSTEM_ITEM | FITTED | -40..85 | CONTROLLED
RF-PIGTAIL | SYSTEM | J8/J9/J10 cable | RF cable | Internal 150 mm U.FL-compatible right-angle to SMA female bulkhead pigtail | Taoglas | CAB.0243 | 1.13 mm micro-coax 150 mm MHF I/U.FL-compatible R/A to waterproof SMA(F) bulkhead | 3 | 12 | 2 | 14 | 30 | 3 | 33 | 60 | 6 | 66 | SCALE_CEIL_FROM_20_BASELINE | COMMON | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Taoglas or established distributor; exact CAB.0243 only; no substitution | Reconcile PO packing slip quantity and visible damage; verify every installed cable continuity polarity length and route then mate retention bend seal torque temperature and VNA performance during assembly EOL and EVT | One identical pigtail on J8 J9 and J10; Taoglas SPE-24-8-147-A states I-PEX MHF I (U.FL compatible) to normal-polarity SMA(F) bulkhead with 150 mm 1.13 mm coax minimum bend radius 6.8 mm and published -60..200 C operating range; product page calls the bulkhead waterproof but gives no numeric IP class; installed physical validation remains open |  | SYSTEM_ITEM | FITTED | -60..200 | CONTROLLED
HARNESS | SYSTEM | - | Harness | Complete labeled harness set | Dioneya controlled design | DIO-HARNESS-SET-REV-A | Controlled labeled station harness set Rev.A | 1 | 4 | 1 | 5 | 10 | 1 | 11 | 20 | 2 | 22 | SCALE_CEIL_FROM_20_BASELINE | COMMON | CONTROLLED_INTERNAL_ARTICLE_PHYSICAL_RELEASE_PENDING | Customer-selected qualified harness assembler; build only to the controlled drawing and schedule | 100 percent continuity polarity pull sample | Internal harness-set identity binds the controlled pinout drawing schedule housings and contacts; final cut lengths exact wire AVL crimp tooling physical electrical SI thermal FAI and selected assembler remain release gates |  | SYSTEM_ITEM | FITTED | -40..105 selected connector/contact envelope; station -40..70 qualification pending | CONTROLLED_BUILD_TO_PRINT_IDENTITY
HSG-VC | SYSTEM | HSG1 | Housing | Vacuum-cast polyurethane housing set | Dioneya controlled design | DIO-HSG-VC-REV-A | Vacuum-cast polyurethane housing set build-to-print scope | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | VACUUM_CASTING_PRIMARY | CONTROLLED_INTERNAL_ARTICLE_MECHANICAL_RELEASE_PENDING | Customer-selected qualified vacuum-casting supplier; quotation and purchase outside the engineering repository | FAI dimensions material cure finish inserts leak fit acoustic and RF checks | Internal housing-set identity only; released source geometry material shrink inserts seals FAI leak fit acoustic RF and environmental evidence remain mandatory before build |  | MECHANICAL_OPTION | N/A | -40..70 target; material and assembled-housing qualification pending | CONTROLLED_CUSTOMER_RFQ_SCOPE
HSG-3D | SYSTEM | HSG1 | Housing | 3D-printed fallback housing set | TBD | TBD | Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | THREE_D_PRINT_FALLBACK | SOURCE_PACKAGE_REQUIRED | Qualified print supplier or controlled FlashForge 5M Pro process | Engineering sample dimensions material finish leak fit acoustic and RF checks | Conditional selected-lot demand is activated only by ECO; 4 10 and 20 station scenarios remain zero until activation |  | MECHANICAL_OPTION | N/A | OPEN | CONDITIONAL_NOT_RELEASED
HSG-IM | SYSTEM | HSG1 | Housing | Injection-molding source package and DFM | TBD | TBD | Source_data | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | INJECTION_MOLDING_FUTURE | SOURCE_PACKAGE_REQUIRED | Qualified mold manufacturer for DFM quotation | Source audit wall draft ribs bosses parting ejector shrink material and tooling concept | No tooling or physical pilot housing without separate authorization |  | MECHANICAL_OPTION | N/A | OPEN | CONDITIONAL_NOT_RELEASED
U16 | PCB-MAIN | U16 | Logic | BG95 UART/status 1.8V/3.3V translator | Texas Instruments | SN74AXC8T245PWR | TSSOP-24 | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_UART_POWER_SAMPLE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A MAIN freeze; blockers: UART/RI/STATUS timing; partial-power isolation; burst ground-offset margin; measured current |  | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
U17 | PCB-MAIN | U17 | Logic | T5838 four-channel AAD WAKE OR aggregation | Texas Instruments | SN74LVC32APWR | TSSOP-14 | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_AAD_WAKE_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A MAIN freeze; blockers: quiescent-current measurement; individual and aggregate wake latency; false-wake and open-harness tests |  | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
U18 | PCB-MAIN | U18 | Logic | T5838 aggregated WAKE 1.8V-to-3.3V translator | Texas Instruments | SN74AXC1T45DRLR | SOT-5X3_6 | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_AAD_WAKE_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A MAIN freeze; blockers: wake edge and Stop-mode latency; partial-power test; quiescent-current measurement |  | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
Q-MODEM-PWRKEY | PCB-MAIN | Q1 | Transistor | BG95 PWRKEY open-collector driver | Nexperia | MMBT3904,215 | SOT23 | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_CONTROL_TIMING_SAMPLE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A MAIN freeze; blockers: 500-1000 ms pulse; collector-low margin; cold-start and shutdown timing |  | ELECTRICAL_COMPONENT | FITTED | -65..150 | CONTROLLED_PENDING_VERIFICATION
Q-MODEM-RESET | PCB-MAIN | Q2 | Transistor | BG95 RESET_N open-collector driver | Nexperia | MMBT3904,215 | SOT23 | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_CONTROL_TIMING_SAMPLE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A MAIN freeze; blockers: 2-3.8 s reset pulse; collector-low margin; reset recovery and mutual exclusion |  | ELECTRICAL_COMPONENT | FITTED | -65..150 | CONTROLLED_PENDING_VERIFICATION
Q-SIM-MUX-EN | PCB-MAIN | Q3 | Transistor | Dual-SIM mux boot-safe enable inverter | Nexperia | MMBT3904,215 | SOT23 | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_SIM_SAFE_STATE_SAMPLE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A MAIN freeze; blockers: reset and brownout High-Z behavior; U13 EN low margin; 100 slot-change cycles |  | ELECTRICAL_COMPONENT | FITTED | -65..150 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C1 | PCB-MAIN | C1 | Capacitor | U1 VDD pin 11 local bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U1 pin 11 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C2 | PCB-MAIN | C2 | Capacitor | U1 VDD pin 27 local bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U1 pin 27 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C3 | PCB-MAIN | C3 | Capacitor | U1 VDD pin 51 local bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U1 pin 51 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C4 | PCB-MAIN | C4 | Capacitor | U1 VDD pin 75 local bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U1 pin 75 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C5 | PCB-MAIN | C5 | Capacitor | U1 VDD pin 100 local bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U1 pin 100 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C6 | PCB-MAIN | C6 | Capacitor | U1 package bulk | Murata | GRM188R61A106KE69D | 0603 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Verify effective capacitance after DC bias | 10 uF 10 V X5R | ELECTRICAL_COMPONENT | FITTED | -55..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C7 | PCB-MAIN | C7 | Capacitor | U1 VBAT pin 6 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; No backup cell in Rev.A | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C8 | PCB-MAIN | C8 | Capacitor | U1 VDDA pin 21 high frequency bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Single supply analog domain | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C9 | PCB-MAIN | C9 | Capacitor | U1 VDDA pin 21 local bulk | Murata | GRM155R61C105KA12D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Single supply analog domain | 1 uF 16 V X5R | ELECTRICAL_COMPONENT | FITTED | -55..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C10 | PCB-MAIN | C10 | Capacitor | U1 VREF+ pin 20 high frequency bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=VREF+;2=GND; VREF+ tied to VDDA | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C11 | PCB-MAIN | C11 | Capacitor | U1 VREF+ pin 20 local bulk | Murata | GRM155R61C105KA12D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=VREF+;2=GND; VREFBUF disabled | 1 uF 16 V X5R | ELECTRICAL_COMPONENT | FITTED | -55..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C12 | PCB-MAIN | C12 | Capacitor | U1 VDDUSB pin 73 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at VDDUSB | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C13 | PCB-MAIN | C13 | Capacitor | U1 VDDSMPS pin 47 local input capacitor | Murata | GRM188R61A106KE69D | 0603 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Verify ESR below 10 mOhm at 3 MHz and effective capacitance | 10 uF 10 V X5R | ELECTRICAL_COMPONENT | FITTED | -55..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C14 | PCB-MAIN | C14 | Capacitor | U1 VDD11 pin 49 core capacitor | Murata | GRM155R61A225KE15D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=VCORE_1V1;2=GND; VCORE must not power external circuitry | 2.2 uF 10 V X5R | ELECTRICAL_COMPONENT | FITTED | -55..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C15 | PCB-MAIN | C15 | Capacitor | U1 VDD11 pin 98 core capacitor | Murata | GRM155R61A225KE15D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=VCORE_1V1;2=GND; VCORE must not power external circuitry | 2.2 uF 10 V X5R | ELECTRICAL_COMPONENT | FITTED | -55..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C16 | PCB-MAIN | C16 | Capacitor | U1 VDD11 pin 49 optional high frequency position | Murata | GRM155R71E104KE14D | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=VCORE_1V1;2=GND; Populate only by signed power integrity change | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | DNP | -55..125 | CONTROLLED_DNP
MAIN-010-C17 | PCB-MAIN | C17 | Capacitor | U1 VDD11 pin 98 optional high frequency position | Murata | GRM155R71E104KE14D | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=VCORE_1V1;2=GND; Populate only by signed power integrity change | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | DNP | -55..125 | CONTROLLED_DNP
MAIN-010-C18 | PCB-MAIN | C18 | Capacitor | U1 normal reset filter | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=NRST;2=GND; Keep reset path short | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C19 | PCB-MAIN | C19 | Capacitor | PCB-MAIN 3V3 entry bulk | Murata | GRM21BR61A226ME44L | 0805 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Verify rail transient and DC bias in Review A | 22 uF 10 V X5R | ELECTRICAL_COMPONENT | FITTED | -55..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C20 | PCB-MAIN | C20 | Capacitor | PCB-MAIN 1V8 entry bulk | Murata | GRM188R61A106KE69D | 0603 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=1V8_MIC;2=GND; Verify microphone burst and wake current | 10 uF 10 V X5R | ELECTRICAL_COMPONENT | FITTED | -55..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C21 | PCB-MAIN | C21 | Capacitor | U2 VCC pin 2 high frequency bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U2 pin 2 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C22 | PCB-MAIN | C22 | Capacitor | U2 VCC pin 2 local bulk | Murata | GRM155R61C105KA12D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U2 pin 2 | 1 uF 16 V X5R | ELECTRICAL_COMPONENT | FITTED | -55..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C23 | PCB-MAIN | C23 | Capacitor | U3 VDD pin 9 high frequency bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U3 pin 9 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C24 | PCB-MAIN | C24 | Capacitor | U3 VDD pin 9 local bulk | Murata | GRM188R61A106KE69D | 0603 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Verify motion sensor rail transient | 10 uF 10 V X5R | ELECTRICAL_COMPONENT | FITTED | -55..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C25 | PCB-MAIN | C25 | Capacitor | U3 VDD_IO pin 10 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U3 pin 10 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C26 | PCB-MAIN | C26 | Capacitor | U4 VDD pin 3 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Keep away from thermal gradients | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C27 | PCB-MAIN | C27 | Capacitor | U7 VCCA pin 1 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=1V8_MIC;2=GND; Place at U7 pin 1 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C28 | PCB-MAIN | C28 | Capacitor | U7 VCCB pin 23 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U7 pin 23 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C29 | PCB-MAIN | C29 | Capacitor | U7 VCCB pin 24 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U7 pin 24 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C30 | PCB-MAIN | C30 | Capacitor | U17 VCC pin 14 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=1V8_MIC;2=GND; Place at U17 pin 14 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C31 | PCB-MAIN | C31 | Capacitor | U18 VCCA pin 1 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=1V8_MIC;2=GND; Place at U18 pin 1 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C32 | PCB-MAIN | C32 | Capacitor | U18 VCCB pin 6 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U18 pin 6 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C33 | PCB-MAIN | C33 | Capacitor | U16 VCCA pin 1 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=U8_VDD_EXT_1V8;2=GND_MODEM; Place at U16 pin 1 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C34 | PCB-MAIN | C34 | Capacitor | U16 VCCB pin 23 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND_MODEM; Place at U16 pin 23 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C35 | PCB-MAIN | C35 | Capacitor | U16 VCCB pin 24 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND_MODEM; Place at U16 pin 24 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C36 | PCB-MAIN | C36 | Capacitor | U8 VBAT_BB local burst bulk | KEMET | T520D107M006ATE015 | 7343-31 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM_BB;2=GND_MODEM; Verify voltage droop and ripple current | 100 uF 6.3 V 15 mOhm polymer | ELECTRICAL_COMPONENT | FITTED | -55..105 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C37 | PCB-MAIN | C37 | Capacitor | U8 VBAT_BB broadband bypass | Murata | GRM155R71E224KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM_BB;2=GND_MODEM; Place in Quectel value sequence | 220 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C38 | PCB-MAIN | C38 | Capacitor | U8 VBAT_BB broadband bypass | Murata | GRM155R71E473KA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM_BB;2=GND_MODEM; Place in Quectel value sequence | 47 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C39 | PCB-MAIN | C39 | Capacitor | U8 VBAT_BB RF bypass | Murata | GRM1555C1H151JA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM_BB;2=GND_MODEM; Place in Quectel value sequence | 150 pF 50 V C0G | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C40 | PCB-MAIN | C40 | Capacitor | U8 VBAT_BB RF bypass | Murata | GRM1555C1H101JA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM_BB;2=GND_MODEM; Place in Quectel value sequence | 100 pF 50 V C0G | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C41 | PCB-MAIN | C41 | Capacitor | U8 VBAT_BB RF bypass | Murata | GRM1555C1H680JA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM_BB;2=GND_MODEM; Place in Quectel value sequence | 68 pF 50 V C0G | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C42 | PCB-MAIN | C42 | Capacitor | U8 VBAT_BB RF bypass | Murata | GRM1555C1H330JA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM_BB;2=GND_MODEM; Place in Quectel value sequence | 33 pF 50 V C0G | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C43 | PCB-MAIN | C43 | Capacitor | U8 VBAT_BB RF bypass | Murata | GRM1555C1H100JA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM_BB;2=GND_MODEM; Place in Quectel value sequence | 10 pF 50 V C0G | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C44 | PCB-MAIN | C44 | Capacitor | U8 VBAT_RF local burst bulk | KEMET | T520D107M006ATE015 | 7343-31 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM_RF;2=GND_MODEM; Verify voltage droop and ripple current | 100 uF 6.3 V 15 mOhm polymer | ELECTRICAL_COMPONENT | FITTED | -55..105 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C45 | PCB-MAIN | C45 | Capacitor | U8 VBAT_RF broadband bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM_RF;2=GND_MODEM; Place at RF VBAT pads | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C46 | PCB-MAIN | C46 | Capacitor | U8 VBAT_RF RF bypass | Murata | GRM1555C1H330JA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM_RF;2=GND_MODEM; Place at RF VBAT pads | 33 pF 50 V C0G | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C47 | PCB-MAIN | C47 | Capacitor | U8 VBAT_RF RF bypass | Murata | GRM1555C1H100JA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM_RF;2=GND_MODEM; Place at RF VBAT pads | 10 pF 50 V C0G | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C48 | PCB-MAIN | C48 | Capacitor | Q1 collector and U8 PWRKEY pulse filter | Murata | GRM155R71E103KA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=U8_PWRKEY_N;2=GND_MODEM; No corresponding large capacitor on RESET_N | 10 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C49 | PCB-MAIN | C49 | Capacitor | U13 VCC pin 8 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND_MODEM; Place at U13 pin 8 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C50 | PCB-MAIN | C50 | Capacitor | J6 local selected SIM supply bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM1_VDD_CONN;2=GND_MODEM; Place connector side of series path | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C51 | PCB-MAIN | C51 | Capacitor | J7 local selected SIM supply bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM2_VDD_CONN;2=GND_MODEM; Place connector side of series path | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C52 | PCB-MAIN | C52 | Capacitor | J6 card detect hardware debounce | Murata | GRM155R71E103KA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM1_DET;2=GND_MODEM; Firmware debounce remains at least 20 ms | 10 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C53 | PCB-MAIN | C53 | Capacitor | J7 card detect hardware debounce | Murata | GRM155R71E103KA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM2_DET;2=GND_MODEM; Firmware debounce remains at least 20 ms | 10 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C54 | PCB-MAIN | C54 | Capacitor | J6 reset shunt tuning position | Murata | GRM1555C1H330JA01D | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM1_RST_CONN;2=GND_MODEM; Populate only from signed SIM edge evidence | 33 pF 50 V C0G | ELECTRICAL_COMPONENT | DNP | -55..125 | CONTROLLED_DNP
MAIN-010-C55 | PCB-MAIN | C55 | Capacitor | J6 clock shunt tuning position | Murata | GRM1555C1H330JA01D | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM1_CLK_CONN;2=GND_MODEM; Populate only from signed SIM edge evidence | 33 pF 50 V C0G | ELECTRICAL_COMPONENT | DNP | -55..125 | CONTROLLED_DNP
MAIN-010-C56 | PCB-MAIN | C56 | Capacitor | J6 data shunt tuning position | Murata | GRM1555C1H330JA01D | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM1_DATA_CONN;2=GND_MODEM; Populate only from signed SIM edge evidence | 33 pF 50 V C0G | ELECTRICAL_COMPONENT | DNP | -55..125 | CONTROLLED_DNP
MAIN-010-C57 | PCB-MAIN | C57 | Capacitor | J7 reset shunt tuning position | Murata | GRM1555C1H330JA01D | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM2_RST_CONN;2=GND_MODEM; Populate only from signed SIM edge evidence | 33 pF 50 V C0G | ELECTRICAL_COMPONENT | DNP | -55..125 | CONTROLLED_DNP
MAIN-010-C58 | PCB-MAIN | C58 | Capacitor | J7 clock shunt tuning position | Murata | GRM1555C1H330JA01D | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM2_CLK_CONN;2=GND_MODEM; Populate only from signed SIM edge evidence | 33 pF 50 V C0G | ELECTRICAL_COMPONENT | DNP | -55..125 | CONTROLLED_DNP
MAIN-010-C59 | PCB-MAIN | C59 | Capacitor | J7 data shunt tuning position | Murata | GRM1555C1H330JA01D | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM2_DATA_CONN;2=GND_MODEM; Populate only from signed SIM edge evidence | 33 pF 50 V C0G | ELECTRICAL_COMPONENT | DNP | -55..125 | CONTROLLED_DNP
MAIN-010-C60 | PCB-MAIN | C60 | Capacitor | U9 VCC pin 8 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U9 pin 8 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C61 | PCB-MAIN | C61 | Capacitor | U9 VCC pin 8 local bulk | Murata | GRM188R61A106KE69D | 0603 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Total feed resistance must remain at most 0.2 Ohm | 10 uF 10 V X5R | ELECTRICAL_COMPONENT | FITTED | -55..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C62 | PCB-MAIN | C62 | Capacitor | U9 V_IO pin 7 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U9 pin 7 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C63 | PCB-MAIN | C63 | Capacitor | Figure 38 antenna current sense filter C14 | Murata | GRM155R71C103KA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=GNSS_ANT_SHORT_N;2=GND; Keep at R62 and L2 junction | 10 nF 16 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C64 | PCB-MAIN | C64 | Capacitor | Figure 38 external RF DC block C18 | Murata | GRM1555C1E470JA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=GNSS_RF_ANT_BIASED;2=GNSS_RF_DC_BLOCK; Series before FL1 input C | 47 pF 25 V C0G | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C65 | PCB-MAIN | C65 | Capacitor | U5 local supply bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=GNSS_ANT_BIAS_RAW;2=GND; Place at U5 pin 4 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C66 | PCB-MAIN | C66 | Capacitor | U10 VCC pin 9 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U10 pin 9 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C67 | PCB-MAIN | C67 | Capacitor | U10 VCC pin 9 local bulk | Murata | GRM188R61A106KE69D | 0603 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Verify transmit burst droop | 10 uF 10 V X5R | ELECTRICAL_COMPONENT | FITTED | -55..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C68 | PCB-MAIN | C68 | Capacitor | U10 reset RC capacitor | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=LORA_RESET_N;2=GND; Place at U10 pin 15 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C69 | PCB-MAIN | C69 | Capacitor | LoRa pi network module-side shunt | Murata | GRM1555C1H100JA01D | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=LORA_RF_MODULE;2=GND; Populate only from signed VNA evidence | 10 pF 50 V C0G | ELECTRICAL_COMPONENT | DNP | -55..125 | CONTROLLED_DNP
MAIN-010-C70 | PCB-MAIN | C70 | Capacitor | LoRa pi network connector-side shunt | Murata | GRM1555C1H100JA01D | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=LORA_RF_ANT;2=GND; Populate only from signed VNA evidence | 10 pF 50 V C0G | ELECTRICAL_COMPONENT | DNP | -55..125 | CONTROLLED_DNP
MAIN-010-C71 | PCB-MAIN | C71 | Capacitor | U11 VDD pin 28 bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U11 pin 28 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C72 | PCB-MAIN | C72 | Capacitor | U11 VDD and VDDH local bulk | Murata | GRM188R61A106KE69D | 0603 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Normal-voltage mode with VDD and VDDH joined | 10 uF 10 V X5R | ELECTRICAL_COMPONENT | FITTED | -55..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C73 | PCB-MAIN | C73 | Capacitor | U6 local supply bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place at U6 pin 5 | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C74 | PCB-MAIN | C74 | Capacitor | J12 microSD local bypass | Murata | GRM155R71E104KE14D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; J12 VDD connector-side | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C75 | PCB-MAIN | C75 | Capacitor | J12 microSD local bulk | Murata | GRM188R61A106KE69D | 0603 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Verify insertion transient | 10 uF 10 V X5R | ELECTRICAL_COMPONENT | FITTED | -55..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C76 | PCB-MAIN | C76 | Capacitor | J12 card detect hardware debounce | Murata | GRM155R71E103KA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SD_DET;2=GND; Firmware debounce remains mandatory | 10 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C77 | PCB-MAIN | C77 | Capacitor | Controlled USB shield AC bond | Murata | GRM155R72A472KA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=USB_SHIELD;2=GND; Parallel with R97 and optional R98 | 4.7 nF 100 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C78 | PCB-MAIN | C78 | Capacitor | Tamper input hardware debounce after R100 | Murata | GRM155R71E103KA01D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=TAMPER_IN_U1;2=GND; Firmware debounce and open-circuit alarm remain mandatory | 10 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-C79 | PCB-MAIN | C79 | Capacitor | Cellular pi network module-side shunt | Murata | GRM1555C1H100JA01D | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_RF;2=GND_MODEM; Populate only from signed VNA evidence | 10 pF 50 V C0G | ELECTRICAL_COMPONENT | DNP | -55..125 | CONTROLLED_DNP
MAIN-010-C80 | PCB-MAIN | C80 | Capacitor | Cellular pi network connector-side shunt | Murata | GRM1555C1H100JA01D | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_RF_ANT;2=GND_MODEM; Populate only from signed VNA evidence | 10 pF 50 V C0G | ELECTRICAL_COMPONENT | DNP | -55..125 | CONTROLLED_DNP
MAIN-010-R1 | PCB-MAIN | R1 | Resistor | U1 normal reset pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=NRST; Works with C18 and direct SWD fixture access | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R2 | PCB-MAIN | R2 | Resistor | U1 BOOT0 normal-state pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=BOOT0;2=GND; Fixture may drive only while reset is asserted | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R3 | PCB-MAIN | R3 | Resistor | Rev.A strap bit zero fitted pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=HW_REV0;2=GND; Rev.A encoding is binary 00 | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R4 | PCB-MAIN | R4 | Resistor | Revision bit zero alternate pull-up | Panasonic | ERJ-2RKF1003X | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=HW_REV0; Never populate together with R3 | 100 kOhm 1% | ELECTRICAL_COMPONENT | DNP | -55..155 | CONTROLLED_DNP
MAIN-010-R5 | PCB-MAIN | R5 | Resistor | Rev.A strap bit one fitted pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=HW_REV1;2=GND; Rev.A encoding is binary 00 | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R6 | PCB-MAIN | R6 | Resistor | Revision bit one alternate pull-up | Panasonic | ERJ-2RKF1003X | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=HW_REV1; Never populate together with R5 | 100 kOhm 1% | ELECTRICAL_COMPONENT | DNP | -55..155 | CONTROLLED_DNP
MAIN-010-R7 | PCB-MAIN | R7 | Resistor | U2 chip-select safe-state pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=NOR_NCS_U2; Device remains deselected during MCU reset | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R8 | PCB-MAIN | R8 | Resistor | OCTOSPI clock source damping at U1 | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=NOR_CLK_U1;2=NOR_CLK_U2; Review A may change only from measured SI evidence | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R9 | PCB-MAIN | R9 | Resistor | OCTOSPI IO0 series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=NOR_IO0_U1;2=NOR_IO0_U2; Review A may change only from measured SI evidence | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R10 | PCB-MAIN | R10 | Resistor | OCTOSPI IO1 series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=NOR_IO1_U1;2=NOR_IO1_U2; Review A may change only from measured SI evidence | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R11 | PCB-MAIN | R11 | Resistor | OCTOSPI IO2 series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=NOR_IO2_U1;2=NOR_IO2_U2; Review A may change only from measured SI evidence | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R12 | PCB-MAIN | R12 | Resistor | OCTOSPI IO3 series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=NOR_IO3_U1;2=NOR_IO3_U2; Review A may change only from measured SI evidence | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R13 | PCB-MAIN | R13 | Resistor | Authoritative PCB-MAIN I2C2 SCL pull-up | Panasonic | ERJ-2RKF2201X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=I2C2_SCL_BUS; PCB-PWR pull-up footprint remains DNP | 2.2 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R14 | PCB-MAIN | R14 | Resistor | Authoritative PCB-MAIN I2C2 SDA pull-up | Panasonic | ERJ-2RKF2201X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=I2C2_SDA_BUS; PCB-PWR pull-up footprint remains DNP | 2.2 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R15 | PCB-MAIN | R15 | Resistor | I2C2 SCL master-side series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=I2C2_SCL_U1;2=I2C2_SCL_BUS; Place adjacent to U1 | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R16 | PCB-MAIN | R16 | Resistor | I2C2 SDA master-side series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=I2C2_SDA_U1;2=I2C2_SDA_BUS; Place adjacent to U1 | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R17 | PCB-MAIN | R17 | Resistor | PDM clock source termination at U7 | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=PDM_CLK_1V8_U7;2=PDM_CLK_1V8_FANOUT; Verify all four harness edges and skew | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R18 | PCB-MAIN | R18 | Resistor | AAD configuration fanout damping at U7 | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=AAD_CFG_1V8_U7;2=AAD_CFG_1V8_FANOUT; Verify one-wire writes on all four leaves | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R19 | PCB-MAIN | R19 | Resistor | MIC1 WAKE inactive-state pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=MIC_WAKE1;2=GND; No connector means inactive LOW | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R20 | PCB-MAIN | R20 | Resistor | MIC2 WAKE inactive-state pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=MIC_WAKE2;2=GND; No connector means inactive LOW | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R21 | PCB-MAIN | R21 | Resistor | MIC3 WAKE inactive-state pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=MIC_WAKE3;2=GND; No connector means inactive LOW | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R22 | PCB-MAIN | R22 | Resistor | MIC4 WAKE inactive-state pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=MIC_WAKE4;2=GND; No connector means inactive LOW | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R23 | PCB-MAIN | R23 | Resistor | U18 MCU-side inactive-state pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=MIC_WAKE;2=GND; Keeps PA8 low during partial power | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R24 | PCB-MAIN | R24 | Resistor | Q1 base current limiter | Panasonic | ERJ-2RKF4701X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_PWRKEY_CMD;2=Q1_BASE; Q1 pin 1 endpoint | 4.7 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R25 | PCB-MAIN | R25 | Resistor | Q1 base-emitter off-state pull | Panasonic | ERJ-2RKF4702X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=Q1_BASE;2=GND_MODEM; Prevents unintended PWRKEY assertion | 47 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R26 | PCB-MAIN | R26 | Resistor | Q2 base current limiter | Panasonic | ERJ-2RKF4701X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_RESET_N_CMD;2=Q2_BASE; Q2 pin 1 endpoint | 4.7 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R27 | PCB-MAIN | R27 | Resistor | Q2 base-emitter off-state pull | Panasonic | ERJ-2RKF4702X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=Q2_BASE;2=GND_MODEM; Prevents unintended RESET_N assertion | 47 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R28 | PCB-MAIN | R28 | Resistor | Modem receive path idle-HIGH pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=CELL_TX_U16; U16 B5 side | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R29 | PCB-MAIN | R29 | Resistor | Modem DTR default-awake pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_DTR_U16;2=GND_MODEM; U16 B6 side | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R30 | PCB-MAIN | R30 | Resistor | U8 UART transmit idle-HIGH pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=U8_VDD_EXT_1V8;2=U8_MAIN_TXD_1V8; U16 A1 side | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R31 | PCB-MAIN | R31 | Resistor | U8 ring indicator inactive-HIGH pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=U8_VDD_EXT_1V8;2=U8_MAIN_RI_1V8; U16 A3 side | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R32 | PCB-MAIN | R32 | Resistor | MCU receive inactive-HIGH pull-up | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=CELL_RX_U16; U16 B1 side | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R33 | PCB-MAIN | R33 | Resistor | MCU RI inactive-HIGH pull-up | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=CELL_RI_U16; U16 B3 side | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R34 | PCB-MAIN | R34 | Resistor | Modem status inactive-LOW pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_STATUS_U16;2=GND_MODEM; U16 B2 side | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R35 | PCB-MAIN | R35 | Resistor | BG95 USB boot normal-state pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_USB_BOOT_1V8;2=GND_MODEM; Fixture drive is current limited through R38 | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R36 | PCB-MAIN | R36 | Resistor | BG95 debug TX source-series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_DBG_TXD_U8;2=CELL_DBG_TXD_TP; Fixture is 1.8 V tolerant | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R37 | PCB-MAIN | R37 | Resistor | BG95 debug RX fixture-side damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_DBG_RXD_TP;2=CELL_DBG_RXD_U8; Fixture output only after VREF valid | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R38 | PCB-MAIN | R38 | Resistor | BG95 USB boot fixture current limiter | Panasonic | ERJ-2RKF1001X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_USB_BOOT_TP;2=CELL_USB_BOOT_1V8; Fixture normally high impedance | 1 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R39 | PCB-MAIN | R39 | Resistor | BG95 USB D+ controlled series link | Panasonic | ERJ-2GE0R00X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_USB_DP_U8;2=CELL_USB_DP_TP; Preserve 90 Ohm differential pair | 0 Ohm | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R40 | PCB-MAIN | R40 | Resistor | BG95 USB D- controlled series link | Panasonic | ERJ-2GE0R00X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_USB_DM_U8;2=CELL_USB_DM_TP; Preserve 90 Ohm differential pair | 0 Ohm | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R41 | PCB-MAIN | R41 | Resistor | BG95 debug reference sense isolation | Panasonic | ERJ-2RKF1001X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=U8_VDD_EXT_1V8;2=CELL_DBG_VREF_TP; VTREF contact never sources station power | 1 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R42 | PCB-MAIN | R42 | Resistor | U8 VBAT_RF star branch link | Panasonic | ERJ-2GE0R00X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM;2=3V8_MODEM_RF; Place immediately before U8 RF branch | 0 Ohm | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R43 | PCB-MAIN | R43 | Resistor | Cellular RF pi network series baseline | Panasonic | ERJ-2GE0R00X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_RF;2=CELL_RF_ANT; Change only from signed VNA evidence | 0 Ohm | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R44 | PCB-MAIN | R44 | Resistor | U13 active-HIGH disable pull-up | Panasonic | ERJ-2RKF4702X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=U13_EN_N; U13 remains High-Z while Q3 is off | 47 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R45 | PCB-MAIN | R45 | Resistor | Dual-SIM selector default-SIM1 pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM_MUX_SEL;2=GND_MODEM; Drives both U13 IN pins | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R46 | PCB-MAIN | R46 | Resistor | Q3 base current limiter | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM_MUX_EN;2=Q3_BASE; Q3 pin 1 endpoint | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R47 | PCB-MAIN | R47 | Resistor | Q3 base-emitter off-state pull | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=Q3_BASE;2=GND_MODEM; Preserves U13 High-Z at reset | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R48 | PCB-MAIN | R48 | Resistor | J6 card-detect pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=SIM1_DET; No card reads LOW through grounded switch | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R49 | PCB-MAIN | R49 | Resistor | J7 card-detect pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=SIM2_DET; No card reads LOW through grounded switch | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R50 | PCB-MAIN | R50 | Resistor | J6 reset series tuning link | Panasonic | ERJ-2GE0R00X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM1_RST_MUX;2=SIM1_RST_CONN; U14 protection is connector-side | 0 Ohm | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R51 | PCB-MAIN | R51 | Resistor | J6 clock series tuning link | Panasonic | ERJ-2GE0R00X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM1_CLK_MUX;2=SIM1_CLK_CONN; U14 protection is connector-side | 0 Ohm | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R52 | PCB-MAIN | R52 | Resistor | J6 data series tuning link | Panasonic | ERJ-2GE0R00X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM1_DATA_MUX;2=SIM1_DATA_CONN; U14 protection is connector-side | 0 Ohm | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R53 | PCB-MAIN | R53 | Resistor | J7 reset series tuning link | Panasonic | ERJ-2GE0R00X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM2_RST_MUX;2=SIM2_RST_CONN; U15 protection is connector-side | 0 Ohm | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R54 | PCB-MAIN | R54 | Resistor | J7 clock series tuning link | Panasonic | ERJ-2GE0R00X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM2_CLK_MUX;2=SIM2_CLK_CONN; U15 protection is connector-side | 0 Ohm | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R55 | PCB-MAIN | R55 | Resistor | J7 data series tuning link | Panasonic | ERJ-2GE0R00X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SIM2_DATA_MUX;2=SIM2_DATA_CONN; U15 protection is connector-side | 0 Ohm | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R56 | PCB-MAIN | R56 | Resistor | U9 TX source-series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=GNSS_RX_U9;2=GNSS_RX_U1; No pull resistor allowed | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R57 | PCB-MAIN | R57 | Resistor | U1 TX source-series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=GNSS_TX_U1;2=GNSS_TX_U9; No pull resistor allowed | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R58 | PCB-MAIN | R58 | Resistor | U9 TIMEPULSE source-series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=GNSS_PPS_U9;2=GNSS_PPS_U1; Do not load LOW at startup | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R59 | PCB-MAIN | R59 | Resistor | Figure 38 voltage-divider upper resistor R5 | Panasonic | ERJ-2GEJ561X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=GNSS_ANT_SWITCHED;2=GNSS_ANT_DIV; Feeds U5 non-inverting input | 560 Ohm 5% 0.1 W | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R60 | PCB-MAIN | R60 | Resistor | Figure 38 voltage-divider lower resistor R6 | Panasonic | ERJ-2GEJ104X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=GNSS_ANT_DIV;2=GND; Sets open-detect threshold with R59 | 100 kOhm 5% 0.1 W | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R61 | PCB-MAIN | R61 | Resistor | Figure 38 P-channel gate pull-up R7 | Panasonic | ERJ-2GEJ104X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=GNSS_ANT_BIAS_RAW;2=GNSS_ANT_GATE; Antenna supply defaults off | 100 kOhm 5% 0.1 W | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R62 | PCB-MAIN | R62 | Resistor | Figure 38 current limiter and shunt R8 | Panasonic | ERJ-8GEYJ100V | 1206 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=GNSS_ANT_SWITCHED;2=GNSS_ANT_SHORT_N; PIO3 senses active-LOW short directly | 10 Ohm 5% 0.25 W | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R63 | PCB-MAIN | R63 | Resistor | U10 TXEN fail-closed pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=LORA_TXEN;2=GND; TXEN and RXEN HIGH together is forbidden | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R64 | PCB-MAIN | R64 | Resistor | U10 RXEN fail-closed pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=LORA_RXEN;2=GND; TXEN and RXEN HIGH together is forbidden | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R65 | PCB-MAIN | R65 | Resistor | U10 DIO1 inactive-state pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=LORA_DIO1;2=GND; MCU input remains deterministic | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R66 | PCB-MAIN | R66 | Resistor | U10 BUSY inactive-state pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=LORA_BUSY;2=GND; MCU input remains deterministic | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R67 | PCB-MAIN | R67 | Resistor | U10 reset pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=LORA_RESET_N; Works with C68 | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R68 | PCB-MAIN | R68 | Resistor | U10 chip-select safe-state pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=LORA_NSS_U10; Radio remains deselected during MCU reset | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R69 | PCB-MAIN | R69 | Resistor | U1 NSS source-series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=LORA_NSS_U1;2=LORA_NSS_U10; Place adjacent to U1 | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R70 | PCB-MAIN | R70 | Resistor | U1 SCK source-series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=LORA_SCK_U1;2=LORA_SCK_U10; Place adjacent to U1 | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R71 | PCB-MAIN | R71 | Resistor | U1 MOSI source-series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=LORA_MOSI_U1;2=LORA_MOSI_U10; Place adjacent to U1 | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R72 | PCB-MAIN | R72 | Resistor | U10 MISO source-series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=LORA_MISO_U10;2=LORA_MISO_U1; Place adjacent to U10 | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R73 | PCB-MAIN | R73 | Resistor | LoRa RF pi network series baseline | Panasonic | ERJ-2GE0R00X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=LORA_RF_MODULE;2=LORA_RF_ANT; Change only from signed VNA evidence | 0 Ohm | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R74 | PCB-MAIN | R74 | Resistor | U11 UART TX source-series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=BLE_RX_U11;2=BLE_RX_U1; Place adjacent to U11 | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R75 | PCB-MAIN | R75 | Resistor | U1 UART TX source-series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=BLE_TX_U1;2=BLE_TX_U11; Place adjacent to U1 | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R76 | PCB-MAIN | R76 | Resistor | U11 application DFU request pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=BLE_DFU_REQ; U1 drives LOW only through open drain | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R77 | PCB-MAIN | R77 | Resistor | U6 input fail-closed pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=BLE_EN;2=GND; Holds nRF reset asserted during U1 reset | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R78 | PCB-MAIN | R78 | Resistor | U6 open-drain output pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=NRF_RESET_N; U11 runs only when U6 releases output | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R79 | PCB-MAIN | R79 | Resistor | U1 SDMMC clock source damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SD_CK_U1;2=SD_CK_CARD; Place adjacent to U1 | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R80 | PCB-MAIN | R80 | Resistor | SDMMC command series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SD_CMD_U1;2=SD_CMD_CARD; Review A validates timing margin | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R81 | PCB-MAIN | R81 | Resistor | SDMMC data zero series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SD_D0_U1;2=SD_D0_CARD; Review A validates timing margin | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R82 | PCB-MAIN | R82 | Resistor | SDMMC data one series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SD_D1_U1;2=SD_D1_CARD; Review A validates timing margin | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R83 | PCB-MAIN | R83 | Resistor | SDMMC data two series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SD_D2_U1;2=SD_D2_CARD; Review A validates timing margin | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R84 | PCB-MAIN | R84 | Resistor | SDMMC data three series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SD_D3_U1;2=SD_D3_CARD; Review A validates timing margin | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R85 | PCB-MAIN | R85 | Resistor | microSD command pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=SD_CMD_CARD; Connector-side of R80 | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R86 | PCB-MAIN | R86 | Resistor | microSD data zero pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=SD_D0_CARD; Connector-side of R81 | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R87 | PCB-MAIN | R87 | Resistor | microSD data one pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=SD_D1_CARD; Connector-side of R82 | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R88 | PCB-MAIN | R88 | Resistor | microSD data two pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=SD_D2_CARD; Connector-side of R83 | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R89 | PCB-MAIN | R89 | Resistor | microSD data three pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=SD_D3_CARD; Connector-side of R84 | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R90 | PCB-MAIN | R90 | Resistor | J12 normally-open card-detect pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=SD_DET; Card insertion closes detect to GND | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R91 | PCB-MAIN | R91 | Resistor | U1 USB D+ source-series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=USB_DP_U1;2=USB_DP_CONN; Place adjacent to U1 PA12 | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R92 | PCB-MAIN | R92 | Resistor | U1 USB D- source-series damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=USB_DM_U1;2=USB_DM_CONN; Place adjacent to U1 PA11 | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R93 | PCB-MAIN | R93 | Resistor | USB-C device-mode CC1 Rd | Panasonic | ERJ-2RKF5101X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=USB_CC1;2=GND; CC1 and CC2 remain independent | 5.1 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R94 | PCB-MAIN | R94 | Resistor | USB-C device-mode CC2 Rd | Panasonic | ERJ-2RKF5101X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=USB_CC2;2=GND; CC1 and CC2 remain independent | 5.1 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R95 | PCB-MAIN | R95 | Resistor | U1 PA9 protected high-impedance VBUS sense series limiter | Panasonic | ERJ-2RKF1001X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=USB_VBUS_CONN;2=USB_VBUS_SENSE; No station power path through J11 | 1 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R96 | PCB-MAIN | R96 | Resistor | U1 PA9 disconnected-state pull-down | Panasonic | ERJ-2RKF1003X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=USB_VBUS_SENSE;2=GND; PA9 remains the dedicated OTG_FS_VBUS endpoint | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R97 | PCB-MAIN | R97 | Resistor | Controlled USB shield DC bleed | Panasonic | ERJ-2RKF1004X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=USB_SHIELD;2=GND; Parallel with C77 | 1 MOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R98 | PCB-MAIN | R98 | Resistor | Optional hard shield bond | Panasonic | ERJ-2GE0R00X | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=USB_SHIELD;2=GND; Populate only from signed EMC evidence | 0 Ohm | ELECTRICAL_COMPONENT | DNP | -55..155 | CONTROLLED_DNP
MAIN-010-R99 | PCB-MAIN | R99 | Resistor | Normally-closed tamper loop pull-up | Panasonic | ERJ-2RKF1002X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=TAMPER_IN_CONN; Open loop is alarm or cable fault | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R100 | PCB-MAIN | R100 | Resistor | Tamper input series protection and filter resistor | Panasonic | ERJ-2RKF1001X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=TAMPER_IN_CONN;2=TAMPER_IN_U1; C78 is U1-side filter capacitor | 1 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R101 | PCB-MAIN | R101 | Resistor | EOL UART DUT-TX source damping | Panasonic | ERJ-2RKF22R0X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=TEST_UART_TX_U1;2=TEST_UART_TX_TP; Fixture input is protected externally | 22 Ohm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R102 | PCB-MAIN | R102 | Resistor | EOL UART DUT-RX current limiter | Panasonic | ERJ-2RKF1001X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=TEST_UART_RX_TP;2=TEST_UART_RX_U1; Fixture drives only at valid VTREF | 1 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-R103 | PCB-MAIN | R103 | Resistor | Intentional connector-to-MCU fault net bridge | Panasonic | ERJ-2GE0R00X | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=FAULT;2=PWR_FAULT; Resolves frozen J_PWR FAULT name and U1 PWR_FAULT name | 0 Ohm | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-L1 | PCB-MAIN | L1 | Inductor | U1 internal SMPS output inductor | Murata | LQH32PN2R2NN0L | 1210 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SMPS_SW;2=VCORE_1V1; Isat above 0.5 A and DCR below 200 mOhm | 2.2 uH 20% | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-L2 | PCB-MAIN | L2 | Inductor | Figure 38 RF bias-T injection L3 | Murata | LQW15AN27NJ00D | 0402 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=GNSS_ANT_SHORT_N;2=GNSS_RF_ANT_BIASED; Verify impedance above 500 Ohm at GNSS L1 and current above 300 mA | 27 nH 5% | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-FB1 | PCB-MAIN | FB1 | Ferrite_Bead | U8 VBAT_BB star branch ferrite | Murata | BLM31KN601SN1L | 1206 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM;2=3V8_MODEM_BB; Review A must verify low DCR current margin and at least 800 Ohm from 700 to 960 MHz | 600 Ohm at 100 MHz | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-FL1 | PCB-MAIN | FL1 | SAW_Filter | External cellular-immunity SAW before U9 RF_IN | Abracon | ABSES5AF-L100KM | 1109-5 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: C=GNSS_RF_DC_BLOCK;A=GNSS_RF_FILTERED;B=GND;D=GND;E=GND; Passband covers 1559.05 to 1605.66 MHz | 1582.4 MHz wideband GNSS SAW | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-U5 | PCB-MAIN | U5 | Operational_Amplifier | Figure 38 active-antenna open-detect comparator | Analog Devices | LT6000IDCB#TRMPBF | DFN-6_DCB_2x3mm | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=GNSS_ANT_DIV;2=GNSS_ANT_SHORT_N;3=GNSS_ANT_BIAS_RAW;4=GNSS_ANT_BIAS_RAW;5=GND;6=GNSS_ANT_DETECT;EP=GND; SHDN pin 3 is held enabled at the local antenna bias supply | Single rail-to-rail low-power op amp | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-U6 | PCB-MAIN | U6 | Open_Drain_Buffer | Fail-closed BLE reset buffer | Texas Instruments | SN74LVC1G07DBVR | SOT-23-5_DBV | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=NC;2=BLE_EN;3=GND;4=NRF_RESET_N;5=3V3_DIGITAL; R77 and R78 define deterministic reset behavior | Single non-inverting open-drain buffer | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-Q4 | PCB-MAIN | Q4 | Dual_MOSFET | Figure 38 T1 P-channel plus T2 N-channel antenna supply switch | Vishay | Si1016X-T1-GE3 | SOT-563_SC-89 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=GND;2=GNSS_ANT_OFF_N;3=GNSS_ANT_SWITCHED;4=GNSS_ANT_BIAS_RAW;5=GNSS_ANT_GATE;6=GNSS_ANT_GATE; Channel1 N source-gate-drain pins 1-2-6 and channel2 P drain-source-gate pins 3-4-5 | Complementary N and P channel 20 V | ELECTRICAL_COMPONENT | FITTED | -55..150 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-U19 | PCB-MAIN | U19 | ESD_Array | J_MIC1 connector-side four-signal ESD shunt | Texas Instruments | TPD4E05U06DQAR | USON-10_DQA | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=PDM_CLK_1V8_FANOUT;2=PDM_DATA1_1V8;3=GND;4=MIC_WAKE1;5=AAD_CFG_1V8_FANOUT;6=NC;7=NC;8=GND;9=NC;10=NC; No series pass-through inside device | 4 channel 0.5 pF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-U20 | PCB-MAIN | U20 | ESD_Array | J_MIC2 connector-side four-signal ESD shunt | Texas Instruments | TPD4E05U06DQAR | USON-10_DQA | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=PDM_CLK_1V8_FANOUT;2=PDM_DATA2_1V8;3=GND;4=MIC_WAKE2;5=AAD_CFG_1V8_FANOUT;6=NC;7=NC;8=GND;9=NC;10=NC; No series pass-through inside device | 4 channel 0.5 pF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-U21 | PCB-MAIN | U21 | ESD_Array | J_MIC3 connector-side four-signal ESD shunt | Texas Instruments | TPD4E05U06DQAR | USON-10_DQA | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=PDM_CLK_1V8_FANOUT;2=PDM_DATA3_1V8;3=GND;4=MIC_WAKE3;5=AAD_CFG_1V8_FANOUT;6=NC;7=NC;8=GND;9=NC;10=NC; No series pass-through inside device | 4 channel 0.5 pF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-U22 | PCB-MAIN | U22 | ESD_Array | J_MIC4 connector-side four-signal ESD shunt | Texas Instruments | TPD4E05U06DQAR | USON-10_DQA | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=PDM_CLK_1V8_FANOUT;2=PDM_DATA4_1V8;3=GND;4=MIC_WAKE4;5=AAD_CFG_1V8_FANOUT;6=NC;7=NC;8=GND;9=NC;10=NC; No series pass-through inside device | 4 channel 0.5 pF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-U23 | PCB-MAIN | U23 | ESD_Array | J12 DAT2 DAT3 CMD and CLK connector-side ESD shunt | Texas Instruments | TPD4E05U06DQAR | USON-10_DQA | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SD_D2_CARD;2=SD_D3_CARD;3=GND;4=SD_CMD_CARD;5=SD_CK_CARD;6=NC;7=NC;8=GND;9=NC;10=NC; Place adjacent to J12 | 4 channel 0.5 pF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-U24 | PCB-MAIN | U24 | ESD_Array | J12 DAT0 DAT1 and detect connector-side ESD shunt | Texas Instruments | TPD4E05U06DQAR | USON-10_DQA | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=SD_D0_CARD;2=SD_D1_CARD;3=GND;4=SD_DET;5=NC;6=NC;7=NC;8=GND;9=NC;10=NC; Fourth channel intentionally NC | 4 channel 0.5 pF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-U25 | PCB-MAIN | U25 | USB_ESD_Array | J11 STM32 USB D+ and D- connector-side ESD shunt | Texas Instruments | TPD2EUSB30DRTR | SOT-9X3_DRT | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=USB_DP_CONN;2=USB_DM_CONN;3=GND; Preserve USB2 differential impedance | 2 channel 0.7 pF USB ESD | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-U26 | PCB-MAIN | U26 | USB_ESD_Array | BG95 recovery USB D+ and D- fixture-side ESD shunt | Texas Instruments | TPD2EUSB30DRTR | SOT-9X3_DRT | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_USB_DP_TP;2=CELL_USB_DM_TP;3=GND_MODEM; Never connect to J11 USB nets | 2 channel 0.7 pF USB ESD | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-U27 | PCB-MAIN | U27 | ESD_Array | BG95 debug fixture four-signal ESD shunt | Texas Instruments | TPD4E05U06DQAR | USON-10_DQA | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_DBG_TXD_TP;2=CELL_DBG_RXD_TP;3=GND_MODEM;4=CELL_DBG_VREF_TP;5=CELL_USB_BOOT_TP;6=NC;7=NC;8=GND_MODEM;9=NC;10=NC; All fixture signals remain 1.8 V domain | 4 channel 0.5 pF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-D1 | PCB-MAIN | D1 | Supply_TVS | U8 VBAT_BB low-leakage TVS shunt | Nexperia | PESD5V0S1UL | SOD882 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM_BB;2=GND_MODEM; Cathode pin 1 is the protected rail | 5 V unidirectional 150 W TVS | ELECTRICAL_COMPONENT | FITTED | -55..150 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-D2 | PCB-MAIN | D2 | Supply_TVS | U8 VBAT_RF low-leakage TVS shunt | Nexperia | PESD5V0S1UL | SOD882 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V8_MODEM_RF;2=GND_MODEM; Cathode pin 1 is the protected rail | 5 V unidirectional 150 W TVS | ELECTRICAL_COMPONENT | FITTED | -55..150 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-D3 | PCB-MAIN | D3 | RF_ESD | J8 connector-side cellular RF ESD shunt | Nexperia | PESD5V0C1BSF | SOD962-2 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_RF_ANT;2=GND_MODEM; No series element and no RF stub | 5 V bidirectional 0.2 pF RF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-D4 | PCB-MAIN | D4 | RF_ESD | J9 connector-side GNSS RF ESD shunt | Texas Instruments | TPD1E05U06DYAR | SOD-523_DYA | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=GNSS_RF_ANT_BIASED;2=GND; Unidirectional part is required because the RF node carries DC antenna bias | 5.5 V unidirectional 0.5 pF RF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-D5 | PCB-MAIN | D5 | RF_ESD | J10 connector-side LoRa RF ESD shunt | Nexperia | PESD5V0C1BSF | SOD962-2 | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=LORA_RF_ANT;2=GND; No series element and no RF stub | 5 V bidirectional 0.2 pF RF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-D6 | PCB-MAIN | D6 | ESD_Diode | J11 VBUS connector-side ESD shunt | Texas Instruments | TPD1E05U06DYAR | SOD-523_DYA | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=USB_VBUS_CONN;2=GND; VBUS is sense-only on PCB-MAIN | 5.5 V 0.5 pF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-D7 | PCB-MAIN | D7 | ESD_Diode | J11 CC1 connector-side ESD shunt | Texas Instruments | TPD1E05U06DYAR | SOD-523_DYA | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=USB_CC1;2=GND; Place ahead of R93 | 5.5 V 0.5 pF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-D8 | PCB-MAIN | D8 | ESD_Diode | J11 CC2 connector-side ESD shunt | Texas Instruments | TPD1E05U06DYAR | SOD-523_DYA | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=USB_CC2;2=GND; Place ahead of R94 | 5.5 V 0.5 pF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-D9 | PCB-MAIN | D9 | ESD_Diode | J13 tamper connector-side ESD shunt | Texas Instruments | TPD1E05U06DYAR | SOD-523_DYA | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=TAMPER_IN_CONN;2=GND; Place adjacent to J13 | 5.5 V 0.5 pF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-D10 | PCB-MAIN | D10 | ESD_Diode | BG95 recovery VBUS fixture-side ESD shunt | Texas Instruments | TPD1E05U06DYAR | SOD-523_DYA | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=CELL_USB_VBUS;2=GND_MODEM; Fixture-controlled VBUS only | 5.5 V 0.5 pF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
MAIN-010-D11 | PCB-MAIN | D11 | ESD_Diode | J12 microSD supply connector-side ESD shunt | Texas Instruments | TPD1E05U06DYAR | SOD-523_DYA | 1 | 4 | 0 | 4 | 10 | 0 | 10 | 20 | 0 | 20 | NONE | COMMON | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-AUTH-010 exact capture authority; physical pins: 1=3V3_DIGITAL;2=GND; Place adjacent to J12 VDD | 5.5 V 0.5 pF ESD | ELECTRICAL_COMPONENT | FITTED | -40..125 | CONTROLLED_PENDING_VERIFICATION
J-USB | PCB-MAIN | J11 | Connector | STM32 USB-C service and system-memory recovery | GCT | USB4105-GF-A-120 | 16 positions | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | MECHANICAL_AUTHORITY_FROZEN_PENDING_PHYSICAL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Mating USB-C_cable; terminal N/A; blockers: service-cover seal; connector insertion and cycle test |  | ELECTRICAL_COMPONENT | FITTED | -40..85 | CONTROLLED_PENDING_VERIFICATION
J-PWR-IN | PCB-PWR | J1 | Connector | Battery protected-bus input | Molex | 430450213 | 2 positions | 1 | 4 | 1 | 5 | 10 | 3 | 13 | 20 | 5 | 25 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_MECHANICS | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Mating Molex_430250200; terminal Molex_430300038; blockers: final orientation and service clearance; pull/thermal test |  | ELECTRICAL_COMPONENT | FITTED | header -40..125; housing -40..105 | CONTROLLED_PENDING_VERIFICATION
J-MIC-MAIN | PCB-MAIN | J_MIC1;J_MIC2;J_MIC3;J_MIC4 | Connector | Four 6-position microphone MAIN board headers | Molex | 5040500691 | Pico-Lock 1.50 mm 6-circuit right-angle SMT | 4 | 16 | 3 | 19 | 40 | 6 | 46 | 80 | 12 | 92 | SCALE_CEIL_FROM_20_BASELINE | COMMON | MECHANICAL_AUTHORITY_FROZEN_PENDING_SI_AAD | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | MAIN-side mates of four PCB-MIC harnesses; same header MPN and pin order as every leaf |  | ELECTRICAL_COMPONENT | FITTED | -40..105 | CONTROLLED_PENDING_VERIFICATION
H-MIC | HARNESS-MIC | H_MIC1:A/B;H_MIC2:A/B;H_MIC3:A/B;H_MIC4:A/B | Housing | Pico-Lock 6-position cable housings, two per MIC harness | Molex | 5040510601 | Pico-Lock 1.50 mm 6-circuit housing | 8 | 32 | 4 | 36 | 80 | 8 | 88 | 160 | 16 | 176 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_HARNESS_LENGTH_PULL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Two housings per cable x four cables; keyed to 5040500691 board headers |  | HARNESS_COMPONENT | FITTED | -40..105 | CONTROLLED_PENDING_VERIFICATION
T-MIC | HARNESS-MIC | H_MIC1..H_MIC4 contacts | Terminal | Pico-Lock crimp terminals, twelve per MIC harness | Molex | 5040520098 | Pico-Lock crimp terminal 28-24 AWG | 48 | 192 | 48 | 240 | 480 | 48 | 528 | 960 | 48 | 1008 | FIXED_LOT_MIN | COMMON | SELECTED_PENDING_CRIMP_PULL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | 6 contacts x 2 ends x 4 harnesses; procurement includes one-station terminal spare set |  | HARNESS_COMPONENT | FITTED | -40..105 | CONTROLLED_PENDING_VERIFICATION
H-PWR-MAIN | HARNESS-PWR-MAIN | H_PWR_MAIN:A/B | Housing | Micro-Fit 3.0 12-position cable housings, two per MAIN-PWR harness | Molex | 43025-1200 | Micro-Fit 3.0 12-circuit housing | 2 | 8 | 1 | 9 | 20 | 2 | 22 | 40 | 4 | 44 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_MECHANICS_I2C_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | One housing at PCB-MAIN and one at PCB-PWR |  | HARNESS_COMPONENT | FITTED | -40..105 | CONTROLLED_PENDING_VERIFICATION
T-PWR-MAIN-PWR | HARNESS-PWR-MAIN | H_PWR_MAIN power contacts | Terminal | Micro-Fit crimp terminals for six power/ground conductors at both ends | Molex | 43030-0038 | Micro-Fit female crimp terminal 18 AWG class | 12 | 48 | 3 | 51 | 120 | 6 | 126 | 240 | 12 | 252 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_CURRENT_PULL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Pins 1-6 x two cable ends; final wire construction must match approved terminal range |  | HARNESS_COMPONENT | FITTED | -40..105 | CONTROLLED_PENDING_VERIFICATION
T-PWR-MAIN-CTL | HARNESS-PWR-MAIN | H_PWR_MAIN control contacts | Terminal | Micro-Fit crimp terminals for six control/I2C conductors at both ends | Molex | 43030-0001 | Micro-Fit female crimp terminal 20-24 AWG class | 12 | 48 | 3 | 51 | 120 | 6 | 126 | 240 | 12 | 252 | SCALE_CEIL_FROM_20_BASELINE | COMMON | SELECTED_PENDING_I2C_PULL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Pins 7-12 x two cable ends; includes I2C2 SCL/SDA on pins 11/12 |  | HARNESS_COMPONENT | FITTED | -40..105 | CONTROLLED_PENDING_VERIFICATION
R-MIC | PCB-MIC | PCB-MIC:R1 x4 | Passive | 0 ohm PDM DATA source-termination/tuning link | Panasonic Industry | ERJ-2GE0R00X | 0402 1005 metric | 4 | 16 | 40 | 56 | 40 | 40 | 80 | 80 | 40 | 120 | FIXED_LOT_MIN | COMMON | SELECTED_POPULATED_BASELINE_PENDING_SI | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | One populated R1 per PCB-MIC leaf; any DNP/value change requires SI review and BOM revision | 0 ohm | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
PWR-C-100N | PCB-PWR | C1;C2;C4;C6 | Passive | PCB-PWR 100 nF 25 V X7R | TDK | CGA2B3X7R1E104K050BB | 0402 | 4 | 16 | 40 | 56 | 40 | 40 | 80 | 80 | 40 | 120 | FIXED_LOT_MIN | COMMON | LOCKED_CANDIDATE_PENDING_DERATING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Capacitor_SMD:C_0402_1005Metric; blockers: DC bias and assembly review; bootstrap loop placement and assembly review | 100 nF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
PWR-C-LDO | PCB-PWR | C7;C8 | Passive | PCB-PWR 2.2 uF 10 V X7R | TDK | CGA3E1X7R1A225K080AC | 0603 | 2 | 8 | 40 | 48 | 20 | 40 | 60 | 40 | 40 | 80 | FIXED_LOT_MIN | COMMON | LOCKED_CANDIDATE_PENDING_DERATING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Capacitor_SMD:C_0603_1608Metric; blockers: effective capacitance and microphone noise test; effective capacitance and noise test | 2.2 uF 10 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
PWR-C-CIN-HF | PCB-PWR | C9;C20;C21 | Passive | PCB-PWR 100 nF 50 V X7R | TDK | CGA3E2X7R1H104K080AA | 0603 | 3 | 12 | 40 | 52 | 30 | 40 | 70 | 60 | 40 | 100 | FIXED_LOT_MIN | COMMON | CONTROLLED_CANDIDATE_PENDING_MULTIPLE_REVIEWS | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Capacitor_SMD:C_0603_1608Metric; blockers: DC bias high-frequency loop placement and EMI review; transient profile and TVS coordination | 100 nF 50 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
PWR-C-INPUT | PCB-PWR | C10;C11;C12 | Passive | PCB-PWR 4.7 uF 50 V X7R | TDK | CGA6P3X7R1H475K250AB | 1210 | 3 | 12 | 40 | 52 | 30 | 40 | 70 | 60 | 40 | 100 | FIXED_LOT_MIN | COMMON | CONTROLLED_CANDIDATE_PENDING_MULTIPLE_REVIEWS | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Capacitor_SMD:C_1210_3225Metric; blockers: DC bias load-step and hot-loop review; transient profile DC bias and assembly review | 4.7 uF 50 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
PWR-C-BULK | PCB-PWR | C13 | Passive | PCB-PWR 100 uF 35 V hybrid | Panasonic Industry | EEH-ZK1V101XP | SMD can 6.3x7.7 mm | 1 | 4 | 40 | 44 | 10 | 40 | 50 | 20 | 40 | 60 | FIXED_LOT_MIN | COMMON | LOCKED_CANDIDATE_PACKAGE_REVIEW_PENDING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Capacitor_SMD:CP_Elec_6.3x7.7; blockers: manufacturer land-pattern comparison transient ripple and thermal test | 100 uF 35 V hybrid | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
PWR-COUT-3V8 | PCB-PWR | C3;C14;C15;C16 | Passive | PCB-PWR 22 uF 25 V X7R | TDK | CGA6P3X7R1E226M250AB | 1210 | 4 | 16 | 40 | 56 | 40 | 40 | 80 | 80 | 40 | 120 | FIXED_LOT_MIN | COMMON | LOCKED_CANDIDATE_PENDING_DERATING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Capacitor_SMD:C_1210_3225Metric; blockers: DC bias load-step ripple and assembly review | 22 uF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
PWR-COUT-3V3 | PCB-PWR | C5;C17;C18;C19 | Passive | PCB-PWR 22 uF 25 V X7R | TDK | CGA6P3X7R1E226M250AB | 1210 | 4 | 16 | 40 | 56 | 40 | 40 | 80 | 80 | 40 | 120 | FIXED_LOT_MIN | COMMON | LOCKED_CANDIDATE_PENDING_DERATING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Capacitor_SMD:C_1210_3225Metric; blockers: DC bias load-step ripple and assembly review | 22 uF 25 V X7R | ELECTRICAL_COMPONENT | FITTED | -55..125 | CONTROLLED_PENDING_VERIFICATION
PWR-R-100K-01 | PCB-PWR | R1 | Passive | PCB-PWR 100 kOhm 0.1% | Panasonic Industry | ERA-2AEB104X | 0402 | 1 | 4 | 40 | 44 | 10 | 40 | 50 | 20 | 40 | 60 | FIXED_LOT_MIN | COMMON | LOCKED_CANDIDATE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Resistor_SMD:R_0402_1005Metric; blockers: feedback tolerance and load-step verification | 100 kOhm 0.1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
PWR-R-35K7 | PCB-PWR | R2 | Passive | PCB-PWR 35.7 kOhm 0.1% | Panasonic Industry | ERA-2AEB3572X | 0402 | 1 | 4 | 40 | 44 | 10 | 40 | 50 | 20 | 40 | 60 | FIXED_LOT_MIN | COMMON | LOCKED_CANDIDATE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Resistor_SMD:R_0402_1005Metric; blockers: feedback tolerance and load-step verification | 35.7 kOhm 0.1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
PWR-R-86K6 | PCB-PWR | R3;R7 | Passive | PCB-PWR 86.6 kOhm 0.1% | Panasonic Industry | ERA-2AEB8662X | 0402 | 2 | 8 | 40 | 48 | 20 | 40 | 60 | 40 | 40 | 80 | FIXED_LOT_MIN | COMMON | LOCKED_CANDIDATE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Resistor_SMD:R_0402_1005Metric; blockers: switching-frequency measurement | 86.6 kOhm 0.1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
PWR-R-0R | PCB-PWR | R4;R8 | Passive | PCB-PWR 0 ohm | Panasonic Industry | ERJ-2GE0R00X | 0402 | 2 | 8 | 40 | 48 | 20 | 40 | 60 | 40 | 40 | 80 | FIXED_LOT_MIN | COMMON | LOCKED_FITTED | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Resistor_SMD:R_0402_1005Metric; blockers: mode and sleep-current test | 0 ohm | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
PWR-R-0R-DNP | PCB-PWR | R5;R9 | Passive | PCB-PWR 0 ohm | Panasonic Industry | ERJ-2GE0R00X | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | LOCKED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Resistor_SMD:R_0402_1005Metric; blockers: assembly population control | 0 ohm | ELECTRICAL_COMPONENT | DNP | -55..155 | CONTROLLED_DNP
PWR-R-100K | PCB-PWR | R6;R11 | Passive | PCB-PWR 100 kOhm 1% | Panasonic Industry | ERJ-2RKF1003X | 0402 | 2 | 8 | 40 | 48 | 20 | 40 | 60 | 40 | 40 | 80 | FIXED_LOT_MIN | COMMON | LOCKED_FITTED | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Resistor_SMD:R_0402_1005Metric; blockers: startup state verification | 100 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
PWR-R-10K | PCB-PWR | R10;R12 | Passive | PCB-PWR 10 kOhm 1% | Panasonic Industry | ERJ-2RKF1002X | 0402 | 2 | 8 | 40 | 48 | 20 | 40 | 60 | 40 | 40 | 80 | FIXED_LOT_MIN | COMMON | LOCKED_FITTED | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Resistor_SMD:R_0402_1005Metric; blockers: logic threshold and fault verification; logic threshold and startup verification | 10 kOhm 1% | ELECTRICAL_COMPONENT | FITTED | -55..155 | CONTROLLED_PENDING_VERIFICATION
PWR-R-4K7-DNP | PCB-PWR | R13;R14 | Passive | PCB-PWR 4.7 kOhm 1% | Panasonic Industry | ERJ-2RKF4701X | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | LOCKED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Resistor_SMD:R_0402_1005Metric; blockers: I2C harness capacitance and population control | 4.7 kOhm 1% | ELECTRICAL_COMPONENT | DNP | -55..155 | CONTROLLED_DNP
PWR-R-10K-DNP | PCB-PWR | R15 | Passive | PCB-PWR 10 kOhm 1% | Panasonic Industry | ERJ-2RKF1002X | 0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NONE | COMMON | LOCKED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint Resistor_SMD:R_0402_1005Metric; blockers: diagnostic population control | 10 kOhm 1% | ELECTRICAL_COMPONENT | DNP | -55..155 | CONTROLLED_DNP
PWR-NET-TIE | PCB-PWR | NT1;NT2;NT3 | PCB feature | PCB-PWR 2-pad copper net tie | PCB fabrication | NET_TIE_COPPER_REV_A | NetTie-2 SMD pad 0.5 mm | 3 | 12 | 0 | 12 | 30 | 0 | 30 | 60 | 0 | 60 | NONE | COMMON | LOCKED_LAYOUT_PENDING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A source PCB_PWR_PASSIVE_AUTHORITY_REV_A.csv; footprint NetTie:NetTie-2_SMD_Pad0.5mm; blockers: layout current-return review | 2-pad copper net tie | PCB_FEATURE | PCB_FEATURE | N/A | CONTROLLED_PENDING_VERIFICATION
PWR-L | PCB-PWR | L1;L2 | Passive | PCB-PWR 4.7 uH +/-20% | Coilcraft | XAL7030-472MEC | XAL7030 | 2 | 8 | 10 | 18 | 20 | 10 | 30 | 40 | 10 | 50 | FIXED_LOT_MIN | COMMON | SELECTED_PENDING_LAYOUT_THERMAL_EMI | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | Rev.A freeze source POWER_COMPONENT_FREEZE_REV_A.csv; exact land pattern controlled; blockers: placement and hot-loop review; 0.48 W max-DCR loss at 4 A; +70 C thermal; load-step; EMI | 4.7 uH +/-20% | ELECTRICAL_COMPONENT | FITTED | -40..125 ambient / +165 component | CONTROLLED_PENDING_VERIFICATION

## RFQ
RFQ_ID | BOM_Item_IDs | Category | Manufacturer | MPN_or_spec | Required_qty_4 | Required_qty_10 | Required_qty_20 | Preferred_channel | Quote_date | Supplier | URL | MOQ | Lead_time_days | Stock_claim | Traceability_required | Sample_required | Status | Blocking_check
RFQ-001 | U1 | MCU | STMicroelectronics | STM32U585VIT6Q | 5 | 13 | 25 | Authorized distributor | [6 empty] | Yes | No | RFQ_REQUIRED | Quote exact manufacturer MPN and LQFP100 package with no substitution; verify device identity during PCBA programming and EOL
RFQ-002 | MK1 | Microphone | TDK InvenSense | MMICT5838-00-012 | 20 | 48 | 96 | Authorized distributor | [6 empty] | Yes | No | RFQ_REQUIRED | Quote exact manufacturer MPN with no substitution; perform port inspection acoustic sensitivity noise and phase matching during assembly EOL and EVT
RFQ-003 | U8 | Cellular | Quectel | BG95-M3 marking and firmware identity | 5 | 13 | 25 | Quectel authorized channel | [6 empty] | Yes | No | RFQ_REQUIRED | Quote exact BG95-M3 with no substitution; verify article firmware and IMEI during PCBA EOL; operator attach burst and TLS remain assembled-station EVT
RFQ-004 | U9 | GNSS | u-blox | MAX-M10S-00B | 5 | 13 | 25 | Authorized distributor | [6 empty] | Yes | No | RFQ_REQUIRED | Quote exact manufacturer MPN with no substitution; verify fix sensitivity PPS and antenna interface during PCBA EOL and assembled-station EVT
RFQ-005 | U10 | LoRa | Ebyte | E22-900M22S | 6 | 13 | 26 | Ebyte official or authorized | [6 empty] | Yes | No | RFQ_REQUIRED | Quote must state exact 20x14 22-pad castellated-ANT option with no module IPEX fitted and no substitution; verify sleep current conducted RF and RU868 windows 864-865 and 868.7-869.2 MHz during EOL and EVT
RFQ-006 | U11 | BLE | Raytac | MDBT50Q-P1MV2 | 5 | 13 | 25 | Raytac authorized or traceable distributor | [6 empty] | Yes | No | RFQ_REQUIRED | Quote exact module suffix with no substitution; verify integrated-antenna keepout pairing OTA current and RF range during PCBA EOL and EVT
RFQ-007 | U2 | QSPI NOR | Winbond | W25Q512JVFIQ | 5 | 13 | 25 | Authorized or traceable tier-1 | [6 empty] | Yes | No | RFQ_REQUIRED | Quote exact manufacturer MPN with no substitution; verify JEDEC identity read write erase and soak during PCBA EOL and EVT
RFQ-008 | BAT1 | Battery | Epower Tech Co. Ltd | DIO-BAT-LFP-12V50-H-REV-A heated 12.8 V 50 Ah 640 Wh LiFePO4 M8 | 5 | 11 | 21 | Epower Tech direct supplier quote |  |  | hardware/reviews/EVT_BATTERY_50AH_HEATED_ACCEPTANCE_REV_A.md |  |  |  | Yes | No | RFQ_REQUIRED | Quote exact internal article DIO-BAT-LFP-12V50-H-REV-A with heating option and no substitution; PO must bind 198 x 166 x 170 mm body M8 studs 12-14 mm high about 143 mm pitch charge 0..55 C discharge -20..60 C heater power threshold hysteresis and source plus applicable UN38.3 SDS and route documents; perform dimensions polarity voltage heater capacity DCIR BMS and cold-system validation during assembly and EVT
RFQ-009 | PV1 | Solar | SLD Tech / Solarland | SLP080S-12M 80 W 12 V monocrystalline | 5 | 11 | 21 | SLD Tech or authorized distributor |  |  | https://sldtechinc.com/80w-12v-monocrystalline-solar-panel-s/ |  |  |  | Yes | No | RFQ_REQUIRED | Quote exact SLP080S-12M with no substitution and confirm quantity price delivery and packaging; perform Voc Isc Vmp Imp Pmax IV cold-Voc insulation wet-leakage mounting cable and transport validation during assembly and EVT
RFQ-010 | MPPT1 | MPPT | Victron Energy | SmartSolar MPPT 75/10 article SCC075010060R | 5 | 11 | 21 | Victron authorized distributor |  |  | https://www.victronenergy.com/media/pg/Manual_SmartSolar_MPPT_75-10_up_to_100-20/en/technical-specifications.html |  |  |  | Yes | No | RFQ_REQUIRED | Quote exact SCC075010060R with no substitution and confirm quantity price and delivery; bind firmware and exported heated 12.8 V LiFePO4 profile then verify charge inhibit until the battery reaches the approved threshold with RFQ-026 reverse current quiescent transient terminal enclosure and thermal behavior during assembly EOL and EVT
RFQ-011 | ASM-MAIN | PCBA main | Customer-selected standard PCBA service | DIO-PCBA-MAIN-EVT-A; JLC06161H-3313; SAC305 Type-4; 100 um stencil | 6 | 12 | 22 | Customer order portal with AOI and X-ray | [6 empty] | Yes | No | RFQ_REQUIRED | PRIMARY PROCUREMENT TRACK; upload only after routing DRC CAM and Review B; checkout/file-parser DFM must have no unresolved errors; hold remaining 20 boards until two first articles pass SPI AOI X-ray polarity smoke and interface checks
RFQ-012 | ASM-MIC | PCBA mic | Customer-selected standard PCBA service | DIO-PCBA-MIC-EVT-A; 2-layer FR-4 1.0 mm ENIG; controlled acoustic keepout | 18 | 42 | 82 | Customer order portal with AOI | [6 empty] | Yes | No | RFQ_REQUIRED | PRIMARY PROCUREMENT TRACK; upload only after final CAM and Review B; checkout DFM and first-panel 0.8 mm acoustic-bore inspection are stop gates; inspect every acoustic port after supported depaneling
RFQ-013 | ASM-PWR | PCBA power | Customer-selected standard PCBA service | DIO-PCBA-PWR-EVT-A; JLC04161H-3313A; 4-layer 90 x 60 x 1.60 mm; four M3 NPTH; outer 2 oz inner 1 oz; 70/35 um | 6 | 12 | 22 | Customer order portal with AOI and X-ray | [6 empty] | Yes | No | RFQ_REQUIRED | PRIMARY PROCUREMENT TRACK; upload only after routing DRC CAM and Review B; checkout/file-parser DFM must match the EVT baseline; hold remaining 20 boards until two first articles pass inspection current-limited smoke rail-drop and interface checks; complete plus70C thermal and fault validation on EVT
RFQ-014 | HARNESS | Harness | Project engineering under customer EVT authority | DIO-HARNESS-SET-EVT-A; MIC 275 +/-5 mm; MAIN-PWR 440 +/-5 mm; BAT-PWR 330 +/-5 mm; 10 percent service margin | 5 | 11 | 22 | Customer-selected harness assembler or controlled in-house build | [6 empty] | Yes | No | RFQ_REQUIRED | Use TE 55A0111-24 with Molex 5040520098 for MIC; TE 55A0111-18 with Molex 430300038 for power and battery; Alpha 3051 with Molex 430300001 for logic; TE 8-34114-1 M8 ring; qualify first-off crimp height and destructive pull then test 100 percent continuity polarity cross-short and resistance; verify installed route strain PDM AAD I2C thermal and cold behavior on EVT
RFQ-015 | U13 | SIM switch | Texas Instruments | TS3A27518EPWR | 5 | 13 | 25 | Authorized distributor | [6 empty] | Yes | No | RFQ_REQUIRED | Quote exact manufacturer MPN with no substitution; verify supply leakage Ron capacitance ESD and BG95 signal integrity during PCBA EOL and EVT
RFQ-016 | J-SIM1¦J-SIM2 | SIM connector | TE Connectivity | 2336582-1 | 10 | 26 | 50 | Authorized or traceable TE distributor | [6 empty] | Yes | No | RFQ_REQUIRED | Quote exact manufacturer MPN and drawing revision with no substitution; verify coplanarity card detect mating cycles and service access during assembly and EVT
RFQ-017 | HSG-VC | Vacuum-cast housing | Dioneya controlled design | DIO-HSG-VC-REV-A outdoor polyurethane housing set build-to-print scope with inserts seals and service cover | 4 | 10 | 20 | Customer-selected qualified vacuum-casting supplier | [6 empty] | Yes | No | RFQ_REQUIRED | Internal article identity is controlled but no caster is selected; quote only the released selected EVT lot source package and apply first-article shrink cure material UV finish leak fit acoustic and RF checks within that lot; no separate pre-order qualification unit
RFQ-018 | HSG-3D | 3D-printed fallback housing | TBD | Outdoor printed housing set with inserts seals and service cover | 0 | 0 | 0 | Qualified print supplier or controlled FlashForge 5M Pro process | [6 empty] | Yes | No | CONDITIONAL_CAPACITY_QUOTE | Quote capacity for 4 10 and 20; procure only after fallback activation and validate the activated selected lot through first-article and EVT controls
RFQ-019 | HSG-IM | Injection-molding DFM | TBD | Independent CAD DFM and tool quotation package | 0 | 0 | 0 | Qualified mold manufacturer | [6 empty] | Yes | No | SOURCE_DATA_AND_DFM_ONLY | Review tool concept material draft wall ribs bosses parting ejector shrink and expected tooling lead time; no tooling authorization
RFQ-020 | ANT-CELL | Cellular antenna | Taoglas | G30.B.108111 IP67 1 m cable SMA(M) | 5 | 11 | 22 | Taoglas or established distributor |  |  | https://www.taoglas.com/product/olympian-g30-2g3g4g-lte-antenna/ |  |  |  | Yes | No | RFQ_REQUIRED | Quote exact G30.B.108111 with no substitution and state ordered cable construction because the manufacturer page is inconsistent; confirm quantity price and delivery; verify installed SMA-bulkhead VSWR loss attach seal and coexistence during assembly EOL and EVT
RFQ-021 | ANT-GNSS | Active GNSS antenna | Taoglas | AA.166.A.301111 IP67 3 m RG174 SMA(M) | 5 | 11 | 22 | Taoglas or established distributor |  |  | https://www.taoglas.com/product/aa-166-a-301111-ulysses-miniature-magnetic-mount-beidougpsglonassgalileo-antenna-with-3000mm-rg-174-smam/ |  |  |  | Yes | No | RFQ_REQUIRED | Quote exact AA.166.A.301111 with no substitution and confirm quantity price and delivery; verify current at 3.3 V is at most 50 mA plus mounting sensitivity PPS seal and coexistence during assembly EOL and EVT
RFQ-022 | ANT-LORA | RU868 antenna | Taoglas | TI.89.B.2111W IP67 860-930 MHz SMA(M) | 5 | 11 | 22 | Taoglas or established distributor |  |  | https://www.taoglas.com/product/ti-89-b-ism-lora-860-930-mhz-white-terminal-mount-antenna-2dbi-smam-fixed-straight-waterproof-enclosure/ |  |  |  | Yes | No | RFQ_REQUIRED | Quote exact TI.89.B.2111W with no substitution and confirm quantity price and delivery; verify installed SMA-bulkhead VSWR conducted power sensitivity seal coexistence and RU868 radiated compliance during assembly EOL and EVT
RFQ-023 | PCB-MAIN | Bare PCB main | JLCPCB or equivalent meeting EVT baseline | DIO-PCB-MAIN-EVT-A_JLC06161H-3313; 6-layer 1.6 mm order; ENIG; 1/0.5 oz; impedance +/-10 percent | 6 | 12 | 22 | Customer order portal | [6 empty] | Yes | No | RFQ_REQUIRED | ALTERNATIVE QUOTATION TRACK ONLY; do not issue together with ASM-MAIN; upload only released Gerber drill IPC-356 and fabrication drawing after routing DRC CAM RF/SI and Review B; select JLC06161H-3313 controlled impedance and standard coupon/TDR when offered; stop on any checkout DFM or parser mismatch
RFQ-024 | PCB-MIC | Bare PCB microphone | JLCPCB or equivalent meeting EVT baseline | DIO-PCB-MIC-EVT-A; 2-layer FR-4 24 x 22 x 1.0 mm ENIG 1 oz | 18 | 42 | 82 | Customer order portal | [6 empty] | Yes | No | RFQ_REQUIRED | ALTERNATIVE QUOTATION TRACK ONLY; do not issue together with ASM-MIC; upload only released Gerber drill IPC-356 and fabrication drawing after CAM and Review B; standard routed-tab panel away from MK1 H1 H2; stop on DFM or first-panel acoustic-bore defect
RFQ-025 | PCB-PWR | Bare PCB power | JLCPCB or equivalent meeting EVT baseline | DIO-PCB-PWR-EVT-A_JLC04161H-3313A; 4-layer 90 x 60 x 1.6 mm; four circular M3 NPTH; outer 2 oz inner 1 oz; 70/35 um; ENIG | 6 | 12 | 22 | Customer order portal | [6 empty] | Yes | No | RFQ_REQUIRED | ALTERNATIVE QUOTATION TRACK ONLY; do not issue together with ASM-PWR; upload only released Gerber drill IPC-356 and fabrication drawing after routing DRC CAM and Review B; select JLC04161H-3313A and stop on checkout DFM mismatch; retain net test first-article power checks and series mechanical revalidation
RFQ-026 | MPPT-TEMP | Battery temperature sensor | Victron Energy | Smart Battery Sense long-range up to 10 m radio article SBS050150200 | 5 | 11 | 21 | Victron authorized distributor |  |  | https://www.victronenergy.com/media/pg/Smart_Battery_Sense/en/technical-specifications.html |  |  |  | Yes | No | RFQ_REQUIRED | Quote exact SBS050150200 with no substitution and confirm quantity price and delivery; verify 0.45 m lead M10 eyelet retention on DIO-BAT-LFP-12V50-H-REV-A M8 terminals voltage and temperature accuracy VE.Smart pairing warm-up cutoff reconnect fallback below -10 C and cold-soak behavior during assembly EOL and EVT
RFQ-027 | RF-PIGTAIL | RF pigtail | Taoglas | CAB.0243 150 mm 1.13 mm MHF I/U.FL-compatible R/A to waterproof SMA(F) bulkhead | 14 | 33 | 66 | Taoglas or established distributor |  |  | https://www.taoglas.com/datasheets/CAB.0243.pdf |  |  |  | Yes | No | RFQ_REQUIRED | Quote exact CAB.0243 and SPE-24-8-147-A with no substitution and confirm quantity price and delivery; verify normal SMA polarity 150 mm length 6.8 mm minimum bend mate with Hirose U.FL-R-SMT-1(60) routing insertion loss VSWR bulkhead seal torque and temperature during assembly EOL and EVT

## Cost estimate
EVT-PRE-20 cost tracks
Customer-comparable values use the presented 2026-09-09 China engineering estimate. Internal values use the current exact-MPN public-price exposure below; the two bases are not interchangeable.
Customer-comparable engineering estimate | [8 empty] | Assumptions and controls
Lot | ALT: Bare PCB kit, direct RUB | ALT: Bare PCB kit +10% | PRIMARY: Full PCBA, direct RUB | PRIMARY: Full PCBA +10% | PRIMARY PCBA / station | Internal bare exposure | Internal full exposure |  | USD/RUB | 85.0757 |  | Presented direct BOM, lot 20 | 561805.8925 |  | Cable/connector spare cost, lot 20 | 6601.0236
4 | 103959.1024 | 114355.0126 | 120293.6368 | 132323.0004 | 30073.4092 | 920420 | 970820 |  | Other BOM, USD/station | 255.18 |  | Maximum at +15% | 646076.7764 |  | Board reserve | 2 each MAIN / PWR / MIC
10 | 255441.4908 | 280985.6398 | 290152.3764 | 319167.614 | 29015.2376 | 2093540 | 2198540 |  | Planning reserve | 10% |  | Full-PCBA direct delta | 2.19% |  | Alternative track | components + bare PCB; assembly excluded
20 | 508768.8504 | 559645.7354 | 574106.988 | 631517.6868 | 28705.3494 | 4032880 | 4228880 |  | Spare boards / design | 2 |  | Source | Dioneya_EVT_PRE_20_BOM_priced_v0_2.xlsx |  | Primary track | full PCBA with assembly/test service
PRIMARY procurement route: full PCBA. Bare PCB is an alternative quotation track only. Cable and connector reserves are retained; both tracks use exactly two spare boards of every design and are never added together.
Procurement_ID | Manufacturer | MPN | Category | Unit_price_RUB_estimate | Price_basis | Displayed_source_price | Source_currency | Source_URL | Checked_on | Estimate_confidence | Procure_qty_4 | Line_cost_4_RUB_estimate | Procure_qty_10 | Line_cost_10_RUB_estimate | Procure_qty_20 | Line_cost_20_RUB_estimate | Estimate_note
PR-001 | Dioneya controlled design | DIO-ASM-MAIN-REV-A | PCBA | 3500 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 6 | 21000 | 12 | 42000 | 22 | 77000 | Primary full-PCBA procurement track; assembly and EOL service estimate excludes components and remains subject to the CM quotation.
PR-002 | Dioneya controlled design | DIO-ASM-MIC-REV-A | PCBA | 700 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 18 | 12600 | 42 | 29400 | 82 | 57400 | Primary full-PCBA procurement track; assembly and EOL service estimate excludes components and remains subject to the CM quotation.
PR-003 | Dioneya controlled design | DIO-ASM-PWR-REV-A | PCBA | 2800 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 6 | 16800 | 12 | 33600 | 22 | 61600 | Primary full-PCBA procurement track; assembly and EOL service estimate excludes components and remains subject to the CM quotation.
PR-004 | Dioneya controlled design | DIO-HARNESS-SET-REV-A | Harness | 4500 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 22500 | 11 | 49500 | 22 | 99000 | Rounded engineering estimate pending supplier quotation.
PR-005 | TBD | TBD | Housing | 12000 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 0 | 0 | 0 | 0 | 0 | 0 | Rounded engineering estimate pending supplier quotation.
PR-006 | TBD | TBD | Housing | 250000 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 0 | 0 | 0 | 0 | 0 | 0 | Rounded engineering estimate pending supplier quotation.
PR-007 | Dioneya controlled design | DIO-HSG-VC-REV-A | Housing | 18000 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 72000 | 10 | 180000 | 20 | 360000 | Rounded engineering estimate pending supplier quotation.
PR-008 | Dioneya controlled design | DIO-PCB-MAIN-REV-A | Bare PCB | 2200 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 6 | 13200 | 12 | 26400 | 22 | 48400 | Alternative bare-PCB quotation track only; do not add to the selected full-PCBA purchase set.
PR-009 | Dioneya controlled design | DIO-PCB-MIC-REV-A | Bare PCB | 350 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 18 | 6300 | 42 | 14700 | 82 | 28700 | Alternative bare-PCB quotation track only; do not add to the selected full-PCBA purchase set.
PR-010 | Dioneya controlled design | DIO-PCB-PWR-REV-A | Bare PCB | 1600 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 6 | 9600 | 12 | 19200 | 22 | 35200 | Alternative bare-PCB quotation track only; do not add to the selected full-PCBA purchase set.
PR-011 | Littelfuse | 0451008.MRL | Protection | 250 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 6 | 1500 | 15 | 3750 | 30 | 7500 | Rounded engineering estimate pending supplier quotation.
PR-012 | TE Connectivity | 2336582-1 | SIM | 550 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 10 | 5500 | 26 | 14300 | 50 | 27500 | Rounded engineering estimate pending supplier quotation.
PR-013 | Molex | 43025-1200 | Housing | 500 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 9 | 4500 | 22 | 11000 | 44 | 22000 | Rounded engineering estimate pending supplier quotation.
PR-014 | Molex | 43030-0001 | Terminal | 45 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 51 | 2295 | 126 | 5670 | 252 | 11340 | Rounded engineering estimate pending supplier quotation.
PR-015 | Molex | 43030-0038 | Terminal | 55 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 51 | 2805 | 126 | 6930 | 252 | 13860 | Rounded engineering estimate pending supplier quotation.
PR-016 | Molex | 430450213 | Connector | 350 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 1750 | 13 | 4550 | 25 | 8750 | Rounded engineering estimate pending supplier quotation.
PR-017 | Molex | 430451202 | Connector | 900 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 10 | 9000 | 26 | 23400 | 50 | 45000 | Rounded engineering estimate pending supplier quotation.
PR-018 | Molex | 5040500291 | Connector | 250 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 1250 | 13 | 3250 | 25 | 6250 | Rounded engineering estimate pending supplier quotation.
PR-019 | Molex | 5040500691 | Connector | 480 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 38 | 18240 | 92 | 44160 | 184 | 88320 | Rounded engineering estimate pending supplier quotation.
PR-020 | Molex | 5040510601 | Housing | 180 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 36 | 6480 | 88 | 15840 | 176 | 31680 | Rounded engineering estimate pending supplier quotation.
PR-021 | Molex | 5040520098 | Terminal | 35 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 240 | 8400 | 528 | 18480 | 1008 | 35280 | Rounded engineering estimate pending supplier quotation.
PR-022 | Taoglas | AA.166.A.301111 | Antenna | 3300 | PUBLIC_AUTHORIZED_CHANNEL_PRICE | EUR 23.80 at qty 10 | EUR | https://www.mouser.lu/en/ProductDetail/Taoglas/AA.166.A.301111?qs=MLItCLRbWsy9cGP7TTjqEA%3D%3D | 2026-09-18 | MEDIUM | 5 | 16500 | 11 | 36300 | 22 | 72600 | Published price converted to a rounded landed-RUB planning value; final cart/quote controls.
PR-023 | Abracon | ABSES5AF-L100KM | SAW_Filter | 550 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 2200 | 10 | 5500 | 20 | 11000 | Rounded engineering estimate pending supplier quotation.
PR-024 | Quectel | BG95-M3 | Cellular | 3500 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 17500 | 13 | 45500 | 25 | 87500 | Rounded engineering estimate pending supplier quotation.
PR-025 | Murata | BLM31KN601SN1L | Ferrite_Bead | 45 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 180 | 10 | 450 | 20 | 900 | Rounded engineering estimate pending supplier quotation.
PR-026 | Taoglas | CAB.0243 | RF cable | 650 | PUBLIC_AUTHORIZED_CHANNEL_PRICE | $5.2068 at qty 50 | USD | https://www.digikey.com/en/products/detail/taoglas-limited/CAB-0243/24770240 | 2026-09-18 | MEDIUM | 14 | 9100 | 33 | 21450 | 66 | 42900 | Published price converted to a rounded landed-RUB planning value; final cart/quote controls.
PR-027 | TDK | CGA2B3X7R1E104K050BB | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 56 | 1400 | 80 | 2000 | 120 | 3000 | Rounded engineering estimate pending supplier quotation.
PR-028 | TDK | CGA2B3X7R1E104K050BB | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 56 | 1400 | 80 | 2000 | 120 | 3000 | Rounded engineering estimate pending supplier quotation.
PR-029 | TDK | CGA3E1X7R1A225K080AC | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 48 | 1200 | 60 | 1500 | 80 | 2000 | Rounded engineering estimate pending supplier quotation.
PR-030 | TDK | CGA3E2X7R1H104K080AA | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 52 | 1300 | 70 | 1750 | 100 | 2500 | Rounded engineering estimate pending supplier quotation.
PR-031 | TDK | CGA6P3X7R1E226M250AB | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 112 | 2800 | 160 | 4000 | 240 | 6000 | Rounded engineering estimate pending supplier quotation.
PR-032 | TDK | CGA6P3X7R1H475K250AB | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 52 | 1300 | 70 | 1750 | 100 | 2500 | Rounded engineering estimate pending supplier quotation.
PR-033 | Texas Instruments | CSD18540Q5B | Protection | 450 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 2250 | 13 | 5850 | 25 | 11250 | Rounded engineering estimate pending supplier quotation.
PR-034 | Epower Tech Co. Ltd | DIO-BAT-LFP-12V50-H-REV-A | Battery | 60000 | ENGINEERING_BUDGETARY_CEILING_PENDING_SUPPLIER_QUOTE |  | RUB |  | 2026-10-19 | LOW | 5 | 300000 | 11 | 660000 | 21 | 1260000 | Temporary planning ceiling for the accepted heated 50 Ah configuration; replace with the supplier quotation before commercial reconciliation.
PR-035 | Ebyte | E22-900M22S | LoRa | 1500 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 6 | 9000 | 13 | 19500 | 26 | 39000 | Rounded engineering estimate pending supplier quotation.
PR-036 | Panasonic Industry | EEH-ZK1V101XP | Passive | 120 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 44 | 5280 | 50 | 6000 | 60 | 7200 | Rounded engineering estimate pending supplier quotation.
PR-037 | Panasonic Industry | ERA-2AEB104X | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 44 | 1100 | 50 | 1250 | 60 | 1500 | Rounded engineering estimate pending supplier quotation.
PR-038 | Panasonic Industry | ERA-2AEB3572X | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 44 | 1100 | 50 | 1250 | 60 | 1500 | Rounded engineering estimate pending supplier quotation.
PR-039 | Panasonic Industry | ERA-2AEB8662X | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 48 | 1200 | 60 | 1500 | 80 | 2000 | Rounded engineering estimate pending supplier quotation.
PR-040 | Panasonic | ERJ-2GE0R00X | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 0 | 0 | 0 | 0 | 0 | 0 | Rounded engineering estimate pending supplier quotation.
PR-041 | Panasonic | ERJ-2GE0R00X | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 48 | 576 | 120 | 1440 | 240 | 2880 | Rounded engineering estimate pending supplier quotation.
PR-042 | Panasonic Industry | ERJ-2GE0R00X | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 0 | 0 | 0 | 0 | 0 | 0 | Rounded engineering estimate pending supplier quotation.
PR-043 | Panasonic Industry | ERJ-2GE0R00X | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 48 | 1200 | 60 | 1500 | 80 | 2000 | Rounded engineering estimate pending supplier quotation.
PR-044 | Panasonic Industry | ERJ-2GE0R00X | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 56 | 1400 | 80 | 2000 | 120 | 3000 | Rounded engineering estimate pending supplier quotation.
PR-045 | Panasonic | ERJ-2GEJ104X | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 8 | 96 | 20 | 240 | 40 | 480 | Rounded engineering estimate pending supplier quotation.
PR-046 | Panasonic | ERJ-2GEJ561X | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 48 | 10 | 120 | 20 | 240 | Rounded engineering estimate pending supplier quotation.
PR-047 | Panasonic | ERJ-2RKF1001X | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 20 | 240 | 50 | 600 | 100 | 1200 | Rounded engineering estimate pending supplier quotation.
PR-048 | Panasonic | ERJ-2RKF1002X | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 76 | 912 | 190 | 2280 | 380 | 4560 | Rounded engineering estimate pending supplier quotation.
PR-049 | Panasonic Industry | ERJ-2RKF1002X | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 0 | 0 | 0 | 0 | 0 | 0 | Rounded engineering estimate pending supplier quotation.
PR-050 | Panasonic Industry | ERJ-2RKF1002X | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 48 | 1200 | 60 | 1500 | 80 | 2000 | Rounded engineering estimate pending supplier quotation.
PR-051 | Panasonic | ERJ-2RKF1003X | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 0 | 0 | 0 | 0 | 0 | 0 | Rounded engineering estimate pending supplier quotation.
PR-052 | Panasonic | ERJ-2RKF1003X | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 84 | 1008 | 210 | 2520 | 420 | 5040 | Rounded engineering estimate pending supplier quotation.
PR-053 | Panasonic Industry | ERJ-2RKF1003X | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 48 | 1200 | 60 | 1500 | 80 | 2000 | Rounded engineering estimate pending supplier quotation.
PR-054 | Panasonic | ERJ-2RKF1004X | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 48 | 10 | 120 | 20 | 240 | Rounded engineering estimate pending supplier quotation.
PR-055 | Panasonic | ERJ-2RKF2201X | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 8 | 96 | 20 | 240 | 40 | 480 | Rounded engineering estimate pending supplier quotation.
PR-056 | Panasonic | ERJ-2RKF22R0X | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 116 | 1392 | 290 | 3480 | 580 | 6960 | Rounded engineering estimate pending supplier quotation.
PR-057 | Panasonic | ERJ-2RKF4701X | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 8 | 96 | 20 | 240 | 40 | 480 | Rounded engineering estimate pending supplier quotation.
PR-058 | Panasonic Industry | ERJ-2RKF4701X | Passive | 25 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 0 | 0 | 0 | 0 | 0 | 0 | Rounded engineering estimate pending supplier quotation.
PR-059 | Panasonic | ERJ-2RKF4702X | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 12 | 144 | 30 | 360 | 60 | 720 | Rounded engineering estimate pending supplier quotation.
PR-060 | Panasonic | ERJ-2RKF5101X | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 8 | 96 | 20 | 240 | 40 | 480 | Rounded engineering estimate pending supplier quotation.
PR-061 | Panasonic | ERJ-8GEYJ100V | Resistor | 12 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 48 | 10 | 120 | 20 | 240 | Rounded engineering estimate pending supplier quotation.
PR-062 | STMicroelectronics | ESDALC6V1-5P6 | ESD | 140 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 10 | 1400 | 25 | 3500 | 50 | 7000 | Rounded engineering estimate pending supplier quotation.
PR-063 | Taoglas | G30.B.108111 | Antenna | 4050 | PUBLIC_AUTHORIZED_CHANNEL_PRICE | $32.38 at qty 10 | USD | https://www.mouser.com/ | 2026-09-18 | MEDIUM | 5 | 20250 | 11 | 44550 | 22 | 89100 | Published price converted to a rounded landed-RUB planning value; final cart/quote controls.
PR-064 | Murata | GRM1555C1E470JA01D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 120 | 10 | 300 | 20 | 600 | Rounded engineering estimate pending supplier quotation.
PR-065 | Murata | GRM1555C1H100JA01D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 0 | 0 | 0 | 0 | 0 | 0 | Rounded engineering estimate pending supplier quotation.
PR-066 | Murata | GRM1555C1H100JA01D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 8 | 240 | 20 | 600 | 40 | 1200 | Rounded engineering estimate pending supplier quotation.
PR-067 | Murata | GRM1555C1H101JA01D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 120 | 10 | 300 | 20 | 600 | Rounded engineering estimate pending supplier quotation.
PR-068 | Murata | GRM1555C1H151JA01D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 120 | 10 | 300 | 20 | 600 | Rounded engineering estimate pending supplier quotation.
PR-069 | Murata | GRM1555C1H330JA01D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 0 | 0 | 0 | 0 | 0 | 0 | Rounded engineering estimate pending supplier quotation.
PR-070 | Murata | GRM1555C1H330JA01D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 8 | 240 | 20 | 600 | 40 | 1200 | Rounded engineering estimate pending supplier quotation.
PR-071 | Murata | GRM1555C1H680JA01D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 120 | 10 | 300 | 20 | 600 | Rounded engineering estimate pending supplier quotation.
PR-072 | Murata | GRM155R61A225KE15D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 8 | 240 | 20 | 600 | 40 | 1200 | Rounded engineering estimate pending supplier quotation.
PR-073 | Murata | GRM155R61C105KA12D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 12 | 360 | 30 | 900 | 60 | 1800 | Rounded engineering estimate pending supplier quotation.
PR-074 | Murata | GRM155R71C103KA01D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 120 | 10 | 300 | 20 | 600 | Rounded engineering estimate pending supplier quotation.
PR-075 | Murata | GRM155R71E103KA01D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 20 | 600 | 50 | 1500 | 100 | 3000 | Rounded engineering estimate pending supplier quotation.
PR-076 | Murata | GRM155R71E104KE14D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 0 | 0 | 0 | 0 | 0 | 0 | Rounded engineering estimate pending supplier quotation.
PR-077 | Murata | GRM155R71E104KE14D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 140 | 4200 | 350 | 10500 | 700 | 21000 | Rounded engineering estimate pending supplier quotation.
PR-078 | Murata | GRM155R71E224KE14D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 120 | 10 | 300 | 20 | 600 | Rounded engineering estimate pending supplier quotation.
PR-079 | Murata | GRM155R71E473KA01D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 120 | 10 | 300 | 20 | 600 | Rounded engineering estimate pending supplier quotation.
PR-080 | Murata | GRM155R72A472KA01D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 120 | 10 | 300 | 20 | 600 | Rounded engineering estimate pending supplier quotation.
PR-081 | Murata | GRM188R61A106KE69D | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 32 | 960 | 80 | 2400 | 160 | 4800 | Rounded engineering estimate pending supplier quotation.
PR-082 | Murata | GRM21BR61A226ME44L | Capacitor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 120 | 10 | 300 | 20 | 600 | Rounded engineering estimate pending supplier quotation.
PR-083 | Texas Instruments | INA226AIDGSR | Monitor | 550 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 2750 | 13 | 7150 | 25 | 13750 | Rounded engineering estimate pending supplier quotation.
PR-084 | STMicroelectronics | LIS2DW12TR | Motion | 350 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 1750 | 13 | 4550 | 25 | 8750 | Rounded engineering estimate pending supplier quotation.
PR-085 | Texas Instruments | LM74700QDBVRQ1 | Protection | 600 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 3000 | 13 | 7800 | 25 | 15000 | Rounded engineering estimate pending supplier quotation.
PR-086 | Texas Instruments | LMR604403SRAKR | Power | 950 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 10 | 9500 | 26 | 24700 | 50 | 47500 | Rounded engineering estimate pending supplier quotation.
PR-087 | Murata | LQH32PN2R2NN0L | Inductor | 180 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 720 | 10 | 1800 | 20 | 3600 | Rounded engineering estimate pending supplier quotation.
PR-088 | Murata | LQW15AN27NJ00D | Inductor | 180 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 720 | 10 | 1800 | 20 | 3600 | Rounded engineering estimate pending supplier quotation.
PR-089 | Analog Devices | LT6000IDCB#TRMPBF | Operational_Amplifier | 650 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 2600 | 10 | 6500 | 20 | 13000 | Rounded engineering estimate pending supplier quotation.
PR-090 | u-blox | MAX-M10S-00B | GNSS | 2500 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 12500 | 13 | 32500 | 25 | 62500 | Rounded engineering estimate pending supplier quotation.
PR-091 | Raytac | MDBT50Q-P1MV2 | BLE | 2200 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 11000 | 13 | 28600 | 25 | 55000 | Rounded engineering estimate pending supplier quotation.
PR-092 | GCT | MEM2052-00-195-00-A | Connector | 550 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 2750 | 13 | 7150 | 25 | 13750 | Rounded engineering estimate pending supplier quotation.
PR-093 | Nexperia | MMBT3904,215 | Transistor | 30 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 15 | 450 | 39 | 1170 | 75 | 2250 | Rounded engineering estimate pending supplier quotation.
PR-094 | TDK InvenSense | MMICT5838-00-012 | Microphone | 500 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 20 | 10000 | 48 | 24000 | 96 | 48000 | Rounded engineering estimate pending supplier quotation.
PR-095 | PCB fabrication | NET_TIE_COPPER_REV_A | PCB feature | 0 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 12 | 0 | 30 | 0 | 60 | 0 | Rounded engineering estimate pending supplier quotation.
PR-096 | Nexperia | PESD5V0C1BSF | RF_ESD | 120 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 8 | 960 | 20 | 2400 | 40 | 4800 | Rounded engineering estimate pending supplier quotation.
PR-097 | Nexperia | PESD5V0S1UL | Supply_TVS | 100 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 8 | 800 | 20 | 2000 | 40 | 4000 | Rounded engineering estimate pending supplier quotation.
PR-098 | Victron Energy | SBS050150200 | Sensor | 4900 | PUBLIC_DISTRIBUTOR_PRICE | $39.10 | USD | https://www.invertersupply.com/index.php?main_page=product_info&products_id=194069 | 2026-09-18 | MEDIUM | 5 | 24500 | 11 | 53900 | 21 | 102900 | Published price converted to a rounded landed-RUB planning value; final cart/quote controls.
PR-099 | Victron Energy | SCC075010060R | Controller | 8200 | PUBLIC_DISTRIBUTOR_PRICE | $65.45 | USD | https://www.invertersupply.com/index.php?main_page=product_info&products_id=31070 | 2026-09-18 | MEDIUM | 5 | 41000 | 11 | 90200 | 21 | 172200 | Published price converted to a rounded landed-RUB planning value; final cart/quote controls.
PR-100 | Kingston | SDCIT2/32GB | Storage | 2600 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 13000 | 13 | 33800 | 25 | 65000 | Rounded engineering estimate pending supplier quotation.
PR-101 | SLD Tech / Solarland | SLP080S-12M | Solar panel | 22200 | PUBLIC_DISTRIBUTOR_PRICE | $177.63 | USD | https://www.mrsolar.com/solarland-slp080-12m-80w-12v-skinny-solar-panel-w-pro-charge-jbox/ | 2026-09-18 | MEDIUM | 5 | 111000 | 11 | 244200 | 21 | 466200 | Published price converted to a rounded landed-RUB planning value; final cart/quote controls.
PR-102 | Littelfuse | SMBJ18A | Protection | 120 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 600 | 13 | 1560 | 25 | 3000 | Rounded engineering estimate pending supplier quotation.
PR-103 | Texas Instruments | SN74AXC1T45DRLR | Logic | 180 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 900 | 13 | 2340 | 25 | 4500 | Rounded engineering estimate pending supplier quotation.
PR-104 | Texas Instruments | SN74AXC8T245PWR | Level translator ¦ Logic | 600 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 10 | 6000 | 26 | 15600 | 50 | 30000 | Rounded engineering estimate pending supplier quotation.
PR-105 | Texas Instruments | SN74LVC1G07DBVR | Open_Drain_Buffer | 100 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 400 | 10 | 1000 | 20 | 2000 | Rounded engineering estimate pending supplier quotation.
PR-106 | Texas Instruments | SN74LVC32APWR | Logic | 220 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 1100 | 13 | 2860 | 25 | 5500 | Rounded engineering estimate pending supplier quotation.
PR-107 | STMicroelectronics | STM32U585VIT6Q | MCU | 2500 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 12500 | 13 | 32500 | 25 | 62500 | Rounded engineering estimate pending supplier quotation.
PR-108 | STMicroelectronics | STTS22HTR | Temperature | 250 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 1250 | 13 | 3250 | 25 | 6250 | Rounded engineering estimate pending supplier quotation.
PR-109 | Vishay | Si1016X-T1-GE3 | Dual_MOSFET | 180 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 720 | 10 | 1800 | 20 | 3600 | Rounded engineering estimate pending supplier quotation.
PR-110 | SiTime | SiT1552AI-JE-DCC-32.768D | Clock | 500 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 2500 | 13 | 6500 | 25 | 12500 | Rounded engineering estimate pending supplier quotation.
PR-111 | KEMET | T520D107M006ATE015 | Capacitor | 300 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 8 | 2400 | 20 | 6000 | 40 | 12000 | Rounded engineering estimate pending supplier quotation.
PR-112 | Taoglas | TI.89.B.2111W | Antenna | 1350 | PUBLIC_DISTRIBUTOR_PRICE | EUR 9.673 at qty 10 | EUR | https://www.digikey.ee/ | 2026-09-18 | MEDIUM | 5 | 6750 | 11 | 14850 | 22 | 29700 | Published price converted to a rounded landed-RUB planning value; final cart/quote controls.
PR-113 | Texas Instruments | TPD1E05U06DYAR | ESD_Diode | 100 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 24 | 2400 | 60 | 6000 | 120 | 12000 | Rounded engineering estimate pending supplier quotation.
PR-114 | Texas Instruments | TPD1E05U06DYAR | RF_ESD | 100 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 4 | 400 | 10 | 1000 | 20 | 2000 | Rounded engineering estimate pending supplier quotation.
PR-115 | Texas Instruments | TPD2EUSB30DRTR | USB_ESD_Array | 180 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 8 | 1440 | 20 | 3600 | 40 | 7200 | Rounded engineering estimate pending supplier quotation.
PR-116 | Texas Instruments | TPD4E05U06DQAR | ESD_Array | 250 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 28 | 7000 | 70 | 17500 | 140 | 35000 | Rounded engineering estimate pending supplier quotation.
PR-117 | Texas Instruments | TPS7A2018PDBVR | Power | 160 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 800 | 13 | 2080 | 25 | 4000 | Rounded engineering estimate pending supplier quotation.
PR-118 | Texas Instruments | TS3A27518EPWR | SIM switch | 550 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 2750 | 13 | 7150 | 25 | 13750 | Rounded engineering estimate pending supplier quotation.
PR-119 | Hirose | U.FL-R-SMT-1(60) | RF connector | 250 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 12 | 3000 | 28 | 7000 | 56 | 14000 | Rounded engineering estimate pending supplier quotation.
PR-120 | Hirose | U.FL-R-SMT-1(60) | RF connector | 250 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 6 | 1500 | 14 | 3500 | 28 | 7000 | Rounded engineering estimate pending supplier quotation.
PR-121 | GCT | USB4105-GF-A-120 | Connector | 650 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 3250 | 13 | 8450 | 25 | 16250 | Rounded engineering estimate pending supplier quotation.
PR-122 | Winbond | W25Q512JVFIQ | Memory | 800 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 5 | 4000 | 13 | 10400 | 25 | 20000 | Rounded engineering estimate pending supplier quotation.
PR-123 | Vishay Dale | WSK2512R0100FEA | Shunt | 450 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 6 | 2700 | 15 | 6750 | 30 | 13500 | Rounded engineering estimate pending supplier quotation.
PR-124 | Coilcraft | XAL7030-472MEC | Passive | 420 | ENGINEERING_BUDGETARY_ESTIMATE |  | RUB |  | 2026-09-18 | LOW | 18 | 7560 | 30 | 12600 | 50 | 21000 | Rounded engineering estimate pending supplier quotation.

## Program 41
Program_Procurement_ID | Procurement_ID | Assemblies | Item_IDs | Category | Manufacturer | MPN | Package | Value | Variant | Population | Qty_per_station | Production_lots_20 | Bench_stations | Total_stations | Base_qty_2x20_plus_1 | Spare_qty_two_evt20_lots | Procure_qty_2x20_plus_1 | Spare_policy | Procurement_track | BOM_disposition | Status | China_source_policy | Incoming_control | Program_scope
PG-001 | PR-001 | PCB-MAIN | ASM-MAIN | PCBA | Dioneya controlled design | DIO-ASM-MAIN-REV-A | 6-layer PCBA build-to-print service scope |  | COMMON | N/A | 1 | 2 | 1 | 41 | 41 | 4 | 45 | FIXED_LOT_MIN | PRIMARY_FULL_PCBA | CONTROLLED_CUSTOMER_RFQ_SCOPE | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_EMS_SELECTION_PENDING | Customer-selected qualified EMS; quotation and purchase outside the engineering repository | AOI plus X-ray where hidden joints plus functional test | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-002 | PR-002 | PCB-MIC | ASM-MIC | PCBA | Dioneya controlled design | DIO-ASM-MIC-REV-A | 2-layer microphone PCBA build-to-print service scope |  | COMMON | N/A | 4 | 2 | 1 | 41 | 164 | 4 | 168 | FIXED_LOT_MIN | PRIMARY_FULL_PCBA | CONTROLLED_CUSTOMER_RFQ_SCOPE | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_EMS_SELECTION_PENDING | Customer-selected qualified EMS; quotation and purchase outside the engineering repository | AOI acoustic port inspection channel functional test | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-003 | PR-003 | PCB-PWR | ASM-PWR | PCBA | Dioneya controlled design | DIO-ASM-PWR-REV-A | assembled 4-layer power PCB build-to-print service scope; EVT DIM-003 90x60x1.6 mm and H1-H4 accepted; outer 2 oz target; inner 1 oz target; final stackup pending DFM |  | COMMON | N/A | 1 | 2 | 1 | 41 | 41 | 4 | 45 | FIXED_LOT_MIN | PRIMARY_FULL_PCBA | CONTROLLED_CUSTOMER_RFQ_SCOPE | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_EMS_SELECTION_PENDING | Customer-selected qualified EMS; quotation and purchase outside the engineering repository | AOI functional high-current thermal | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-004 | PR-004 | SYSTEM | HARNESS | Harness | Dioneya controlled design | DIO-HARNESS-SET-REV-A | Controlled labeled station harness set Rev.A |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 4 | 45 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_BUILD_TO_PRINT_IDENTITY | CONTROLLED_INTERNAL_ARTICLE_PHYSICAL_RELEASE_PENDING | Customer-selected qualified harness assembler; build only to the controlled drawing and schedule | 100 percent continuity polarity pull sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-005 | PR-005 | SYSTEM | HSG-3D | Housing | TBD | TBD | Assembly |  | THREE_D_PRINT_FALLBACK | N/A | 0 | 2 | 1 | 41 | 0 | 0 | 0 | NONE | COMMON_PROGRAM_PROCUREMENT | CONDITIONAL_NOT_RELEASED | SOURCE_PACKAGE_REQUIRED | Qualified print supplier or controlled FlashForge 5M Pro process | Engineering sample dimensions material finish leak fit acoustic and RF checks | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-006 | PR-006 | SYSTEM | HSG-IM | Housing | TBD | TBD | Source_data |  | INJECTION_MOLDING_FUTURE | N/A | 0 | 2 | 1 | 41 | 0 | 0 | 0 | NONE | COMMON_PROGRAM_PROCUREMENT | CONDITIONAL_NOT_RELEASED | SOURCE_PACKAGE_REQUIRED | Qualified mold manufacturer for DFM quotation | Source audit wall draft ribs bosses parting ejector shrink material and tooling concept | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-007 | PR-007 | SYSTEM | HSG-VC | Housing | Dioneya controlled design | DIO-HSG-VC-REV-A | Vacuum-cast polyurethane housing set build-to-print scope |  | VACUUM_CASTING_PRIMARY | N/A | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_CUSTOMER_RFQ_SCOPE | CONTROLLED_INTERNAL_ARTICLE_MECHANICAL_RELEASE_PENDING | Customer-selected qualified vacuum-casting supplier; quotation and purchase outside the engineering repository | FAI dimensions material cure finish inserts leak fit acoustic and RF checks | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-008 | PR-008 | PCB-MAIN | PCB-MAIN | Bare PCB | Dioneya controlled design | DIO-PCB-MAIN-REV-A | 6-layer FR-4 110x75x1.6 mm build-to-print fabrication scope |  | COMMON | N/A | 1 | 2 | 1 | 41 | 41 | 4 | 45 | FIXED_LOT_MIN | ALTERNATIVE_BARE_PCB_QUOTATION_ONLY | CONTROLLED_CUSTOMER_RFQ_SCOPE | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_FAB_SELECTION_PENDING | Customer-selected qualified PCB fabricator; quotation and purchase outside the engineering repository | Coupon dimensions finish stackup impedance and netlist test | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-009 | PR-009 | PCB-MIC | PCB-MIC | Bare PCB | Dioneya controlled design | DIO-PCB-MIC-REV-A | 2-layer FR-4 microphone PCB build-to-print fabrication scope |  | COMMON | N/A | 4 | 2 | 1 | 41 | 164 | 4 | 168 | FIXED_LOT_MIN | ALTERNATIVE_BARE_PCB_QUOTATION_ONLY | CONTROLLED_CUSTOMER_RFQ_SCOPE | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_FAB_SELECTION_PENDING | Customer-selected qualified PCB fabricator; quotation and purchase outside the engineering repository | Outline hole position finish netlist | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-010 | PR-010 | PCB-PWR | PCB-PWR | Bare PCB | Dioneya controlled design | DIO-PCB-PWR-REV-A | 4-layer FR-4 90x60x1.6 mm build-to-print fabrication scope; EVT DIM-003 and H1-H4 accepted; outer 2 oz target; inner 1 oz target; final stackup pending DFM |  | COMMON | N/A | 1 | 2 | 1 | 41 | 41 | 4 | 45 | FIXED_LOT_MIN | ALTERNATIVE_BARE_PCB_QUOTATION_ONLY | CONTROLLED_CUSTOMER_RFQ_SCOPE | CONTROLLED_INTERNAL_ARTICLE_CUSTOMER_FAB_SELECTION_PENDING | Customer-selected qualified PCB fabricator; quotation and purchase outside the engineering repository | Copper thickness netlist high-current and Kelvin review | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-011 | PR-011 | PCB-PWR | PWR-FUSE-01 | Protection | Littelfuse | 0451008.MRL | Nano2_451_6.1x2.69mm |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 20 | 61 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | CANDIDATE_SELECTED_FOR_EVT_QUALIFICATION_NATIVE_VALUE_ECO_APPLIED_REPEAT_EVIDENCE_PASS_PHYSICAL_QUALIFICATION_PENDING | Authorized distributor | Marking continuity and controlled fault clearing | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-012 | PR-012 | PCB-MAIN | J-SIM1 ¦ J-SIM2 | SIM | TE Connectivity | 2336582-1 | Nano-SIM 4FF connector with DET |  | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 20 | 102 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | TECHNICALLY_SELECTED_PROCUREMENT_RISK | Approved connector vendor | Mating cycles card detect coplanarity and ESD | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-013 | PR-013 | HARNESS-PWR-MAIN | H-PWR-MAIN | Housing | Molex | 43025-1200 | Micro-Fit 3.0 12-circuit housing |  | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 8 | 90 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_MECHANICS_I2C_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-014 | PR-014 | HARNESS-PWR-MAIN | T-PWR-MAIN-CTL | Terminal | Molex | 43030-0001 | Micro-Fit female crimp terminal 20-24 AWG class |  | COMMON | FITTED | 12 | 2 | 1 | 41 | 492 | 24 | 516 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_I2C_PULL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-015 | PR-015 | HARNESS-PWR-MAIN | T-PWR-MAIN-PWR | Terminal | Molex | 43030-0038 | Micro-Fit female crimp terminal 18 AWG class |  | COMMON | FITTED | 12 | 2 | 1 | 41 | 492 | 24 | 516 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_CURRENT_PULL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-016 | PR-016 | PCB-PWR | J-PWR-IN | Connector | Molex | 430450213 | 2 positions |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_MECHANICS | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-017 | PR-017 | PCB-MAIN ¦ PCB-PWR | J-PWR-MAIN ¦ J-PWR-PWR | Connector | Molex | 430451202 | 12 positions |  | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 20 | 102 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | MECHANICAL_AUTHORITY_FROZEN_PENDING_HARNESS_SI ¦ SELECTED_ELECTRICAL_PENDING_MECHANICS | Authorized Molex distributor | Marking dimensions latch mate continuity | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-018 | PR-018 | PCB-MAIN | J-TAMPER | Connector | Molex | 5040500291 | Pico-Lock 1.50 mm 2-circuit right-angle SMT |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | MECHANICAL_AUTHORITY_FROZEN_PENDING_PHYSICAL_TEST | Authorized Molex distributor | Mating pull continuity cable-break and cover-open fault coverage | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-019 | PR-019 | PCB-MAIN ¦ PCB-MIC | J-MIC ¦ J-MIC-MAIN | Connector | Molex | 5040500691 | Pico-Lock 1.50 mm 6-circuit right-angle SMT |  | COMMON | FITTED | 8 | 2 | 1 | 41 | 328 | 48 | 376 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | MECHANICAL_AUTHORITY_FROZEN_PENDING_SI_AAD | Authorized Molex distributor ¦ Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample ¦ Mating pull test contact resistance continuity and temperature | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-020 | PR-020 | HARNESS-MIC | H-MIC | Housing | Molex | 5040510601 | Pico-Lock 1.50 mm 6-circuit housing |  | COMMON | FITTED | 8 | 2 | 1 | 41 | 328 | 32 | 360 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_HARNESS_LENGTH_PULL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-021 | PR-021 | HARNESS-MIC | T-MIC | Terminal | Molex | 5040520098 | Pico-Lock crimp terminal 28-24 AWG |  | COMMON | FITTED | 48 | 2 | 1 | 41 | 1968 | 96 | 2064 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_CRIMP_PULL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-022 | PR-022 | SYSTEM | ANT-GNSS | Antenna | Taoglas | AA.166.A.301111 | IP67 magnetic 37.8x40.4x10 mm with 3 m RG174 SMA(M) |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 4 | 45 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Taoglas or established distributor; exact AA.166.A.301111 only; no substitution | Reconcile PO packing slip quantity and visible damage; verify connector cable route current at 3.3 V receiver sensitivity PPS mounting and coexistence during assembly EOL and EVT | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-023 | PR-023 | PCB-MAIN | MAIN-010-FL1 | SAW_Filter | Abracon | ABSES5AF-L100KM | 1109-5 | 1582.4 MHz wideband GNSS SAW | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-024 | PR-024 | PCB-MAIN | U8 | Cellular | Quectel | BG95-M3 | LGA-102_23.6x19.9mm |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_INCOMING_ID_AND_POST_ASSEMBLY_EVT | Quectel authorized channel or CM with traceability | IMEI label firmware RF conducted attach TLS | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-025 | PR-025 | PCB-MAIN | MAIN-010-FB1 | Ferrite_Bead | Murata | BLM31KN601SN1L | 1206 | 600 Ohm at 100 MHz | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-026 | PR-026 | SYSTEM | RF-PIGTAIL | RF cable | Taoglas | CAB.0243 | 1.13 mm micro-coax 150 mm MHF I/U.FL-compatible R/A to waterproof SMA(F) bulkhead |  | COMMON | FITTED | 3 | 2 | 1 | 41 | 123 | 12 | 135 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Taoglas or established distributor; exact CAB.0243 only; no substitution | Reconcile PO packing slip quantity and visible damage; verify every installed cable continuity polarity length and route then mate retention bend seal torque temperature and VNA performance during assembly EOL and EVT | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-027 | PR-027 | PCB-PWR | PWR-C-100N | Passive | TDK | CGA2B3X7R1E104K050BB | 0402 | 100 nF 25 V X7R | COMMON | FITTED | 4 | 2 | 1 | 41 | 164 | 80 | 244 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | LOCKED_CANDIDATE_PENDING_DERATING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-028 | PR-028 | PCB-MIC | C-MIC | Passive | TDK | CGA2B3X7R1E104K050BB | 0402 1005 metric | 100 nF 25 V X7R | COMMON | FITTED | 4 | 2 | 1 | 41 | 164 | 80 | 244 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SAMPLE | Traceable passive vendor | Value package reel label capacitance sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-029 | PR-029 | PCB-PWR | PWR-C-LDO | Passive | TDK | CGA3E1X7R1A225K080AC | 0603 | 2.2 uF 10 V X7R | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 80 | 162 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | LOCKED_CANDIDATE_PENDING_DERATING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-030 | PR-030 | PCB-PWR | PWR-C-CIN-HF | Passive | TDK | CGA3E2X7R1H104K080AA | 0603 | 100 nF 50 V X7R | COMMON | FITTED | 3 | 2 | 1 | 41 | 123 | 80 | 203 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | CONTROLLED_CANDIDATE_PENDING_MULTIPLE_REVIEWS | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-031 | PR-031 | PCB-PWR | PWR-COUT-3V3 ¦ PWR-COUT-3V8 | Passive | TDK | CGA6P3X7R1E226M250AB | 1210 | 22 uF 25 V X7R | COMMON | FITTED | 8 | 2 | 1 | 41 | 328 | 160 | 488 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | LOCKED_CANDIDATE_PENDING_DERATING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-032 | PR-032 | PCB-PWR | PWR-C-INPUT | Passive | TDK | CGA6P3X7R1H475K250AB | 1210 | 4.7 uF 50 V X7R | COMMON | FITTED | 3 | 2 | 1 | 41 | 123 | 80 | 203 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | CONTROLLED_CANDIDATE_PENDING_MULTIPLE_REVIEWS | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-033 | PR-033 | PCB-PWR | PWR-REV-FET | Protection | Texas Instruments | CSD18540Q5B | VSON-CLIP 5x6 mm |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED | SELECTED_TECHNICALLY_PROCUREMENT_CHECK | Authorized distributor | Marking Rds thermal and reverse fault test | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-034 | PR-034 | SYSTEM | BAT1 | Battery | Epower Tech Co. Ltd | DIO-BAT-LFP-12V50-H-REV-A | 198x166x170 mm body; 182-184 mm including M8 studs |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 2 | 43 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Epower Tech supplier-configured heated article DIO-BAT-LFP-12V50-H-REV-A only; no substitution; PO must state heater option dimensions terminal geometry and applicable UN38.3 SDS and route documents | Reconcile PO packing slip quantity configuration and damage; check every unit dimensions polarity and OCV; verify heater threshold and current then capacity DCIR BMS charge inhibit and cold behavior during assembly and EVT | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-035 | PR-035 | PCB-MAIN | U10 | LoRa | Ebyte | E22-900M22S | SMD_20x14_22P_1.27mm |  | RU868_PILOT | FITTED | 1 | 2 | 1 | 41 | 41 | 12 | 53 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_CASTELLATED_OPTION_RF_REGULATORY | Ebyte official store or authorized distributor | Marking antenna-interface option firmware conducted power sensitivity sleep current | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-036 | PR-036 | PCB-PWR | PWR-C-BULK | Passive | Panasonic Industry | EEH-ZK1V101XP | SMD can 6.3x7.7 mm | 100 uF 35 V hybrid | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 80 | 121 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | LOCKED_CANDIDATE_PACKAGE_REVIEW_PENDING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-037 | PR-037 | PCB-PWR | PWR-R-100K-01 | Passive | Panasonic Industry | ERA-2AEB104X | 0402 | 100 kOhm 0.1% | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 80 | 121 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | LOCKED_CANDIDATE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-038 | PR-038 | PCB-PWR | PWR-R-35K7 | Passive | Panasonic Industry | ERA-2AEB3572X | 0402 | 35.7 kOhm 0.1% | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 80 | 121 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | LOCKED_CANDIDATE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-039 | PR-039 | PCB-PWR | PWR-R-86K6 | Passive | Panasonic Industry | ERA-2AEB8662X | 0402 | 86.6 kOhm 0.1% | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 80 | 162 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | LOCKED_CANDIDATE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-040 | PR-040 | PCB-MAIN | MAIN-010-R98 | Resistor | Panasonic | ERJ-2GE0R00X | 0402 | 0 Ohm | COMMON | DNP | 0 | 2 | 1 | 41 | 0 | 0 | 0 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_DNP | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-041 | PR-041 | PCB-MAIN | MAIN-010-R103 ¦ MAIN-010-R39 ¦ MAIN-010-R40 ¦ MAIN-010-R42 ¦ MAIN-010-R43 ¦ MAIN-010-R50 ¦ MAIN-010-R51 ¦ MAIN-010-R52 ¦ MAIN-010-R53 ¦ MAIN-010-R54 ¦ MAIN-010-R55 ¦ MAIN-010-R73 | Resistor | Panasonic | ERJ-2GE0R00X | 0402 | 0 Ohm | COMMON | FITTED | 12 | 2 | 1 | 41 | 492 | 0 | 492 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-042 | PR-042 | PCB-PWR | PWR-R-0R-DNP | Passive | Panasonic Industry | ERJ-2GE0R00X | 0402 | 0 ohm | COMMON | DNP | 0 | 2 | 1 | 41 | 0 | 0 | 0 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_DNP | LOCKED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-043 | PR-043 | PCB-PWR | PWR-R-0R | Passive | Panasonic Industry | ERJ-2GE0R00X | 0402 | 0 ohm | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 80 | 162 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | LOCKED_FITTED | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-044 | PR-044 | PCB-MIC | R-MIC | Passive | Panasonic Industry | ERJ-2GE0R00X | 0402 1005 metric | 0 ohm | COMMON | FITTED | 4 | 2 | 1 | 41 | 164 | 80 | 244 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_POPULATED_BASELINE_PENDING_SI | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-045 | PR-045 | PCB-MAIN | MAIN-010-R60 ¦ MAIN-010-R61 | Resistor | Panasonic | ERJ-2GEJ104X | 0402 | 100 kOhm 5% 0.1 W | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 0 | 82 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-046 | PR-046 | PCB-MAIN | MAIN-010-R59 | Resistor | Panasonic | ERJ-2GEJ561X | 0402 | 560 Ohm 5% 0.1 W | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-047 | PR-047 | PCB-MAIN | MAIN-010-R100 ¦ MAIN-010-R102 ¦ MAIN-010-R38 ¦ MAIN-010-R41 ¦ MAIN-010-R95 | Resistor | Panasonic | ERJ-2RKF1001X | 0402 | 1 kOhm 1% | COMMON | FITTED | 5 | 2 | 1 | 41 | 205 | 0 | 205 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-048 | PR-048 | PCB-MAIN | MAIN-010-R1 ¦ MAIN-010-R28 ¦ MAIN-010-R30 ¦ MAIN-010-R31 ¦ MAIN-010-R46 ¦ MAIN-010-R48 ¦ MAIN-010-R49 ¦ MAIN-010-R67 ¦ MAIN-010-R68 ¦ MAIN-010-R7 ¦ MAIN-010-R76 ¦ MAIN-010-R78 ¦ MAIN-010-R85 ¦ MAIN-010-R86 ¦ MAIN-010-R87 ¦ MAIN-010-R88 ¦ MAIN-010-R89 ¦ MAIN-010-R90 ¦ MAIN-010-R99 | Resistor | Panasonic | ERJ-2RKF1002X | 0402 | 10 kOhm 1% | COMMON | FITTED | 19 | 2 | 1 | 41 | 779 | 0 | 779 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-049 | PR-049 | PCB-PWR | PWR-R-10K-DNP | Passive | Panasonic Industry | ERJ-2RKF1002X | 0402 | 10 kOhm 1% | COMMON | DNP | 0 | 2 | 1 | 41 | 0 | 0 | 0 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_DNP | LOCKED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-050 | PR-050 | PCB-PWR | PWR-R-10K | Passive | Panasonic Industry | ERJ-2RKF1002X | 0402 | 10 kOhm 1% | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 80 | 162 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | LOCKED_FITTED | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-051 | PR-051 | PCB-MAIN | MAIN-010-R4 ¦ MAIN-010-R6 | Resistor | Panasonic | ERJ-2RKF1003X | 0402 | 100 kOhm 1% | COMMON | DNP | 0 | 2 | 1 | 41 | 0 | 0 | 0 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_DNP | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-052 | PR-052 | PCB-MAIN | MAIN-010-R19 ¦ MAIN-010-R2 ¦ MAIN-010-R20 ¦ MAIN-010-R21 ¦ MAIN-010-R22 ¦ MAIN-010-R23 ¦ MAIN-010-R29 ¦ MAIN-010-R3 ¦ MAIN-010-R32 ¦ MAIN-010-R33 ¦ MAIN-010-R34 ¦ MAIN-010-R35 ¦ MAIN-010-R45 ¦ MAIN-010-R47 ¦ MAIN-010-R5 ¦ MAIN-010-R63 ¦ MAIN-010-R64 ¦ MAIN-010-R65 ¦ MAIN-010-R66 ¦ MAIN-010-R77 ¦ MAIN-010-R96 | Resistor | Panasonic | ERJ-2RKF1003X | 0402 | 100 kOhm 1% | COMMON | FITTED | 21 | 2 | 1 | 41 | 861 | 0 | 861 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-053 | PR-053 | PCB-PWR | PWR-R-100K | Passive | Panasonic Industry | ERJ-2RKF1003X | 0402 | 100 kOhm 1% | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 80 | 162 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | LOCKED_FITTED | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-054 | PR-054 | PCB-MAIN | MAIN-010-R97 | Resistor | Panasonic | ERJ-2RKF1004X | 0402 | 1 MOhm 1% | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-055 | PR-055 | PCB-MAIN | MAIN-010-R13 ¦ MAIN-010-R14 | Resistor | Panasonic | ERJ-2RKF2201X | 0402 | 2.2 kOhm 1% | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 0 | 82 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-056 | PR-056 | PCB-MAIN | MAIN-010-R10 ¦ MAIN-010-R101 ¦ MAIN-010-R11 ¦ MAIN-010-R12 ¦ MAIN-010-R15 ¦ MAIN-010-R16 ¦ MAIN-010-R17 ¦ MAIN-010-R18 ¦ MAIN-010-R36 ¦ MAIN-010-R37 ¦ MAIN-010-R56 ¦ MAIN-010-R57 ¦ MAIN-010-R58 ¦ MAIN-010-R69 ¦ MAIN-010-R70 ¦ MAIN-010-R71 ¦ MAIN-010-R72 ¦ MAIN-010-R74 ¦ MAIN-010-R75 ¦ MAIN-010-R79 ¦ MAIN-010-R8 ¦ MAIN-010-R80 ¦ MAIN-010-R81 ¦ MAIN-010-R82 ¦ MAIN-010-R83 ¦ MAIN-010-R84 ¦ MAIN-010-R9 ¦ MAIN-010-R91 ¦ MAIN-010-R92 | Resistor | Panasonic | ERJ-2RKF22R0X | 0402 | 22 Ohm 1% | COMMON | FITTED | 29 | 2 | 1 | 41 | 1189 | 0 | 1189 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-057 | PR-057 | PCB-MAIN | MAIN-010-R24 ¦ MAIN-010-R26 | Resistor | Panasonic | ERJ-2RKF4701X | 0402 | 4.7 kOhm 1% | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 0 | 82 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-058 | PR-058 | PCB-PWR | PWR-R-4K7-DNP | Passive | Panasonic Industry | ERJ-2RKF4701X | 0402 | 4.7 kOhm 1% | COMMON | DNP | 0 | 2 | 1 | 41 | 0 | 0 | 0 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_DNP | LOCKED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-059 | PR-059 | PCB-MAIN | MAIN-010-R25 ¦ MAIN-010-R27 ¦ MAIN-010-R44 | Resistor | Panasonic | ERJ-2RKF4702X | 0402 | 47 kOhm 1% | COMMON | FITTED | 3 | 2 | 1 | 41 | 123 | 0 | 123 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-060 | PR-060 | PCB-MAIN | MAIN-010-R93 ¦ MAIN-010-R94 | Resistor | Panasonic | ERJ-2RKF5101X | 0402 | 5.1 kOhm 1% | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 0 | 82 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-061 | PR-061 | PCB-MAIN | MAIN-010-R62 | Resistor | Panasonic | ERJ-8GEYJ100V | 1206 | 10 Ohm 5% 0.25 W | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-062 | PR-062 | PCB-MAIN | U14-U15 | ESD | STMicroelectronics | ESDALC6V1-5P6 | SOT666_1.6x1.6mm |  | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 20 | 102 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SIM_ESD_SI_SAMPLE | Authorized distributor | Capacitance leakage ESD rating marking | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-063 | PR-063 | SYSTEM | ANT-CELL | Antenna | Taoglas | G30.B.108111 | IP67 screw-mount dome with 1 m cable and SMA(M) |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 4 | 45 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Taoglas or established distributor; exact G30.B.108111 only; no substitution; resolve manufacturer page cable-construction discrepancy on quote | Reconcile PO packing slip quantity and visible damage; verify cable length connector mate route seal installed VSWR loss attach and coexistence during assembly EOL and EVT | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-064 | PR-064 | PCB-MAIN | MAIN-010-C64 | Capacitor | Murata | GRM1555C1E470JA01D | 0402 | 47 pF 25 V C0G | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-065 | PR-065 | PCB-MAIN | MAIN-010-C69 ¦ MAIN-010-C70 ¦ MAIN-010-C79 ¦ MAIN-010-C80 | Capacitor | Murata | GRM1555C1H100JA01D | 0402 | 10 pF 50 V C0G | COMMON | DNP | 0 | 2 | 1 | 41 | 0 | 0 | 0 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_DNP | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-066 | PR-066 | PCB-MAIN | MAIN-010-C43 ¦ MAIN-010-C47 | Capacitor | Murata | GRM1555C1H100JA01D | 0402 | 10 pF 50 V C0G | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 0 | 82 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-067 | PR-067 | PCB-MAIN | MAIN-010-C40 | Capacitor | Murata | GRM1555C1H101JA01D | 0402 | 100 pF 50 V C0G | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-068 | PR-068 | PCB-MAIN | MAIN-010-C39 | Capacitor | Murata | GRM1555C1H151JA01D | 0402 | 150 pF 50 V C0G | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-069 | PR-069 | PCB-MAIN | MAIN-010-C54 ¦ MAIN-010-C55 ¦ MAIN-010-C56 ¦ MAIN-010-C57 ¦ MAIN-010-C58 ¦ MAIN-010-C59 | Capacitor | Murata | GRM1555C1H330JA01D | 0402 | 33 pF 50 V C0G | COMMON | DNP | 0 | 2 | 1 | 41 | 0 | 0 | 0 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_DNP | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-070 | PR-070 | PCB-MAIN | MAIN-010-C42 ¦ MAIN-010-C46 | Capacitor | Murata | GRM1555C1H330JA01D | 0402 | 33 pF 50 V C0G | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 0 | 82 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-071 | PR-071 | PCB-MAIN | MAIN-010-C41 | Capacitor | Murata | GRM1555C1H680JA01D | 0402 | 68 pF 50 V C0G | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-072 | PR-072 | PCB-MAIN | MAIN-010-C14 ¦ MAIN-010-C15 | Capacitor | Murata | GRM155R61A225KE15D | 0402 | 2.2 uF 10 V X5R | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 0 | 82 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-073 | PR-073 | PCB-MAIN | MAIN-010-C11 ¦ MAIN-010-C22 ¦ MAIN-010-C9 | Capacitor | Murata | GRM155R61C105KA12D | 0402 | 1 uF 16 V X5R | COMMON | FITTED | 3 | 2 | 1 | 41 | 123 | 0 | 123 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-074 | PR-074 | PCB-MAIN | MAIN-010-C63 | Capacitor | Murata | GRM155R71C103KA01D | 0402 | 10 nF 16 V X7R | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-075 | PR-075 | PCB-MAIN | MAIN-010-C48 ¦ MAIN-010-C52 ¦ MAIN-010-C53 ¦ MAIN-010-C76 ¦ MAIN-010-C78 | Capacitor | Murata | GRM155R71E103KA01D | 0402 | 10 nF 25 V X7R | COMMON | FITTED | 5 | 2 | 1 | 41 | 205 | 0 | 205 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-076 | PR-076 | PCB-MAIN | MAIN-010-C16 ¦ MAIN-010-C17 | Capacitor | Murata | GRM155R71E104KE14D | 0402 | 100 nF 25 V X7R | COMMON | DNP | 0 | 2 | 1 | 41 | 0 | 0 | 0 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_DNP | CONTROLLED_DNP | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-077 | PR-077 | PCB-MAIN | MAIN-010-C1 ¦ MAIN-010-C10 ¦ MAIN-010-C12 ¦ MAIN-010-C18 ¦ MAIN-010-C2 ¦ MAIN-010-C21 ¦ MAIN-010-C23 ¦ MAIN-010-C25 ¦ MAIN-010-C26 ¦ MAIN-010-C27 ¦ MAIN-010-C28 ¦ MAIN-010-C29 ¦ MAIN-010-C3 ¦ MAIN-010-C30 ¦ MAIN-010-C31 ¦ MAIN-010-C32 ¦ MAIN-010-C33 ¦ MAIN-010-C34 ¦ MAIN-010-C35 ¦ MAIN-010-C4 ¦ MAIN-010-C45 ¦ MAIN-010-C49 ¦ MAIN-010-C5 ¦ MAIN-010-C50 ¦ MAIN-010-C51 ¦ MAIN-010-C60 ¦ MAIN-010-C62 ¦ MAIN-010-C65 ¦ MAIN-010-C66 ¦ MAIN-010-C68 ¦ MAIN-010-C7 ¦ MAIN-010-C71 ¦ MAIN-010-C73 ¦ MAIN-010-C74 ¦ MAIN-010-C8 | Capacitor | Murata | GRM155R71E104KE14D | 0402 | 100 nF 25 V X7R | COMMON | FITTED | 35 | 2 | 1 | 41 | 1435 | 0 | 1435 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-078 | PR-078 | PCB-MAIN | MAIN-010-C37 | Capacitor | Murata | GRM155R71E224KE14D | 0402 | 220 nF 25 V X7R | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-079 | PR-079 | PCB-MAIN | MAIN-010-C38 | Capacitor | Murata | GRM155R71E473KA01D | 0402 | 47 nF 25 V X7R | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-080 | PR-080 | PCB-MAIN | MAIN-010-C77 | Capacitor | Murata | GRM155R72A472KA01D | 0402 | 4.7 nF 100 V X7R | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-081 | PR-081 | PCB-MAIN | MAIN-010-C13 ¦ MAIN-010-C20 ¦ MAIN-010-C24 ¦ MAIN-010-C6 ¦ MAIN-010-C61 ¦ MAIN-010-C67 ¦ MAIN-010-C72 ¦ MAIN-010-C75 | Capacitor | Murata | GRM188R61A106KE69D | 0603 | 10 uF 10 V X5R | COMMON | FITTED | 8 | 2 | 1 | 41 | 328 | 0 | 328 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-082 | PR-082 | PCB-MAIN | MAIN-010-C19 | Capacitor | Murata | GRM21BR61A226ME44L | 0805 | 22 uF 10 V X5R | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-083 | PR-083 | PCB-PWR | U-MON-01 | Monitor | Texas Instruments | INA226AIDGSR | VSSOP-10 |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED | SELECTED_REV_A_12PIN_I2C | Authorized distributor | Marking I2C ID calibration and reference-meter compare | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-084 | PR-084 | PCB-MAIN | U3 | Motion | STMicroelectronics | LIS2DW12TR | LGA-12_2x2mm |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SAMPLE | Authorized distributor | Marking orientation WHO_AM_I and self-test | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-085 | PR-085 | PCB-PWR | PWR-REV-CTL | Protection | Texas Instruments | LM74700QDBVRQ1 | SOT-23-6 |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SCHEMATIC_SAMPLE | Authorized distributor | Marking reverse test and gate waveform | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-086 | PR-086 | PCB-PWR | U-PWR1 ¦ U-PWR2 | Power | Texas Instruments | LMR604403SRAKR | RAK-9 |  | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 20 | 102 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_DESIGN_CALC_SAMPLE | Authorized distributor | Load step ripple efficiency sleep current thermal and EMI ¦ Load step ripple efficiency thermal and EMI | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-087 | PR-087 | PCB-MAIN | MAIN-010-L1 | Inductor | Murata | LQH32PN2R2NN0L | 1210 | 2.2 uH 20% | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-088 | PR-088 | PCB-MAIN | MAIN-010-L2 | Inductor | Murata | LQW15AN27NJ00D | 0402 | 27 nH 5% | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-089 | PR-089 | PCB-MAIN | MAIN-010-U5 | Operational_Amplifier | Analog Devices | LT6000IDCB#TRMPBF | DFN-6_DCB_2x3mm | Single rail-to-rail low-power op amp | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-090 | PR-090 | PCB-MAIN | U9 | GNSS | u-blox | MAX-M10S-00B | LCC-18_9.7x10.1mm |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_GNSS_RF_TIMING_SAMPLE | Authorized distributor or traceable module channel | Marking firmware satellite fix PPS test | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-091 | PR-091 | PCB-MAIN | U11 | BLE | Raytac | MDBT50Q-P1MV2 | nRF52840_SMD_10.5x15.5_61P_PCB_antenna |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_ENCLOSURE_RF | Raytac authorized channel or traceable distributor | Module label firmware BLE 2M coded PHY pairing OTA current RF range and temperature test | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-092 | PR-092 | PCB-MAIN | J-SD1 | Connector | GCT | MEM2052-00-195-00-A | microSD push-push SMT 1.95 mm with detect |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | MECHANICAL_AUTHORITY_FROZEN_PENDING_PHYSICAL_TEST | Authorized GCT distributor | Mating detect coplanarity and cycle sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-093 | PR-093 | PCB-MAIN | Q-MODEM-PWRKEY ¦ Q-MODEM-RESET ¦ Q-SIM-MUX-EN | Transistor | Nexperia | MMBT3904,215 | SOT23 |  | COMMON | FITTED | 3 | 2 | 1 | 41 | 123 | 30 | 153 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_CONTROL_TIMING_SAMPLE ¦ SELECTED_PENDING_SIM_SAFE_STATE_SAMPLE | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-094 | PR-094 | PCB-MIC | MK1 | Microphone | TDK InvenSense | MMICT5838-00-012 | LGA-CAV-5 3.5x2.65x0.98 mm |  | COMMON | FITTED | 4 | 2 | 1 | 41 | 164 | 32 | 196 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SAMPLE | TDK authorized channel and same lot requested | Marking lot acoustic sensitivity noise phase and port inspection | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-095 | PR-095 | PCB-PWR | PWR-NET-TIE | PCB feature | PCB fabrication | NET_TIE_COPPER_REV_A | NetTie-2 SMD pad 0.5 mm | 2-pad copper net tie | COMMON | PCB_FEATURE | 3 | 2 | 1 | 41 | 123 | 0 | 123 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | LOCKED_LAYOUT_PENDING | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-096 | PR-096 | PCB-MAIN | MAIN-010-D3 ¦ MAIN-010-D5 | RF_ESD | Nexperia | PESD5V0C1BSF | SOD962-2 | 5 V bidirectional 0.2 pF RF ESD | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 0 | 82 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-097 | PR-097 | PCB-MAIN | MAIN-010-D1 ¦ MAIN-010-D2 | Supply_TVS | Nexperia | PESD5V0S1UL | SOD882 | 5 V unidirectional 150 W TVS | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 0 | 82 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-098 | PR-098 | SYSTEM | MPPT-TEMP | Sensor | Victron Energy | SBS050150200 | Smart Battery Sense long range up to 10 m radio with 0.45 m leads and M10 eyelets |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 2 | 43 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Victron authorized distributor; exact SBS050150200 only; no substitution | Reconcile PO packing slip quantity and visible damage; verify 0.45 m lead M10 eyelets retention on the battery M8 terminals accuracy VE.Smart pairing cutoff reconnect and network retention during station assembly EOL and cold EVT | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-099 | PR-099 | SYSTEM | MPPT1 | Controller | Victron Energy | SCC075010060R | 100x113x40 mm IP43 electronics IP22 terminals |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 2 | 43 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Victron authorized distributor; exact SCC075010060R only; no substitution | Reconcile PO packing slip quantity and visible damage; bind article and firmware at installation; export configuration and test charge profile reverse current quiescent thermal and cutoff during assembly EOL and EVT | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-100 | PR-100 | PCB-MAIN | U12 | Storage | Kingston | SDCIT2/32GB | microSD_card_8_contact |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SAMPLE_ENDURANCE | Kingston authorized channel | CID capacity full write/read temperature and power-loss sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-101 | PR-101 | SYSTEM | PV1 | Solar panel | SLD Tech / Solarland | SLP080S-12M | 1475x342x40 mm framed 36-cell panel |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 2 | 43 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | SLD Tech or authorized distributor; exact SLP080S-12M only; no substitution | Reconcile PO packing slip quantity and visible transit damage; measure installed-unit Voc and perform IV insulation wet-leakage cold-Voc bracket cable and transport validation during assembly and EVT | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-102 | PR-102 | PCB-PWR | PWR-TVS-01 | Protection | Littelfuse | SMBJ18A | SMB_DO-214AA |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | CANDIDATE_PENDING_SURGE_PROFILE | Authorized distributor | Marking clamp pulse and thermal sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-103 | PR-103 | PCB-MAIN | U18 | Logic | Texas Instruments | SN74AXC1T45DRLR | SOT-5X3_6 |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_AAD_WAKE_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-104 | PR-104 | PCB-MAIN | U16 ¦ U7 | Level translator ¦ Logic | Texas Instruments | SN74AXC8T245PWR | TSSOP-24 |  | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 20 | 102 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SI_AAD_SAMPLE ¦ SELECTED_PENDING_UART_POWER_SAMPLE | Authorized or traceable tier-1 channel ¦ Do not substitute auto-direction device without review | Logic levels direction leakage sleep test ¦ Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-105 | PR-105 | PCB-MAIN | MAIN-010-U6 | Open_Drain_Buffer | Texas Instruments | SN74LVC1G07DBVR | SOT-23-5_DBV | Single non-inverting open-drain buffer | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-106 | PR-106 | PCB-MAIN | U17 | Logic | Texas Instruments | SN74LVC32APWR | TSSOP-14 |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_AAD_WAKE_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-107 | PR-107 | PCB-MAIN | U1 | MCU | STMicroelectronics | STM32U585VIT6Q | LQFP100_14x14 |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_TARGET_SAMPLE | Authorized distributor or traceable tier-1 China channel | Label lot date code package X-ray sample ID readout | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-108 | PR-108 | PCB-MAIN | U4 | Temperature | STMicroelectronics | STTS22HTR | UDFN-6L_2x2mm |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_ASSEMBLY_REVIEW | Authorized distributor | X-ray sample ID and temperature compare | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-109 | PR-109 | PCB-MAIN | MAIN-010-Q4 | Dual_MOSFET | Vishay | Si1016X-T1-GE3 | SOT-563_SC-89 | Complementary N and P channel 20 V | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-110 | PR-110 | PCB-MAIN | X1 | Clock | SiTime | SiT1552AI-JE-DCC-32.768D | CSP-4_1.5x0.8mm | 32.768 kHz full-swing LVCMOS | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_LSE_BYPASS_REVIEW | Authorized distributor | Frequency and current sample test | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-111 | PR-111 | PCB-MAIN | MAIN-010-C36 ¦ MAIN-010-C44 | Capacitor | KEMET | T520D107M006ATE015 | 7343-31 | 100 uF 6.3 V 15 mOhm polymer | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 0 | 82 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-112 | PR-112 | SYSTEM | ANT-LORA | Antenna | Taoglas | TI.89.B.2111W | IP67 terminal antenna 180x13 mm SMA(M) |  | RU868_PILOT | FITTED | 1 | 2 | 1 | 41 | 41 | 4 | 45 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED | CONTROLLED_EVT_PURCHASE_EXACT_MPN_VALIDATION_DURING_ASSEMBLY_EVT | Taoglas or established distributor; exact TI.89.B.2111W only; no substitution | Reconcile PO packing slip quantity and visible damage; verify connector mate installed VSWR conducted power sensitivity coexistence and RU868 radiated compliance during assembly EOL and EVT | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-113 | PR-113 | PCB-MAIN | MAIN-010-D10 ¦ MAIN-010-D11 ¦ MAIN-010-D6 ¦ MAIN-010-D7 ¦ MAIN-010-D8 ¦ MAIN-010-D9 | ESD_Diode | Texas Instruments | TPD1E05U06DYAR | SOD-523_DYA | 5.5 V 0.5 pF ESD | COMMON | FITTED | 6 | 2 | 1 | 41 | 246 | 0 | 246 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-114 | PR-114 | PCB-MAIN | MAIN-010-D4 | RF_ESD | Texas Instruments | TPD1E05U06DYAR | SOD-523_DYA | 5.5 V unidirectional 0.5 pF RF ESD | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 0 | 41 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-115 | PR-115 | PCB-MAIN | MAIN-010-U25 ¦ MAIN-010-U26 | USB_ESD_Array | Texas Instruments | TPD2EUSB30DRTR | SOT-9X3_DRT | 2 channel 0.7 pF USB ESD | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 0 | 82 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-116 | PR-116 | PCB-MAIN | MAIN-010-U19 ¦ MAIN-010-U20 ¦ MAIN-010-U21 ¦ MAIN-010-U22 ¦ MAIN-010-U23 ¦ MAIN-010-U24 ¦ MAIN-010-U27 | ESD_Array | Texas Instruments | TPD4E05U06DQAR | USON-10_DQA | 4 channel 0.5 pF ESD | COMMON | FITTED | 7 | 2 | 1 | 41 | 287 | 0 | 287 | NONE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_REVIEW_A | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-117 | PR-117 | PCB-PWR | U-PWR3 | Power | Texas Instruments | TPS7A2018PDBVR | SOT-23-5 |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_NOISE_SAMPLE | Authorized distributor | Noise PSRR dropout thermal and AAD sleep current | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-118 | PR-118 | PCB-MAIN | U13 | SIM switch | Texas Instruments | TS3A27518EPWR | TSSOP-24_PW |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_USIM_SI_SAMPLE | Authorized distributor or traceable tier-1 channel | Marking supply leakage Ron capacitance and 100 switch cycles | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-119 | PR-119 | PCB-MAIN | J-RF-CELL ¦ J-RF-GNSS | RF connector | Hirose | U.FL-R-SMT-1(60) | U.FL SMT receptacle |  | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 32 | 114 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | LAYOUT_ZONE_FROZEN_PENDING_RF_VALIDATION | Authorized Hirose distributor | Visual mate gauge continuity VNA and VSWR ¦ Visual mate gauge continuity receiver sensitivity and active-antenna current | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-120 | PR-120 | PCB-MAIN | J-RF-LORA | RF connector | Hirose | U.FL-R-SMT-1(60) | U.FL SMT receptacle |  | RU868_PILOT | FITTED | 1 | 2 | 1 | 41 | 41 | 16 | 57 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | LAYOUT_ZONE_FROZEN_PENDING_RF_VALIDATION | Authorized Hirose distributor | Visual mate gauge continuity conducted power sensitivity and VSWR | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-121 | PR-121 | PCB-MAIN | J-USB | Connector | GCT | USB4105-GF-A-120 | 16 positions |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | MECHANICAL_AUTHORITY_FROZEN_PENDING_PHYSICAL_TEST | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-122 | PR-122 | PCB-MAIN | U2 | Memory | Winbond | W25Q512JVFIQ | SOIC-16_300mil |  | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 10 | 51 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_SAMPLE | Authorized or traceable LCSC-class channel | Marking electrical ID read/write/erase soak | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-123 | PR-123 | PCB-PWR | R-SHUNT-01 | Shunt | Vishay Dale | WSK2512R0100FEA | WSK2512 4-terminal 6.35x3.18 mm | 10 mOhm 1% 1 W | COMMON | FITTED | 1 | 2 | 1 | 41 | 41 | 20 | 61 | SCALE_CEIL_FROM_20_BASELINE | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_KELVIN_LAYOUT_SAMPLE | Authorized current-sense resistor vendor | Resistance TCR marking and four-wire reference measurement | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench
PG-124 | PR-124 | PCB-PWR | PWR-L | Passive | Coilcraft | XAL7030-472MEC | XAL7030 | 4.7 uH +/-20% | COMMON | FITTED | 2 | 2 | 1 | 41 | 82 | 20 | 102 | FIXED_LOT_MIN | COMMON_PROGRAM_PROCUREMENT | CONTROLLED_PENDING_VERIFICATION | SELECTED_PENDING_LAYOUT_THERMAL_EMI | Authorized or traceable tier-1 channel | Marking MPN package orientation electrical functional sample | TWO_EVT20_PRODUCTION_SETS_PLUS_ONE_BENCH; two EVT-20 reserve pools; no third reserve pool for bench